{"text_format":"1","workbook":"xlsx","n_sheets":31,"sheets":["Version Info","Issues","Cover Sheet","formats","AN - Air","AN - Maritime","AN - Other","PN - Air","PN - Maritime","PN - Other","TS - Air","TS - Maritime","TS - Other","NIS","SP EXP","SP IMP","GUM-C2","CCI-P1","CCI-P2","NCTS-P5","(CTC) NCTS-P5","NCTS-P6","AES-C1","AES-C2","ICS2-R3","PoUS-P1","PoUS-P2","Consolidation","Derogations","AUX_List","ICS2(1)"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":4,"defined_names":35,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Version Info","index":0,"n_rows":90,"n_cols":5,"rows_kept":90,"cut":false,"hidden":true,"merged":[]}
["This sheet will be hidden"]
["Record #","Version","Date","Subject","Change Description"]
[1,1,"2016-11-25",null,"Initial version for publication"]
[2,1.1000000000000001,"2016-12-14","DK","Updated note to all project tabs"]
[3,1.1100000000000001,"2017-01-31","BG","Introduction of PM contacts based on BGs version 2.00 for all projects"]
[4,2,"2017-03-24","PL","Provisional planning for AES(2), TES-AES(1), IMP, NA, PN, TES(PoUS)\nUpdated note for SP_EXP, SP_IMP"]
[5,2,"2017-03-29","SI","Updated dates for SP_EXP, SP_IMP, AES(2), IMP, GUM, NA, PN, TS, TES-PoUS, TES-NCTS"]
[6,2,"2017-04-04","LV","Updated dates for IMP, SP_IMP, TS, PN, NA"]
[7,2,"2017-04-05","EE","Updated dates for SP_EXP, SP_IMP, AES(2), IMP"]
[8,2,"2017-04-07","DK","Initial dates for operations"]
[9,2,"2017-04-07","SE","Updated note on SP_IMP"]
[10,2,"2017-04-20","other","Following countries indicate no change BG, CY, CZ, FI, FR, HU, IE, LT, NL, PT"]
[11,3,"2017-10-18","DK","PM change for GUM"]
[12,3,"2017-10-18","FI","Indicative dates for IMP, SP_IMP, NA, PN, TS"]
[13,3,"2017-10-18","LV","Dates updated for IMP, SP_IMP, TS"]
[14,3,"2017-10-18","LT","Dates updated for SP_EXP, SP_IMP, AES, IMP, GUM, NA, PN, TS, TES-NCTS"]
[15,3,"2017-10-18","IE","Dated updated for SP_EXP, AES(2)"]
[16,3,"2017-10-18","SI","Dates updated for SP_EXP, AES(2), GUM, NA, PN, TS, TES-PoUS, TS-NCTS, TES-AES(1)"]
[17,3,"2017-10-18","GR","Updated 'Version' and 'Issue Date'\nChanged quarter indicators to dates (Q1 = 01/01, Q2 = 01/04, etc.)\nUpdated SP_IMP\nUpdated PMs"]
[18,3,"2017-10-18","PL","Version 3.00 (instead of 0.3) and Issue Date 04/10/2017: AES(2), IMP, TES-AES(1), NA, PN, TES-PoUS, SP_EXP, SP_IMP\nUpdated note: IMP, SP_EXP, SP_IMP  //  Updated PM: TES-PoUS\nUpdated dates: NA, SP_EXP, SP_IMP  //  Updated status: SP_EXP, SP_IMP"]
[19,3,"2017-10-18","SE","Updated 'Version' and 'Issue Date'\nUpdated dates/status: SP_EXP, AES(2), IMP, GUM, PN, TS\nUpdated comments: SP_IMP, AES(2), NA, PN, TS"]
[20,3,"2017-10-18","other","Addition of the \"Issues\"-tab"]
[21,3,"2017-10-30","SI","Operations dates updated for NA, PN & TS"]
[22,3,"2017-10-30","BG","Dates updated for SP_EXP, SP_IMP, AES(2), IMP, GUM, NA, PN, TS"]
[23,3,"2017-10-30","CY","Technical Specs dates updated for NA, PN & TS"]
[24,3,"2017-11-09","ES","All dates for IMP have been deleted, note has been added."]
[25,3,"2017-11-09","ES","Dates updated for GUM, NA, PN, TS"]
[26,3,"2017-11-09","ES","All dates deleted for TES-PoUS, TES-NCTS, TES-AES(1)"]
[27,3,"2017-11-09","ES","Changed Version Number to 2.00 and Issue Date to 08/11/2017"]
[28,3.1,"2018-02-09","BE","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updates for AES. Changed quarter indicators to dates (end of quarter if single date, beginning of quarter till the end of quarter if window)"]
[29,3.1,"2018-02-09","CY","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2)."]
[30,3.1,"2018-02-09","CZ","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2)."]
[31,3.1,"2018-02-09","DE","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2), TES-AES(1) & TES-NCTS."]
[32,3.1,"2018-02-09","DK","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2)."]
[33,3.1,"2018-02-09","EE","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2)."]
[34,3.1,"2018-02-09","ES","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updates for AES(2), TES-AES(1) [agreed to align to the planning of AES(2)] & TES-NCTS. Changed quarter indicators to dates (end of quarter if single date, beginning of quarter till the end of quarter if window)"]
[35,3.1,"2018-02-09","GR","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2)."]
[36,3.1,"2018-02-09","HR","Changes are related to the \"Comparison National Plan & Scoping AES\". Updates for both AES(2) and TES-NCTS: Dates updated -> changed quarter indicators to dates (end of quarter if single date, beginning of quarter till the end of quarter if window). Updated 'Version', 'Issue Date' and Project Manager Details."]
[37,3.1,"2018-02-09","HU","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2), TES-AES(1) & TES-NCTS."]
[38,3.1,"2018-02-09","LV","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2)."]
[39,3.1,"2018-02-09","MT","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2)."]
[40,3.1,"2018-02-09","NL","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2)."]
[41,3.1,"2018-02-09","SI","Changes are related to the \"Comparison National Plan & Scoping AES\": Dates updated for AES(2)."]
[42,3.1,"2018-02-09","FI","Changes are related to the \"Comparison National Plan & Scoping AES\":\nDates updated for IMP, SP_IMP, NA, PN, TS, TES-NCTS, TES-AES(1), TES-PoUS"]
[43,4,"2018-04-17","FI","Updated 'Deployment' dates/status: IMP, SP_IMP, NA, PN, TS, TES-NCTS, TES-PoUS \nChanged quarter indicators to dates (end of quarter if single date, beginning of quarter till the end of quarter if window)"]
[44,4,"2018-04-17","SI","Updated dates/status: SP_EXP, SP_IMP, IMP, GUM, NA, PN, TS, TES-NCTS, TES-AES(1)\nUpdated 'Version' and 'Issue Date'"]
[45,4,"2018-04-17","IE","Updated dates/status/Project Mgr, eMail, Phone: TES-NCTS\nUpdated dates/status: TES-AES(1)\nUpdated 'Version' and 'Issue Date'"]
[46,5,"2018-09-07","NL","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS, but only for Deployment and Operations"]
[47,5,"2018-09-07","CY","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS"]
[48,5,"2018-09-07","DK","Dates and/or status updated for AES2 (for the rest dates remained as in April 2018)."]
[49,5,"2018-09-07","ES","Dates and/or status updated for SP_EXP, SP_IMP, AES(2), NA, PN, TS, TES-PoUS, TES-NCTS, TES-AES(1)"]
[50,5,"2018-09-07","FI","Dates and/or status updated for SP_EXP, AES(2), IMP, NA, PN, TS, TES-PoUS, TES-NCTS, TES-AES(1)\nAdded note for SP_EXP, AES(2)"]
[51,5,"2018-09-07","FR","Dates and/or status updated for SP_EXP, SP_IMP, AES(2), IMP\nDeleted status indication for AES(2)"]
[52,5,"2018-09-07","AT","Dates and/or status updated for SP_EXP, AES2, IMP, GUM, NA, PN, TS\nAdded note for SP_EXP, AES(2) and GUM"]
[53,5,"2018-09-07","HU","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS"]
[54,5,"2018-09-07","SI","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS, TES-PoUS, TES-NCTS, TES-AES(1)"]
[55,5,"2018-09-07","GR","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS, TES-PoUS, TES-NCTS, TES-AES(1)"]
[56,5,"2018-09-07","SE","Dates and/or status updated for SP_EXP, AES2, IMP, GUM, PN, TS"]
[57,5,"2018-09-07","LT","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS, TES-PoUS, TES-NCTS, TES-AES(1)"]
[58,5,"2018-09-07","EE","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS, TES-NCTS, TES-AES(1)"]
[59,5,"2018-09-10","CZ","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS, TES-NCTS, TES-AES(1)"]
[60,5,"2018-09-18","LV","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS, TES-PoUS, TES-NCTS, TES-AES(1)"]
[61,5,"2018-09-19","IE","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS, TES-NCTS, TES-AES(1)"]
[62,5,"2018-09-19","HU","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS"]
[63,5,"2018-09-20","IT","Dates and/or status, Project Managers updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS"]
[64,6,"2018-09-27","DK","Dates and/or status, Project Managers updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS"]
[65,6,"2018-09-27","HR","Dates and/or status, Project Managers updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS, TES-NCTS, TES-AES(1), TES-PoUS"]
[66,7,"2018-10-11","MT","Dates and/or status updated for SP_EXP, SP_IMP, AES2, IMP, GUM, NA, PN, TS, TES-NCTS, TES-AES(1), TES-PoUS"]
[67,8,"2019-05-23","Spring 2019","Bi-annual update for Spring 2019 (AT, CY, DE, DK, EE, ES, FI, FR, GR, HU, HR, IE, LT, LV, NL, PT, RO, SE, SI reporting)"]
[68,9,"2019-09-12","September 2019 intermediate update","Updated version based on the information received from MSs. Updated dates for:\nAT as per mail on the 8/8 v5.00.    \nCZ as per mail on the 1/8. \nHR as per mail on the 9/7/19 version 4.00. \nIE as per mail on 1/8. \nLU as per 20190606bis version. \nMT as per mail on 4/7. \nPL as per mail on 3/6 revised version. \nSK as per mail on 8/7/19 version 1.00. "]
[69,10,"2019-10-01","Oct-19, post-survey","Updated version based on the information received from MSs. Updated dates for:\nBE as per mail on 12/9\nDK as per mail on 18/9\nES as per mail on 18/9\nFR updated NPM as per mail on 17/9\nGR NP as per mail on 17/9\nIE as per mail on 13/9\nMT as per survey replies on 12/9\nPL AES1+2 as per mail on 19/9\nSE as per mail on 18/9 with NP\nSK as per mail on 17/9\nBG as per mail on the 20/09\nEE as per mail on the 23/09\nLV as per phonecall on the 23/09\nCY as per mail on 17/09"]
[70,10.1,"2019-10-09","Oct-19, SfA2 ","BG as per mail on 3/10\nRO as per mail on 4/10\nSI as per mail on 1/10"]
[71,11,"2020-01-29","2020-01-01","AT as per mail on 31/1/20\nBG as per mail on 24/1/20\nCZ as per mail on 28/1/20\nDK as per mail on 31/1/20\nES as per mail on 30/1/20\nFI as per mail on 27/1/20\nFR as per mail on 27/1/20\nIE as per mail on 24/1/20\nLT as per mail on 31/01/20\nPL as per mail on 31/1/20\nPT as per mail on 30/01/20 \nRO as per mail on 29/1/20 -->RO only updated 4 projects, assumed the rest remained the same\nSE as per mail on 30/01/20\nSI as per mail on 15/1/20\nSK as per mail on 31/1/20\nUK has been removed\nHR as per mail on 11/02/20"]
[72,12.1,"2020-05-29","Jan-20 Update - Final","BE as per mail on 02/04/2020\nCY as per mail on 16/03/2020\nCZ as per UCC Annual Report Survey Response for CCI P2\nDE as per mail on 23/03/2020\nEE as per mail on 16/03/2020\nFI as per mail on 18/05/2020 (CCI P2)\nGR as per mail on 15/03/2020\nLV as per mail on 05/03/2020\nMT, HU, IT and NL - confirmed, no changes, updated date\nRO as per mail on 13/05/2020\nNCTS and AES planning from unit B3 - Email from 29/05/2020 Q2 2020 Report"]
[73,13,null,"2020-06-01","AT as per mail on 30/06/2020\nBG as per mail on 29/06/2020, no change to dates, only one phone number updated\nCZ as per mail on 22/06/2020\nEE as per mail on 30/06/2020\nFR as per mail on 06/07/2020\nHU as per mail on 29/06/2020\nIE as per mail on 23/06/2020\nLT as per mail on 30/06/2020\nNL as per mail on 30/06/2020\nPL as per mail on 08/07/2020\nSE as per mail on 30/06/2020\nSI as per mail on 11/06/2020\n"]
[74,13.1,"2020-07-16","June Update","ES per mail on 16/07/2020\n"]
[75,14,"2020-09-17","Sept Update (DK)","DK per mail on 14/09/2020\n"]
[76,15,"2021-02-08","2021-01-01","AT as per mail on 29/01/2021\nCZ as per mail on 01/02/2021\nDK as per mail on 27/01/2021\nEE as per mail on 29/01/2021\nES as per mail on 29/01/2021\nFI as per mail on 07/12/2020\nFR as per mail on 29/01/2021\nHU as per mail on 29/01/2021\nIE as per mail on 08/02/2021\nLT as per mail on 29/01/2021\nLV as per mail on 15/12/2020\nRO as per mail on 29/01/2021\nSE as per mail on 09/02/2021\nSI as per mail on 18/01/2021\n"]
[77,16,"2021-07-07","2021-06-01","CZ as per mail on 30/06/2021\nDK as per mail on 01/07/2021\nEE as per mails on 03/06/2021 and 06/07/2021\nES as per mail on 21/05/2021\nFI as per mail on 29/06/2021\nFR as per mail on 30/06/2021\nIE as per mail on 28/06/2021\nLT as per mail on 30/06/2021\nLV as per mail on 19/05/2021\nPL as per mail on 05/07/2021\nPT as per mail on 29/06/2021\nSE as per mail on 28/06/2021\nSI as per mail on 30/06/2021"]
[78,16.100000000000001,"2021-07-14","2021-06-01","NL as per mail on 02/07/2021"]
[79,16.2,"2021-07-14","2021-06-01","Updated NL's version date to 02/07/2021 for all projects "]
[80,17,"2021-09-14","2021-09-01","HU as per mail on 08/09/2021"]
[81,"17.10","2021-10-29","2021-10-01","LV and PL as per mail on 06/10/21 and 07/10/2021"]
[82,"17.20","2021-11-09","2021-11-01","Corrected some local links on the MS cells, following comments raised on the SfR"]
[83,17.3,"2021-11-19","2021-11-01","Integrated Planning for SE"]
[84,18,"2022-02-18","2022-01-01","Consolidate National Planning responses for January 2022"]
[85,19,"2022-02-24","2022-01-01","SfA for Jan-22 Consolidation (updated GR data) + Updated country list and version information formulas"]
[86,20,"2022-02-28","2022-01-01","SfA Only for BE, DK, HR and RO consolidation of updates"]
[87,25,"2023-01-03","2023-03-23","SfA Only for DK consolidation of updates"]
[88,25.01,"2023-02-03","2023-03-23","SfA Only for ES consolidation of updates"]

{"sheet":"Issues","index":1,"n_rows":52,"n_cols":7,"rows_kept":52,"cut":false,"hidden":true,"merged":[]}
["Comment Date","Project2","Country","Phase","Issue","Proposal / Assumption","Status"]
[null,"NA","SI","Operations","Date of Operations is before Technical Specs, must be updated","01/03/2022 (aligned to date of deployment)","Updated conform MS respons on 30/10/2017"]
[null,"PN","SI","Operations","Date of Operations is before Technical Specs, must be updated","01/03/2022 (aligned to date of deployment)","Updated conform MS respons on 30/10/2017"]
[null,"TS","SI","Operations","Date of Operations is before Technical Specs, must be updated","01/03/2022 (aligned to date of deployment)","Updated conform MS respons on 30/10/2017"]
[null,"SP_IMP","GR","CT","End date was not provided.","Date of deployment has been taken as the end date for CT."]
[null,"SP_EXP","ES","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
[null,"AES(2)","ES","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS","Updated conform MS respons on \"Comparison National Plan & Scoping AES\""]
[null,"AES(2)","HR","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS","Updated conform MS respons on \"Comparison National Plan & Scoping AES\""]
[null,"IMP","SK","CT, Depl, Migr, Op","Dates are in the past, can these be set to Stable/final?","Confirmation needed from MS"]
[null,"GUM","ES","Migr, Op","Dates are in the past, can these be set to Stable/final?","Confirmation needed from MS","Updated conform MS respons on 09/11/2017"]
[null,"NA","CY","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS","Updated conform MS respons on 30/10/2017"]
[null,"PN","CY","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS","Updated conform MS respons on 30/10/2017"]
[null,"TS","CY","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS","Updated conform MS respons on 30/10/2017"]
[null,"TES-PoUs","ES","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS","Updated conform MS respons on 09/11/2017"]
[null,"TES-NCTS","ES","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS","Updated conform MS respons on 09/11/2017"]
[null,"TES-AES(1)","ES","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS","Updated conform MS respons on 09/11/2017"]
["2018-04-17","SP_EXP","CY","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","SP_EXP","ES","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","SP_IMP","BG","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","SP_IMP","ES","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","SP_IMP","LV","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","AES(2)","FR","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","IMP","BG","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","IMP","LV","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","IMP","MT","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","GUM","BG","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","GUM","CZ","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","NA","BG","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","NA","IT","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","PN","BG","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","PN","IT","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","TS","BG","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","TS","IT","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","TES-PoUS","GR","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2018-04-17","TES-PoUS","LT","TS","Date is in the past, can this be set to Stable/final?","Confirmation needed from MS"]
["2019-08-29","All projects","SK","Migr, Op","No dates were provided in last version from 08/07/2019, deleted the existing dates in the consolidationas per the working instructions\n\nFor the National Import Systems Upgrade - SK marked stable/final for TS/CT but no dates","Confirmation needed from MS"]
["2019-08-29","NCTS2","HR","Deploy & Ops","Gave quarter of 2025 and also date from 2023","Assumed it was 2025"]
["2019-08-29","PoUS","HR","CT","Date of CT (Q2 2025) is later than the deployment (01/06/2025)"]
["2019-09-02","PoUS","MT","Deploy & Ops","date of operations is before date of deployment 3months "]
["2019-09-02","cci1","PL","TS & CT","conformance testing starts before TS"]
["2021-07-07","SP2","FI","Deploy & Ops","Date of operations is before deployment","Confirmation needed from MS"]
["2021-07-07","GUM2","PL","CT end and Ops","Date of CT and Ops is 30/09/2025 based on latest planning however confirmed by mail for the report that it should be updated to 02/06/2025 (did this in the NP and in the report however I left as-is for the NP).","Confirmation needed from MS"]
["2021-07-07","PoUS2","SI","Deploy and Ops","Date of operations is before deployment.","Confirmation needed from MS"]
["2021-10-29","GUM","PL","CT and deploy","Deployment is before CT"]
["2022-02-18","PoUS2",null,"Operations","Operations is before deployment","Assumed it was 2025 in fact"]
["2022-02-18","NCTS2","MT","Operations","Operations are before deployment (06/02/2024)","Assumed it was same as Deployment - 02/06/2025"]
["2022-02-28","PoUS2","HR","-","PoUS2 mistyped as NCTS2 in MS reply file, after PoUS1","Assumed it was PoUS based on cell position and dates"]
["2022-03-01","SP IMP, IMP","HR","Tech Specs","date provided is end 2021","Assumed it was Q4 2021 so the data input was 31/12/2021"]
["2022-02-28","ICS2-R2","DK","CT","CT End date is mismatched with the start date - 14.02.03","Assumed based on other relevant dates that it should have been 14.02.23"]
["2022-04-19","SP IMP","LV","Operations","Operations date is prior to deployment - 04/06/2017","Assumed it was in fact 04/06/2018"]
["2022-04-19","ICS2-R3","LV","Operations","Operations is prior to deployment","Assumed it was 2024 in fact"]
["2022-07-28","ICS2-R3","LU","Operations","Operations is prior to deployment- 30/06/2023","Assumed it was 2024 in fact"]

{"sheet":"Cover Sheet","index":2,"n_rows":9,"n_cols":6,"rows_kept":9,"cut":false,"hidden":false,"merged":[[0,0,0,2],[0,3,0,4],[0,5,0,6],[1,0,1,2],[1,3,1,4],[1,5,1,6],[13,0,13,6],[2,0,3,6],[4,0,4,6],[5,0,5,6],[6,0,7,6],[8,0,9,6],[10,0,11,6]]}
["Owner",null,null,"Issued",null,"Version"]
["DG TAXUD",null,null,"2025-02-17",null,28.1]
["Taxation and Customs Union DG"]
[]
[]
["SUBJECT:"]
[]
[]
["National Plans on the Implementation of the UCC Work Programme"]

{"sheet":"formats","index":3,"n_rows":29,"n_cols":7,"rows_kept":29,"cut":false,"hidden":true,"merged":[]}
["This sheet will be hidden"]
["Project Name","Project Type",null,"Country Code","Country",null,"Status"]
["UCC Notification of Arrival","National System",null,"AT","Österreich",null,"Stable/Final"]
["UCC Presentation Notification","National System",null,"BE","Belgique/België",null,"Indicative"]
["UCC Temporary Storage","National System",null,"BG","България"]
["UCC National Import Systems upgrade","National System",null,"CY","Κύπρος"]
["UCC Special Procedures (Component 1) \"National SP EXP\"","National System",null,"CZ","Česká republika"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","National System",null,"DE","Deutschland"]
["UCC Guarantee Management (Component 2) \"National GUM\"","National System",null,"DK","Danmark"]
["UCC Centralised Clearance for Import (Phase 1)","TES System",null,"EE","Eesti"]
["UCC Centralised Clearance for Import (Phase 2)","TES System",null,"GR","Ελλάδα"]
["UCC NCTS upgrade (Phase 5)","TES System",null,"ES","España"]
["UCC NCTS upgrade (Phase 6)","TES System",null,"FI","Suomi/Finland"]
["UCC AES (Component 1) \"Trans-European AES\"","TES System",null,"FR","France"]
["UCC AES (Component 2) \"National Export Systems upgrade\"","National System",null,"HR","Hrvatska"]
["UCC Import Control System 2 – Release 3","TES System",null,"HU","Magyarország"]
["UCC Proof of Union Status (PoUS) - Phase 1","TES System",null,"IE","Éire/Ireland"]
["UCC Proof of Union Status (PoUS) - Phase 2","TES System",null,"IT","Italia"]
[null,null,null,"LT","Lietuva"]
[null,null,null,"LU","Luxembourg"]
[null,null,null,"LV","Latvija"]
[null,null,null,"MT","Malta"]
[null,null,null,"NL","Nederland"]
[null,null,null,"PL","Polska"]
[null,null,null,"PT","Portugal"]
[null,null,null,"RO","România "]
[null,null,null,"SE","Sverige"]
[null,null,null,"SI","Slovenija"]
[null,null,null,"SK","Slovensko"]

{"sheet":"AN - Air","index":4,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,"UCC Notification of Arrival (AN) - Aircraft","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"2021-11-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-07-01","Stable/Final","Completed","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/2","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51433"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"2021-10-12","Stable/Final","Completed","2023-03-01","2023-06-30","Stable/Final","Completed","2023-06-30","Stable/Final","Completed","2023-06-30","2023-10-01","Stable/Final","Completed","2023-10-01","Stable/Final","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3.2,"2025-01-30"]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2022-03-28","Stable/Final","Completed","2022-12-01","2022-12-15","Stable/Final","Completed","2023-03-01","Stable/Final","Completed",null,null,null,null,"2023-03-01","Stable/Final","Completed","https://ep.customs.bg/eportal/",null,"The Commission implementing decision granting a derogation is applying from 1.3.2023 in respect of goods entering the customs territorry of the Union by air and from 1.3.2024 in respect of goods entering the customs territorry of the Union by maritime transport or inland waterways.",10.3,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-05-22","Stable/Final","Completed","2023-10-01","2025-03-10","Stable/Final","In progress","2025-03-31","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-03-31","Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,"Derogation was granted.",8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2023-09-01","Stable/Final","Completed","2023-11-01","2023-12-01","Stable/Final","Completed","2023-12-05","Stable/Final","Completed",null,null,null,null,"2023-12-05","Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,1.7,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"This \"message\" will be covered by the transeuropean system ICS2.  All Milestones affecting EO need to be considered in line with the ICS2 planning for Release 2 and Release 3 provided by EU-COM, especially in relation to the STI. ",null,7.01,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2021-09-01","Stable/Final","Completed","2023-06-15","2023-11-01","Stable/Final","Completed","2023-11-06","Stable/Final","Completed","2023-03-01","2023-10-31","Stable/Final","Completed","2023-10-31","Stable/Final","Completed","www.toldst.dk ",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-10-01","Stable/Final","Completed","2023-10-01","2023-10-01","Stable/Final","Completed","2023-10-01","Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo","Development according to ICS2 project plan.","A derogation request was accordingly submitted by EE on 06.07.2022.",20,"2025-02-10","Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-03-01","Stable/Final","Completed","2022-09-01","2023-10-02","Stable/Final","Completed","2023-03-01","Stable/Final","Completed","2023-03-01","2023-10-01","Stable/Final","Completed","2023-10-02","Stable/Final","Completed",null,null,null,3.2,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2022-06-30","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-03-31","Stable/Final","Completed","2023-03-31","2023-09-30","Stable/Final","Completed","2023-03-31","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,17,"2025-01-27"]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-06-30","Stable/Final","Completed","2023-06-30","2024-06-01","Stable/Final","Completed","2024-06-03","Stable/Final","Completed","https://www.douane.gouv.fr/services-aide/edi","Proposed via ICS release 2\nProgress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report","Updated planning",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2023-09-30","Stable/Final","Completed","2023-09-30","2024-12-31","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","2023-12-31","2023-12-31","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","https://www.aade.gr/customs","THE FUNCTIONALITY OR COMMON REPOSITORY IS USED","derogation request",7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2022-04-01","Stable/Final","Completed","2023-03-01","2023-07-01","Stable/Final","Completed","2023-07-01","Stable/Final","Completed","2023-07-01","2023-10-02","Stable/Final","Completed","2023-10-02","Stable/Final","Completed","https://carina.gov.hr ","EOs used DW for ICS2 R2 and R3, this was the period of inclusion in submitting AN via STI. As a rule, when an EO starts in ICS2 R2 or R3 (AIR and Maritime), he is required to submit AN via STI. DW expired.  ","Derogation for AN ",9.5,"2025-01-31","Sector for customs system","ICS2@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-07-03","Stable/Final","Completed","2023-12-16","2024-03-29","Stable/Final","Completed","2024-04-02","Stable/Final","Completed",null,null,null,null,"2024-04-02","Stable/Final","Completed","https://openkkk.nav.gov.hu/Megosztott%20dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FANPNTS&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D",null,"The developments are in progress.",1.1000000000000001,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2022-01-28","Stable/Final","Completed","2023-04-01","2023-06-01","Stable/Final","Completed","2023-07-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-07-01","Stable/Final","Completed","www.revenue.ie",null,null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2022-06-01","Stable/Final","Completed","2022-09-05","2022-12-12","Stable/Final","Completed","2022-12-13","Stable/Final","Completed",null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/an-pn-ts",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2020-06-01","Stable/Final","Completed","2022-10-15","2023-03-01","Stable/Final","Completed","2023-03-01","Stable/Final","Completed","2022-11-30","2023-10-01","Stable/Final","Completed","2023-10-01","Stable/Final","Completed","https://lrmuitine.lt/web/guest/1000","Lithuania will use central ICS2 R2 functionalinty for AN and not creating national system. ",null,14,"2025-01-31","Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_NA_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2021-12-14","Stable/Final","Completed","2022-10-01","2023-07-01","Stable/Final","Completed","2023-03-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-03-01","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/EOG.html",null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"N/A","stable/final","Not applicable","N/A","N/A","stable/final","Not applicable","2017-09-24","stable/final","Completed","N/A","N/A","Stable/Final","Not applicable","2017-09-25","stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Notification of arrival is now a part of ICS2.\n",null,3.2,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"2024-02-01","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started","www.customs.gov.mt",null,null,3.04,"2025-02-10"]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2021-12-31","Stable/Final","Completed","2023-03-01","2023-06-30","Stable/Final","Completed","2023-06-30","Stable/Final","Completed","2023-06-30","2023-10-01","Stable/Final","Completed","2023-10-01","Stable/Final","Completed","https://www.nhdouane.nl/",null,null,1.01,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2023-01-01","Stable/Final","Completed","2023-06-01","2023-09-30","Stable/Final","Completed","2023-07-01","Stable/Final","Completed","N/A ","N/A ","Stable/Final","Completed","2023-09-30","Stable/Final","Completed",null,null,"Poland was granted a derogation decision.AN functionalities are being developed within ICS2 system and according to its schedule.",0.2,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2022-07-31","Stable/Final","Completed","2022-12-01","2025-04-01","Indicative","In progress","2025-04-04","Indicative","Not started",null,null,null,null,"2025-04-07","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024","Projects 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nOngoing the activities and tests with airports Authorities;\nDevelopment and testing is ongoing.",7.5,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2022-04-13","Stable/Final","Completed","2024-05-01","2024-05-31","Stable/Final","Completed","2024-05-01","Stable/Final","Completed","N/A ","N/A ","Stable/Final","Completed","2024-05-01","Stable/Final","Completed","https://www.customs.ro/e-customs/ICS2/reglementari",null,null,"3.00","2025-02-10","Security and Safety Risk Analysis Service","ro.helpdesk.ics2@customs.ro",40216373051]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","2023-03-01","Stable/Final","Completed","2023-03-01","2023-03-01","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/arrivalnotificationformeansoftransport.4.422c8052175b1d8276959ea.html","We are going to use the central functionalities developed by the COM within the ICS2 project and the date of deployment and operational date follow the expected timelines from the different releases in this project. ",null,24,"2025-01-27","Intelligence Department","underrattelseavd.npm.ics2@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-03-01","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148","Use in ICS2 Arrival process for air cargo and STI foreseen to be in use for maritime in 2024 and other means of transport in 2025. No national solution is nedeed.",null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"2022-10-01","Stable/Final","Completed","2022-12-01","2023-02-14","Stable/Final","Completed","2023-03-01","Stable/Final","Completed",null,null,null,null,"2023-03-01","Stable/Final","Completed",null,"We use central solution via STI/HTI in ICS2-CR",null,1.04,"2025-01-27","Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]

{"sheet":"AN - Maritime","index":5,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,"UCC Notification of Arrival (AN) - Maritime","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html","Not applicabale because only air traffic in Austria",null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/2","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51433"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"2021-10-12","Stable/Final","Completed",null,null,null,null,"2024-06-03","Stable/Final","Completed","2024-06-03","2025-09-01","Stable/Final","In progress","2025-09-01","Stable/Final","In progress",null,null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},null,null,null,null,null,null,null,"2024-06-03","Stable/Final","Completed",null,null,null,null,"2024-06-03","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-05-22","Stable/Final","Completed","2023-10-01","2025-03-10","Stable/Final","In progress","2025-03-31","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-03-31","Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-12-05","Stable/Final","Completed",null,null,null,null,"2023-12-05","Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"This \"message\" will be covered by the transeuropean system ICS2.  All Milestones affecting EO need to be considered in line with the ICS2 planning for Release 2 and Release 3 provided by EU-COM, especially in relation to the STI. ",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2021-09-01","Stable/Final","Completed","2023-12-11","2024-12-04","Stable/Final","Completed","2024-05-25","Stable/Final","Completed","2024-06-03","2024-12-04","Stable/Final","Completed","2025-03-31","Stable/Final","In progress",null,null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","2024-06-03","Stable/Final","Completed","2024-06-03","2025-04-01","Stable/Final","In progress","2025-04-01","Stable/Final","In progress",null,null,"A derogation request was accordingly submitted by EE on 06.07.2022.",{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-03-01","Stable/Final","Completed","2023-10-01","2024-12-04","Stable/Final","Completed","2024-06-03","Stable/Final","Completed","2024-06-03","2024-12-04","Stable/Final","Completed","2024-12-04","Stable/Final","Completed",null,"NA for Martime aligned with ICS2 R3",null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2022-06-30","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","2024-06-30","2024-06-30","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","2024-06-03","Stable/Final","Completed","2024-06-03","2025-04-01","Stable/Final","In progress","2025-04-01","Stable/Final","In progress",null,null,"Updated planning",{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2023-09-30","Stable/Final","Completed","2023-09-30","2023-12-31","Stable/Final","Completed","2024-06-30","Stable/Final","In progress","2024-03-31","2025-03-31","Stable/Final","In progress","2024-06-30","Stable/Final","In progress","https://www.aade.gr/customs",null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"ICS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2022-11-07","Stable/Final","Completed","2024-06-03","2025-09-01","Stable/Final","In progress","2024-12-04","Stable/Final","Completed","2023-06-03","2024-12-04","Stable/Final","Completed","2024-12-04","Stable/Final","Completed","https://carina.gov.hr","For maritime transport start on 04.12.2024.regarding ICS2 R3 step 1.   EOs use STI for submission AN like for ISC R2.",null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","ICS2@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-07-03","Stable/Final","Completed","2023-12-16","2024-03-29","Stable/Final","Completed","2024-04-02","Stable/Final","Completed",null,null,null,null,"2024-04-02","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2022-01-28","Stable/Final","Completed","2023-12-01","2025-07-31","Stable/Final","In progress","2024-06-03","Stable/Final","Completed","2024-06-03","2025-07-31","Stable/Final","In progress","2025-07-31","Stable/Final","In progress","https://www.revenue.ie/","In accordance with Article 133 of UCC, where the informationon arrival is available to the customs authorities they may waive this notification. In IE we are provided with this information from our port and airport authorities and will not, therefore, require the operators to submit notifications of arrival to the STI until the implementation of ICS2 R3",null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2024-03-27","Stable/Final","Completed","2024-05-03","2024-05-31","Stable/Final","Completed","2024-06-03","Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2020-06-01","Stable/Final","Completed","2022-10-15","2024-06-01","Stable/Final","Completed","2024-06-03","Stable/Final","Completed","2024-06-03","01/04/2025","Stable/Final","In progress","01/04/2025","Stable/Final","In progress","https://lrmuitine.lt/web/guest/1000","Lithuania will use central ICS2 R2 functionalinty for AN and not creating national system. Economic operators ask to postpone the beginning of operation in accordance with ICS2 R2 deployment window. ",null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_NA_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable",null,null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"2022-01-10","Stable/Final","Completed","N/A","N/A","Stable/Final","Not applicable","2023-03-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Not applicable","2025-09-01","Stable/Final","In progress","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Information related to arrival is available to customs via International freight logistic and port information system administred by the Ministry of Transport. The process will be adjusted along with the end of transition for ICS2 R3 (systems is already operational in customs) for trade and implementation of Maritime SW",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"2024-06-01","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2023-09-01","Stable/Final","Completed","2024-01-01","29/02/2025","Indicative","In progress","2024-05-27","Stable/Final","Completed","2024-08-01","2025-04-01","Indicative","In progress","2025-09-01","Indicative","In progress",null,"NL is considering to combine the migration for traders for AN maritime with ICS2 R3, following a request from Trade",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2023-01-01","Stable/Final","Completed","2024-04-01","2024-12-04","Indicative","In progress","2024-06-03","Stable/Final","Completed","N/A ","N/A ",null,"Not applicable","2024-12-04","Stable/Final","Completed",null,null,"Poland was granted a derogation decision.AN functionalities are being developed within ICS2 system and according to its schedule.",{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2022-07-31","Stable/Final","Completed","2022-12-01","2025-04-01","Indicative","In progress","2025-04-04","Indicative","Not started",null,null,null,null,"2025-04-07","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024","Projects 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nOngoing the activities and tests with ports Authorities;\nEOs started testing;\nDevelopment and testing is ongoing.",{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2023-07-12","Indicative","In progress","2024-12-16","2025-09-01","Indicative","In progress","2024-12-16","Stable/Final","Completed","N/A ","N/A ",null,"Not applicable","2025-04-01","Indicative","In progress",null,null,null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Security and Safety Risk Analysis Service","ro.helpdesk.ics2@customs.ro",40216373051]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-03","Stable/Final","Completed","2024-06-03","2024-06-03","Stable/Final","Completed","2024-06-03","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/arrivalnotificationformeansoftransport.4.422c8052175b1d8276959ea.html","We are going to use the central functionalities developed by the COM within the ICS2 project and the date of deployment and operational date follow the expected timelines from the different releases in this project. ",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Intelligence Department","underrattelseavd.npm.ics2@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-02","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148","Use in ICS2 Arrival process for air cargo and STI foreseen to be in use for maritime in 2024 and other means of transport in 2025. No national solution is nedeed.",null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable",null,null,null,null,"N/A",null,"Not applicable",null,null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]

{"sheet":"AN - Other","index":6,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,"UCC Notification of Arrival (AN) - Road and rail transport","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","https://www.bmf.gv.at/themen/zoll/ACCS/ics2-import-control-system.html","Not applicabale because only air traffic in Austria",null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/2","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51433"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable",null,null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable",null,null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2024-06-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-01","Stable/Final","Completed",null,null,null,null,"2024-06-01","Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"This \"message\" will be covered by the transeuropean system ICS2.  All Milestones affecting EO need to be considered in line with the ICS2 planning for Release 2 and Release 3 provided by EU-COM, especially in relation to the STI. ",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","N/A","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable",null,"In reference to UCC article 133, notification of arrival is only applicable for a sea-going vessel or an aircraft entering the customs territory. \n ",null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"There is no Notification of Arrival in Road and Rail",null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"ICS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","https://carina.gov.hr","N/A","N/A",{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","ICS2@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-07-03","Stable/Final","Completed","2023-12-16","2024-03-29","Stable/Final","Completed","2024-04-02","Stable/Final","Completed",null,null,null,null,"2024-04-02","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","N/A ","N/A ",null,"Not applicable","N/A",null,"Not applicable",null,"N/A  Arrival for ICS2 Road is not required",null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_NA_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"2022-01-10","Stable/Final","Completed","2025-03-03","2025-09-01","Indicative","Not started","2025-09-01","Indicative","Not started","N/A","N/A","Stable/Final","Not applicable","2025-09-01","Indicative","Not started","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas",null,null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"2024-06-01","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable",null,null,null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2022-09-19","Stable/Final","Completed","2023-12-11","2025-08-31","Stable/Final","In progress","2025-04-01","Stable/Final","In progress","N/A","N/A",null,"Not applicable","2025-09-01","Stable/Final","Not started",null,null,"Poland was granted a derogation decision.AN functionalities are being developed within ICS2 system and according to its schedule.",{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-09-01","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Security and Safety Risk Analysis Service","ro.helpdesk.ics2@customs.ro",40216373051]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"N/A",null,"Not applicable","N/A",null,null,"Not applicable","N/A",null,"Not applicable","N/A",null,null,"Not applicable","N/A",null,"Not applicable","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/arrivalnotificationformeansoftransport.4.422c8052175b1d8276959ea.html","We are going to use the central functionalities developed by the COM within the ICS2 project and the date of deployment and operational date follow the expected timelines from the different releases in this project. ",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Intelligence Department","underrattelseavd.npm.ics2@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable",null,null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable",null,null,null,null,"N/A",null,"Not applicable",null,null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]

{"sheet":"PN - Air","index":7,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,"UCC Presentation Notification (PN) - Aircraft","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/3","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51434"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"2021-10-12","Stable/Final",null,"2023-03-01","2023-06-30","Stable/Final","Completed","2023-07-05","Stable/Final","Completed","2023-07-05","2023-12-31","Indicative","In progress","2023-12-31","Indicative","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2023-08-04","Stable/Final","Completed","2023-09-04","2023-10-16","Stable/Final","Completed","2023-11-10","Stable/Final","Completed",null,null,null,null,"2024-01-15","Stable/Final","Completed","https://ep.customs.bg/eportal/","In rеlation with the update of NIS, which was aligned with the requirements of the new Annex B.",null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-05-22","Stable/Final","Completed","2023-10-01","2025-03-10","Stable/Final","In progress","2025-03-31","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-03-31","Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,"Derogation was granted.",{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2023-09-01","Stable/Final","Completed","2023-11-01","2023-12-01","Stable/Final","Completed","2023-12-05","Stable/Final","Completed",null,null,null,null,"2023-12-05","Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"2020-10-09","Stable/Final","Completed","2021-05-01","2022-10-14","Stable/Final","Completed","2021-03-06","Stable/Final","Completed","2021-05-01","2022-10-14","Stable/Final","Completed","2022-10-31","Stable/Final","Completed","www.zoll.de","This \"message\" is updated as part of \"National Entry System\" of the national IT-System ATLAS (Release 9.1). The scope covers all modes of transport.",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2021-09-01","Stable/Final","Completed","2023-06-15","2023-11-01","Stable/Final","Completed","2023-11-06","Stable/Final","Completed","2023-03-01","2024-07-15","Stable/Final","Completed","2024-07-15","Stable/Final","Completed","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2020-12-31","Stable/Final","Completed","2020-12-01","2023-12-31","Stable/Final","Completed","2021-03-15","Stable/Final","Completed","2021-03-15","2023-12-31","Stable/Final","Completed","2021-03-15","Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo",null,"A derogation request was accordingly submitted by EE on 06.07.2022.",{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-06-30","Stable/Final","Completed","2023-10-01","2025-12-31","Indicative","In progress","2024-01-01","Stable/Final","Completed","2024-01-01","2025-12-31","Indicative","In progress","2026-01-01","Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,"Aligned with the granted derogation date.",{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2020-03-31","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2021-03-31","Stable/Final","Completed","2021-03-31","2021-03-31","Stable/Final","Completed","2021-03-31","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2023-03-31","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-03-06","Stable/Final","Completed","2024-06-03","2024-12-04","Stable/Final","Completed","2024-12-04","Stable/Final","Completed","https://www.douane.gouv.fr/services-aide/edi","Development in France of a notification of dischargement (like UCC Presentation Notification) – reassessment of business process on board – for 2019\nNA for TS and  CT as we use the European application\nProgress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report","Updated planning",{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2023-09-30","Stable/Final","Completed","2023-09-30","2024-12-31","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","2023-12-31","2023-12-31","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","https://www.aade.gr/customs","SOME INFORMATION OF G3 ARE NOT PRESENT","derogation request",{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"ICS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2022-03-31","Stable/Final","Completed","2022-11-01","2023-04-16","Stable/Final","Completed","2023-04-17","Stable/Final","Completed","N/A","N/A",null,"Not applicable","2023-04-17","Stable/Final","Completed","https://carina.gov.hr","This answer applies only within the presentation system that is being developed for the needs of ICS2. PN will be implemented as part of ICS2 for ICS2 R2 and R3(only for goods subject to ICS2) The implementation will be done in a step-by-step approach for the relevant modes of transport. The decision to develop PN as part of ICS2 inevitably leads to delays.  EOs will use DW for ICS2 R2 and R3 and will engage in electronic PN activities accordingly (AIR and MARITIME FINSHED).Other systems such as TS or the import system have their own presentation messages. \nThe mentioned activities refer to the Presentation Notification within the framework of Temporary Storage.","Derogation for PN ",{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","PNTS@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-07-03","Stable/Final","Completed","2023-12-16","2024-03-29","Stable/Final","Completed","2024-04-02","Stable/Final","Completed",null,null,null,null,"2024-04-02","Stable/Final","Completed","https://openkkk.nav.gov.hu/Megosztott%20dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FANPNTS&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D",null,"The developments are in progress.",{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2019-10-04","Stable/Final","Completed","2020-04-30","2021-10-04","Stable/Final","Completed","2020-11-23","Stable/Final","Completed","2020-11-23","2021-10-04","Stable/Final","Completed","2021-10-05","Stable/Final","Completed","www.revenue.ie","Will be updated to Revised Annex B in Q1 2026",null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2022-06-01","Stable/Final","Completed","2022-09-05","2022-12-12","Stable/Final","Completed","2022-12-13","Stable/Final","Completed",null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/an-pn-ts",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2022-07-01","Stable/Final","Completed","2022-10-15","2023-03-01","Stable/Final","Completed","2023-02-28","Stable/Final","Completed","2023-03-01","2023-10-01","Stable/Final","Completed","2023-10-01","Stable/Final","Completed","https://lrmuitine.lt/web/guest/1000","All modes of transport is in production.",null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_PN_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2021-12-14","stable/final","Completed","2022-10-01","2023-07-01","Stable/Final","Completed","2023-01-10","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-01-10","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS.html",null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"2017-06-05","Stable/Final","Completed","2017-08-01","2017-09-22","stable/final","Completed","2017-09-24","stable/final","Completed","N/A","N/A","stable/final","Completed","2017-09-25","stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Information related to presentation notification is a part of TS declaration. Since implementation of ICS R2 PN is also being submitted in ICS2 R2. ",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"2024-02-01","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started","www.customs.gov.mt",null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2022-09-01","Stable/Final","Completed","2023-11-06","2024-02-29","Stable/Final","Completed","2023-12-01","Stable/Final","Completed","2023-12-01","2024-02-29","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","https://www.nhdouane.nl/",null,null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2022-07-29","Stable/Final","Completed","2023-09-30","2025-04-30","Stable/Final","In progress","2025-04-20","Stable/Final","Not started","N/A","N/A ",null,"Not applicable","2025-05-01","Stable/Final","Not started",null,null,"Poland was granted a derogation decision.PN functionalities are being developed within national import system and according to its schedule.",{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2022-07-31","Stable/Final","Completed","2023-03-01","2025-04-01","Indicative","In progress","2025-04-04","Indicative","Not started",null,null,null,null,"2025-04-07","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024"," Projects 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nDevelopment and testing is ongoing.",{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2024-09-30","Stable/Final","Completed","2024-09-30","2024-12-31","Stable/Final","Completed","2024-11-14","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-11-14","Stable/Final","Completed","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn",null,null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","vama@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2022-12-01","Stable/Final","Completed","2023-09-27","2023-12-31","Stable/Final","Completed","2023-09-27","Stable/Final","Completed","2023-09-27","2023-12-31","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html",null,null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.ava.dtl@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2022-10-01","Stable/Final","Completed","2022-11-01","2023-02-01","Stable/Final","Completed","2023-03-01","Stable/Final","Completed","2023-03-01","2023-11-30","Stable/Final","Completed","2023-12-01","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148","","completed within the deadlines set by the derogation regulation",{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"2023-02-01","Stable/Final","Completed","2023-02-01","2023-08-31","Stable/Final","Completed","2023-10-01","Stable/Final","Completed",null,null,null,null,"2023-10-01","Stable/Final","Completed",null,"No standalone national presentation system. PN functionalities are implemented in all impacted systems.",null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]

{"sheet":"PN - Maritime","index":8,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,"UCC Presentation Notification (PN) - Maritime","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html","Not applicabale",null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/3","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51434"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"2021-10-12","Stable/Final","In progress","2023-08-01","2024-02-28","Stable/Final","In progress","2023-07-05","Stable/Final","Completed","2024-06-03","2024-12-31","Indicative","In progress","2024-12-31","Indicative","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2023-08-04","Stable/Final","Completed","2023-09-04","2023-10-16","Stable/Final","Completed","2023-11-10","Stable/Final","Completed",null,null,null,null,"2024-01-15","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-05-22","Stable/Final","Completed","2023-10-01","2025-03-10","Stable/Final","In progress","2025-03-31","Stable/Final","Not started","N/A","N/A",null,"Not started","2025-03-31","Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-12-05","Stable/Final","Completed",null,null,null,null,"2023-12-05","Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Please refer to \"Air transport\".",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2024-03-01","Stable/Final","Completed","2024-04-15","2024-05-24","Stable/Final","Completed","2024-05-25","Stable/Final","Completed","2024-05-25","2024-07-15","Stable/Final","Completed","2024-07-15","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2020-12-31","Stable/Final","Completed","2023-11-01","2025-09-01","Stable/Final","In progress","2021-03-15","Stable/Final","Completed","2023-10-01","2025-09-01","Stable/Final","In progress","2025-09-01","Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo","We would like to draw your attention on the fact that  this project is closely linked to project ICS2 and the project deadlines should be amended accordingly. It means that end date of the deployment window of PN should be 01/09/2025.",null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},null,"AN-PN-TS-NPM-EE@emta.ee"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-06-30","Stable/Final","Completed","2023-10-01","2025-12-31","Indicative","In progress","2024-03-01","Stable/Final","Completed","2024-03-01","2025-12-31","Indicative","In progress","2026-01-01","Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html","Final date for Migration and the date for Operations depend on the deployment date of EMSWe ","Aligned with the granted derogation date. Although the EO are encouraged to continue filing in the national single maritime window until the EMSWe replaces it.",{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2022-06-30","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","2024-06-30","2024-06-30","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2023-03-31","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2024-06-03","Stable/Final","Completed","2024-06-03","2025-04-01","Stable/Final","In progress","2025-04-01","Indicative","In progress",null,null,"Updated planning",{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2023-09-30","Stable/Final","Completed","2023-09-30","2023-12-31","Stable/Final","Completed","2024-06-30","Stable/Final","In progress","2024-03-31","2025-03-31","Stable/Final","In progress","2024-06-30","Stable/Final","In progress","https://www.aade.gr/customs",null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"ICS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2022-03-31","Stable/Final","Completed","2023-01-02","2023-04-16","Stable/Final","Completed","2023-04-17","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-04-17","Stable/Final","Completed",null,"The mentioned activities refer to the Presentation Notification within the framework of temporary storage",null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","PNTS@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-07-03","Stable/Final","Completed","2023-12-16","2024-03-29","Stable/Final","Completed","2024-04-02","Stable/Final","Completed",null,null,null,null,"2024-04-02","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2019-10-04","Stable/Final","Completed","2020-04-30","2021-10-04","Stable/Final","Completed","2020-11-23","Stable/Final","Completed","2020-11-23","2021-10-04","Stable/Final","Completed","2021-10-05","Stable/Final","Completed","www.revenue.ie",null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2024-03-27","Stable/Final","Completed","2024-05-03","2024-05-31","Stable/Final","Completed","2024-06-03","Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2022-07-01","Stable/Final","Completed","2022-10-15","2025-08-30","Stable/Final","In progress","2023-02-28","Stable/Final","Completed","2023-03-01","2025-04-01","Stable/Final","In progress","2025-04-01","Stable/Final","In progress","https://lrmuitine.lt/web/guest/1000","For Other modes of transport the deployment windows will be granted for EO the same as fr ICS2 R3 economic operators. For traders using the ICS2-R3 deployment window, the migration is expected from 03/06/2024.",null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_PN_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable",null,null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","2025-09-01","Stable/Final","In progress","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Currently depending on the business case PN is as a part of TS or NIS or Port system administrered by the Ministry of Transport for goods coming by maritime transport (according to the Article 190 of IA of the UCC) where notification for unloading (incl. PN data set) is submitted. When trade will join ICS3 R3 - PN will be also a part of ICS2 ",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"2024-06-01","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2023-09-01","Stable/Final","Completed","2024-01-01","29/02/2025","Stable/Final","In progress","2024-05-27","Stable/Final","Completed","2024-08-01","2025-04-01","Indicative","In progress","2025-04-01","Indicative","Not started",null,"NL is considering to combine the migration for traders for PN maritime with ICS2 R3, following a request from Trade",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2022-07-29","Stable/Final","Completed","2023-09-30","2025-04-30","Stable/Final","In progress","2025-04-20","Stable/Final","Not started","N/A ","N/A ",null,"Not applicable","2025-05-01","Stable/Final","Not started",null,null,"Poland was granted a derogation decision.PN functionalities are being developed within national import system and according to its schedule.",{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2022-07-31","Stable/Final","Completed","2023-03-01","2025-04-01","Indicative","In progress","2025-04-04","Indicative","Not started",null,null,null,null,"2025-04-07","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024","Projects 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nDevelopment and testing is ongoing.",{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2024-09-30","Stable/Final","Completed","2024-09-30","2024-12-31","Stable/Final","Completed","2024-11-14","Stable/Final","Completed","N/A","N/A",null,"Not applicable","2024-11-14","Stable/Final","Completed","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn",null,null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","vama@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2022-12-01","Stable/Final","Completed","2023-09-27","2024-03-01","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-03","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html","From 3 June 2024 presentation notifications of goods transported by sea should be submitted. The requirement to present goods to customs only applies to goods that are unloaded in Sweden. The presentation notification should refer to the entry summary declaration. To submit presentation notifications for goods, additional information will be required in the MSW from 3 June 2024. Any information that is not provided in structured form when calling at a port, will be collected in an Excel file which is uploaded to MSW Reportal. This information should be provided when unloading goods from third countries (with the exception of goods arriving from Norway).\n\nProvide the following additional information:\n\nENS reference\nTransport document reference at Master and/or House consignment level\nContainer\nReceptacle.","Concerning maritime traffic we have asked for derogation until the 15 August 2025. We are for the moment analysing the consequences for the customs formalities since the deployment of MNSW In Sweden will be delayed Q1 2027.  ",{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.ava.dtl@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2022-10-01","Stable/Final","Completed","2022-01-01","2024-02-28","Stable/Final","Completed","2024-02-29","Stable/Final","Completed","2024-01-01","2024-02-29","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148","","completed within the deadlines set by the derogation regulation",{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable",null,null,null,null,"N/A",null,"Not applicable",null,null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]

{"sheet":"PN - Other","index":9,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,"UCC Presentation Notification (PN) - Road and rail transport","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/3","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51434"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable",null,null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable",null,null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2024-06-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-01","Stable/Final","Completed",null,null,null,null,"2024-06-01","Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Please refer to \"Air transport\".",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2022-08-01","Stable/Final","Completed","2023-03-01","2023-05-22","Stable/Final","Completed","2023-07-29","Stable/Final","Completed","2023-07-29","2024-07-08","Stable/Final","Completed","2024-07-08","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2020-12-31","Stable/Final","Completed","2024-06-03","2025-09-01","Stable/Final","In progress","2021-03-15","Stable/Final","Completed","2024-06-03","2025-09-01","Stable/Final","In progress","2025-09-01","Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo",null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-06-30","Stable/Final","Completed","2023-10-01","2025-12-31","Indicative","In progress","2024-03-01","Stable/Final","Completed","2024-03-01","2025-12-31","Indicative","In progress","2026-01-01","Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2022-06-30","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","2024-06-30","2024-06-30","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"ICS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2022-03-31","Stable/Final","Completed","2023-01-02","2023-04-16","Stable/Final","Completed","2023-04-17","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-04-17","Stable/Final","Completed","https://openkkk.nav.gov.hu/Megosztott%20dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FANPNTS&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D","The mentioned activities refer to the Presentation Notification within the framework of temporary storage",null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","PNTS@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-07-03","Stable/Final","Completed","2023-12-16","2024-03-29","Stable/Final","Completed","2024-04-02","Stable/Final","Completed",null,null,null,null,"2024-04-02","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2019-10-04","Stable/Final","Completed","2020-04-30","2021-10-04","Stable/Final","Completed","2020-11-23","Stable/Final","Completed","2020-11-23","2021-10-04","Stable/Final","Completed","2021-10-05","Stable/Final","Completed","www.revenue.ie",null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"01/07/2022","Stable/Final","Completed","15/10/2022","30/08/2025","Stable/Final","In progress","28/02/2023","Stable/Final","Completed","01/11/2024","01/04/2025","Stable/Final","In progress","01/09/2025","Stable/Final","In progress","https://lrmuitine.lt/web/guest/1000",null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_PN_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"2022-01-10","Stable/Final","Completed","2025-03-03","2025-09-01","Indicative","Not started","2025-09-01","Indicative","Not started","N/A","N/A","Stable/Final","Not applicable","2025-09-01","Indicative","Not started","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas",null,null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"2024-06-01","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable",null,null,null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2022-07-29","Stable/Final","Completed","2023-09-30","2025-08-31","Stable/Final","In progress","2025-04-20","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-09-01","Stable/Final","Not started",null,null,"Poland was granted a derogation decision. PN functionalities are being developed within national import and ICS2 systems and according to its schedule.",{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2024-09-30","Stable/Final","Completed","2024-09-30","2024-12-31","Stable/Final","In progress","2025-06-30","Stable/Final","In progress","N/A","N/A",null,"Not applicable","2025-06-30","Stable/Final","In progress","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn","We are reporting a delay in depolyment of PN because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 12/31/2023. Also, this system is depending by ICS 2 ","the updated deadlines took into account the derogation decisions",{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","vama@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2022-12-01","Stable/Final","Completed","2023-09-27","2024-03-01","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html","For goods that arrive by road from Norway, it will be possible to digitally present goods at customs offices from 1 March 2024. It will also be possible to submit a digital I2 message. However, during a transition period the practical procedure will consist of the driver submitting a manual presentation in the form of the single administrative document (SAD) on paper, .",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.ava.dtl@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"N/A","","Not applicable","N/A","","","Not applicable","N/A","","Not applicable","N/A","","","Not applicable","N/A","","Not applicable",null,null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable",null,null,null,null,"N/A",null,"Not applicable",null,null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]

{"sheet":"TS - Air","index":10,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,"UCC Temporary Storage (TS) - Aircraft","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"2024-10-01","Stable/Final","Completed","2025-02-28","2025-09-01","Indicative","Not started","2025-09-01","Indicative","Not started","N/A","N/A","Stable/Final","Not applicable","2025-09-15","Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/4","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51435"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"2021-10-12","Stable/Final","In progress","2023-08-01","2025-09-30","Stable/Final","In progress","2023-11-29","Stable/Final","Completed","2023-11-29","2025-12-31","Indicative","In progress","2025-12-31","Indicative","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0","Will be aligned with the releases of ICS2, which means that the transportmodi that are part of ICS 2 Part 3 will only start on 1/3/2024.",null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2023-08-04","Stable/Final","Completed","2023-09-04","2023-10-16","Stable/Final","Completed","2023-11-10","Stable/Final","Completed",null,null,null,null,"2024-01-15","Stable/Final","Completed","https://ep.customs.bg/eportal/","In rеlation with the update of NIS, which was aligned with the requirements of the new Annex B.",null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-05-22","Stable/Final","Completed","2023-10-01","2025-03-10","Stable/Final","In progress","2025-03-31","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-03-31","Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,"Derogation was granted.",{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2023-09-01","Stable/Final","Completed","2023-11-01","2023-12-31","Stable/Final","Completed","2023-12-05","Stable/Final","Completed",null,null,null,null,"2023-12-05","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"2020-10-09","Stable/Final","Completed","2021-05-01","2022-10-14","Stable/Final","Completed","2021-03-06","Stable/Final","Completed","2021-05-01","2022-10-14","Stable/Final","Completed","2022-10-31","Stable/Final","Completed","www.zoll.de","This \"message\" is updated as part of \"National Entry System\" of the national IT-System ATLAS (Release 9.1). The scope covers all modes of transport.\nPlease note, that the datamodel is not in line with EU-CDM (FMS) and will be updated following the approach of CCI and the national import system being the basis for the new and modernized import application.",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2024-09-01","Stable/Final","In progress","N/A","N/A","Stable/Final","Not applicable","2025-06-30","Indicative","Not started","2024-12-01","2025-10-01","Indicative","In progress","2025-10-01","Indicative","Not started","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2020-12-31","Stable/Final","Completed","2021-01-04","2023-10-01","Stable/Final","Completed","2021-07-01","Stable/Final","Completed","2021-07-01","2023-12-31","Stable/Final","Completed","2021-07-01","Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo","Estonia has deployed Temporary Storage/Presentation Notification (TS/PN) systems.\n However, not all traders will be using TS/PN system from the 1st of January 2023. The system is open for the migration for the traders. We have previously repeatedly informed Commission that the deadlines for TS and ICS2 should be synchronized (mainly because of the datasets). In that case, traders dealing with air cargo would migrate at the latest accordingly to the national deployment date of ICS2 release 2 and other traders accordingly to the ICS2 release 3.","A derogation request was accordingly submitted by EE on 06.07.2022.",{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-06-30","Stable/Final","Completed","2023-10-01","2025-12-31","Indicative","In progress","2024-01-01","Stable/Final","Completed","2024-01-01","2025-12-31","Indicative","In progress","2026-01-01","Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,"Aligned with the granted derogation date.  Some functionallity not yet available, like G5 for G4 filings.",{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2020-12-31","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2022-12-31","Stable/Final","Completed","2022-12-31","2022-12-31","Stable/Final","Completed","2022-12-31","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2023-03-31","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-03-06","Stable/Final","Completed","2024-06-03","2024-12-04","Stable/Final","Completed","2024-12-04","Stable/Final","Completed","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report","Updated planning",{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2024-12-31","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-30","Indicative","Not started","2025-06-30","2025-06-30","Indicative","Not started","2025-06-30","Indicative","Not started",null,null,"derogation request",{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"ICS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2022-03-31","Stable/Final","Completed","2022-11-01","2023-04-16","Stable/Final","Completed","2023-04-17","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-04-17","Stable/Final","Completed","https://carina.gov.hr ","TS deployment and operation completed on 17.04.2023. The system is fully operational and in use by traders and customs from that date. ",null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","PNTS@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-03-31","Stable/Final","Completed","2023-12-16","2024-03-29","Stable/Final","Completed","2024-04-02","Stable/Final","Completed",null,null,null,null,"2024-04-02","Stable/Final","Completed","https://openkkk.nav.gov.hu/Megosztott%20dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FANPNTS&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D",null,"The developments are in progress.",{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2019-10-04","Stable/Final","Completed","2020-04-30","2021-10-04","Stable/Final","Completed","2020-11-23","Stable/Final","Completed","2020-11-23","2021-10-04","Stable/Final","Completed","2021-10-05","Stable/Final","Completed","www.revenue.ie","Will be updated to Revised Annex B in Q1 2026",null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2022-06-01","Stable/Final","Completed","2022-09-05","2022-12-12","Stable/Final","Completed","2022-12-13","Stable/Final","Completed",null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/an-pn-ts",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2023-05-04","Stable/Final","Completed","2023-06-04","2023-11-17","Stable/Final","Completed","2023-10-31","Stable/Final","Completed","2023-10-31","2023-10-31","Stable/Final","Completed","2023-11-19","Stable/Final","Completed","https://lrmuitine.lt/web/guest/591 ",null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_TS_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2021-12-14","stable/final","Completed","2022-10-01","2023-07-01","Stable/Final","Completed","2023-01-10","stable/final","Completed","N/A","N/A","Stable/Final","Completed","2023-01-10","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS.html",null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"2017-06-05","stable/final","Completed","2017-08-01","2017-09-22","stable/final","Completed","2017-09-24","stable/final","Completed","N/A","N/A","stable/final","Completed","2017-09-25","stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","As from 24.09.2017 National Temporary Storage System has been updated according to UCC data elements. Additional functionality for movements between TS places (if located in Latvia) has been added on 5.03.2018. The undated version of national TS system according to the latest changes of EUCDM is in production since 15.02.2022. ",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"2024-02-01","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started","www.customs.gov.mt",null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2022-09-01","Stable/Final","Completed","2023-11-06","2024-02-29","Stable/Final","Completed","2023-12-01","Stable/Final","Completed","2023-12-01","2024-02-29","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","https://www.nhdouane.nl/",null,null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2022-07-29","Stable/Final","Completed","2023-09-30","2025-04-30","Stable/Final","In progress","2025-04-20","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-05-01","Stable/Final","Not started",null,null,"Poland was granted a derogation decision.TS functionalities are being developed within national import system and according to its schedule.",{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2022-07-31","stable/final","Completed","2022-12-01","2025-04-01","Indicative","In progress","2025-04-04","Indicative","Not started",null,null,null,null,"2025-04-07","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024","Project 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nDevelopment and testing is ongoing.",{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2025-03-31","Indicative","In progress","2025-03-01","2025-06-30","Indicative","In progress","2025-06-30","Indicative","In progress","N/A","N/A",null,"Not applicable","2025-06-30","Stable/Final","In progress","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn","We are reporting a delay in depolyment of TSD because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 12/31/2023. Also, this system is depending by ICS 2 ","the updated deadlines took into account the derogation decisions",{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","vama@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2024-04-01","Stable/Final","Completed","2024-07-01","2024-12-31","Stable/Final","Completed","2024-10-08","Stable/Final","Completed","2024-10-08","2024-12-31","Stable/Final","Completed","2024-12-31","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html",null,null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.ava.dtl@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2023-04-28","Stable/Final","Completed","2023-09-01","2024-02-28","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","2023-11-30","2024-02-28","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148","","completed within the deadlines set by the derogation regulation",{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","N/A","indicative","Not applicable",null,null,null,null,"N/A","indicative","Not applicable",null,"TS business is done with other workarounds in multiple systems and evidences. No TP system in line with annex B of UCC DA is in place at this moment. NA-SK is planning to develope TS system sometime in 2026-2027","Deadline defined in COM Implementing Decision 2023/236 not reached. Second request for derogation sent on 22nd of November 2023.",{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]

{"sheet":"TS - Maritime","index":11,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,"UCC Temporary Storage (TS) - Maritime","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","N/A","Stable/Final","Not applicable",null,"Not applicabale because only air traffic in Austria",null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/4","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51435"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"2021-10-12","Stable/Final","Completed","2023-08-01","2025-09-30","Stable/Final","In progress","2023-11-29","Stable/Final","Completed","2024-03-01","2025-12-31","Indicative","In progress","2025-12-31","Indicative","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2023-08-04","Stable/Final","Completed","2023-09-04","2023-10-16","Stable/Final","Completed","2023-11-10","Stable/Final","Completed",null,null,null,null,"2024-01-15","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-05-22","Stable/Final","Completed","2023-10-01","2025-03-10","Stable/Final","In progress","2025-03-31","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-03-31","Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-12-05","Stable/Final","Completed",null,null,null,null,"2023-12-05","Stable/Final ","Completed",null,null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Please refer to \"Air transport\".",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2024-09-01","Stable/Final","In progress","N/A","N/A","Stable/Final","Not applicable","2025-06-30","Indicative","Not started","2024-12-01","2025-10-01","Indicative","In progress","2025-10-01","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2020-12-31","Stable/Final","Completed","2023-11-01","2025-09-01","Stable/Final","In progress","2023-10-01","Stable/Final","Completed","2023-10-01","2025-09-01","Stable/Final","In progress","2025-09-01","Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo",null,"A derogation request was accordingly submitted by EE on 06.07.2022.",{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-06-30","Stable/Final","Completed","2023-10-01","2025-12-31","Indicative","In progress","2024-03-01","Stable/Final","Completed","2024-03-01","2025-12-31","Indicative","In progress","2026-01-01","Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html","Final date for Migration and the date for Operations depend on the deployment date of EMSWe ","Aligned with the granted derogation date. Although the EO are encouraged to continue filing in the national single maritime window until the EMSWe replaces it.",{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2022-06-30","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","2024-06-30","2024-06-30","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2023-03-31","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2024-06-03","Stable/Final","Completed","2024-06-03","2025-04-01","Stable/Final","In progress","2025-04-01","Indicative","In progress",null,null,"Updated planning",{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2024-12-31","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-30","Indicative","Not started","2025-06-30","2025-06-30","Indicative","Not started","2025-06-30","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"ICS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2022-03-31","Stable/Final","Completed","2023-01-02","2023-04-16","Stable/Final","Completed","2023-04-17","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-04-17","Stable/Final","Completed","https://carina.gov.hr ",null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","PNTS@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-07-03","Stable/Final","Completed","2023-12-16","2024-03-29","Stable/Final","Completed","2024-04-02","Stable/Final","Completed",null,null,null,null,"2024-04-02","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2019-10-04","Stable/Final","Completed","2020-04-30","2021-10-04","Stable/Final","Completed","2020-11-23","Stable/Final","Completed","2020-11-23","2021-10-04","Stable/Final","Completed","2021-10-05","Stable/Final","Completed","www.revenue.ie",null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2024-03-27","Stable/Final","Completed","2024-05-03","2024-05-31","Stable/Final","Completed","2024-06-03","Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2023-05-04","Stable/Final","Completed","2023-06-04","2023-11-17","Stable/Final","Completed","2023-10-31","Stable/Final","Completed","2023-10-31","2023-10-31","Stable/Final","Completed","2023-11-19","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_TS_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2021-12-14","stable/final","Completed","2022-10-01","2023-07-01","Stable/Final","Completed","2023-01-10","stable/final","Completed","N/A","N/A","Stable/Final","Completed","2023-01-10","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"2017-06-05","Stable/Final","Completed","2017-08-01","2017-09-22","Stable/Final","Completed","2017-09-24","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2017-09-25","Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","As from 24.09.2017 National Temporary Storage System has been updated according to UCC data elements. Additional functionality for movements between TS places (if located in Latvia) has been added on 5.03.2018. The undated version of national TS system according to the latest changes of EUCDM is in production since 15.02.2022. ",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"2024-06-01","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2023-09-01","Stable/Final","Completed","2024-01-01","29/02/2025","Stable/Final","In progress","2024-05-27","Stable/Final","Completed","2024-08-01","2025-04-01","Indicative","In progress","2025-04-01","Indicative","Not started",null,"NL is considering to combine the migration for traders for TS maritime with ICS2 R3, following a request from Trade",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2022-07-29","Stable/Final","Completed","2023-09-30","2025-04-30","Stable/Final","In progress","2025-04-20","Stable/Final","Not started","N/A ","N/A ",null,"Not applicable","2025-05-01","Stable/Final","Not started",null,null,"Poland was granted a derogation decision.TS functionalities are being developed within national import system and according to its schedule.",{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2022-07-31","Stable/Final","Completed","2022-12-01","2025-04-01","Indicative","In progress","2025-04-04","Indicative","Not started",null,null,null,null,"2025-04-07","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024","Project 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nEOs started testing;\nOngoing the activities and tests with ports Authorities;\nDevelopment and testing is ongoing.",{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2025-03-31","Indicative","In progress","2025-03-01","2025-06-30","Indicative","In progress","2025-06-30","Indicative","In progress","N/A","N/A",null,"Not applicable","2025-06-30","Stable/Final","In progress","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn","We are reporting a delay in depolyment of TSD because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 12/31/2023. Also, this system is depending by ICS 2 ","the updated deadlines took into account the derogation decisions",{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","vama@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","2025-08-15","Indicative","Not started","2025-08-15","2025-08-15","Indicative","Not started","2025-08-15","Indicative","Not started","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html",null,"Concerning the maritime traffic we have asked for a derogation until 15 August 2025 because of the dependencies to EMSW. Since we aim to use MNSW as the external domain there is no need for technical specification nor conformance testing with Trade from our side. We are for the moment analysing the consequences for the customs formalities since the deployment of MNSW In Sweden will be delayed until Q 1 2027.  ",{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.ava.dtl@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2023-04-28","Stable/Final","Completed","2023-09-01","2024-02-28","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","2023-11-30","2024-02-28","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148","","completed within the deadlines set by the derogation regulation",{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","N/A","Indicative","Not applicable",null,null,null,null,"N/A","Indicative","Not applicable",null,null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]

{"sheet":"TS - Other","index":12,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,"UCC Temporary Storage (TS) - Road and rail transport","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"2024-10-01","Stable/Final","Completed","2025-02-28","2025-09-01","Indicative","Not started","2025-09-01","Indicative","Not started","N/A","N/A","Stable/Final","Not applicable","2025-09-15","Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/4","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51435"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable",null,null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable",null,null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2023-09-01","Stable/Final","Completed","2023-11-01","2023-12-31","Stable/Final","Completed","2023-12-05","Stable/Final","Completed",null,null,null,null,"2023-12-05","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Please refer to \"Air transport\".",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2024-09-01","Stable/Final","In progress","N/A","N/A","Stable/Final","Not applicable","2025-06-30","Indicative","Not started","2024-12-01","2025-10-01","Indicative","In progress","2025-10-01","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2020-12-31","Stable/Final","Completed","2024-06-03","2025-09-01","Stable/Final","In progress","2024-06-03","Stable/Final","Completed","2024-06-03","2025-09-01","Stable/Final","In progress","2025-09-01","Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo",null,"A derogation request was accordingly submitted by EE on 06.07.2022.",{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-06-30","Stable/Final","Completed","2023-10-01","2025-12-31","Indicative","In progress","2024-03-01","Stable/Final","Completed","2024-03-01","2025-12-31","Indicative","In progress","2026-01-01","Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2022-06-30","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","2024-06-30","2024-06-30","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"ICS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2022-03-31","Stable/Final","Completed","2023-01-02","2023-04-16","Stable/Final","Completed","2023-04-17","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-04-17","Stable/Final","Completed","https://carina.gov.hr ",null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","PNTS@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-07-03","Stable/Final","Completed","2023-12-16","2024-03-29","Stable/Final","Completed","2024-04-02","Stable/Final","Completed",null,null,null,null,"2024-04-02","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2019-10-04","Stable/Final","Completed","2020-04-30","2021-10-04","Stable/Final","Completed","2020-11-23","Stable/Final","Completed","2020-11-23","2021-10-04","Stable/Final","Completed","2021-10-05","Stable/Final","Completed","www.revenue.ie",null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_TS_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"2017-06-05","Stable/Final","Completed","2017-08-01","2017-09-22","Stable/Final","Completed","2017-09-24","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2017-09-25","Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","As from 24.09.2017 National Temporary Storage System has been updated according to UCC data elements. Additional functionality for movements between TS places (if located in Latvia) has been added on 5.03.2018. The undated version of national TS system according to the latest changes of EUCDM is in production since 15.02.2022. ",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"2024-06-01","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable",null,null,null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2022-07-29","Stable/Final","Completed","2023-09-30","2025-04-30","Stable/Final","In progress","2025-04-20","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-05-01","Stable/Final","Not started",null,null,"Poland was granted a derogation decision.TS functionalities are being developed within national import system and according to its schedule.",{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2025-03-31","Indicative","In progress","2025-03-01","2025-06-30","Indicative","In progress","2025-06-30","Indicative","In progress","N/A","N/A",null,"Not applicable","2025-06-30","Stable/Final","In progress","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn","We are reporting a delay in depolyment of TSD because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 12/31/2023. Also, this system is depending by ICS 2 ","the updated deadlines took into account the derogation decisions",{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","vama@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},null,null,null,null,null,null,null,"N/A",null,"Not applicable","N/A",null,null,"Not applicable","N/A",null,"Not applicable","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html","Customs declarations of goods delivered by road will be considered as temporary storage declarations. Transit declarations in NCTS will be considered as temporary storage declarations, which means that a separate temporary storage declaration will not be required for goods in transit nor in the road traffic.",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.ava.dtl@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2023-04-28","Stable/Final","Completed","2023-09-01","2024-02-28","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","2023-11-30","2024-02-28","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148",null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","N/A","Indicative","Not applicable",null,null,null,null,"N/A","Indicative","Not applicable",null,null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]

{"sheet":"NIS","index":13,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A6","v":"UCC National Import Systems upgrade"},"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"2024-10-01","Stable/Final","Completed","2025-02-28","2025-09-01","Indicative","Not started","2025-09-01","Indicative","Not started","N/A","N/A","Stable/Final","Not applicable","2025-09-15","Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/5","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51436"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"2021-11-01","Stable/Final","Completed","2023-07-01","2024-06-05","Stable/Final","In progress","2024-08-28","Indicative","In progress","2024-08-28","2024-12-13","Indicative","Not started","2024-12-13","Indicative","Not started","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2023-08-04","Stable/Final","Completed","2023-09-04","2023-10-16","Stable/Final","Completed","2023-11-10","Stable/Final","Completed",null,null,null,null,"2024-01-15","Stable/Final","Completed","https://ep.customs.bg/eportal/","In relation to the update of the new Annex B the new import national system became operational on 15.01.2024.",null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-05-22","Stable/Final","Completed","2023-10-01","2025-03-10","Stable/Final","In progress","2025-03-31","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-03-31","Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,"Derogation was granted.",{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2024-06-30","Stable/Final","Completed","2025-07-01","2025-12-14","Indicative","Not started","2025-12-15","Indicative","Not started",null,null,null,null,"2025-12-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"2020-10-09","Stable/Final","Completed","2021-05-01","2022-10-14","Stable/Final","Completed","2021-03-06","Stable/Final","Completed","2021-05-01","2022-10-14","Stable/Final","Completed","2022-10-31","Stable/Final","Completed","www.zoll.de","This project is implemented in the major release of the national IT-ATLAS (Release 9.1) to ensure that all data requirements from Annex B are covered, especially to provide the information required by Surveillance 3. Please note, that the datamodel is not in line with EU-CDM (FMS) as implemented in CCI. Therefore the national import system will be replaced by CCI being the basis for the new and modernized import application.",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2024-09-01","Stable/Final","In progress","N/A","N/A","Stable/Final","Not applicable","2025-06-30","Indicative","Not started","2024-12-01","2025-10-01","Indicative","In progress","2025-10-01","Indicative","Not started","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2020-09-30","Stable/Final","Completed","2020-12-01","2021-06-30","Stable/Final","Completed","2021-07-01","Stable/Final","Completed","2021-06-30","2021-07-01","Stable/Final","Completed","2021-07-01","Stable/Final","Completed","https://www.emta.ee/ariklient/toll-\nkaubavahetus/tolliinfosusteemid/tolliinfosusteemide-\nkasutajatele",null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","Impulss-EE@emta.ee","    00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-03-14","Stable/Final","Completed","2023-05-16","2025-10-13","Stable/Final","In progress","2023-09-05","Stable/Final","Completed","2023-09-05","2025-10-13","Indicative","In progress","2025-10-14","Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","H1.info@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2019-06-30","Stable/Final","Completed","N/A","N/A",null,"Not applicable","2019-12-31","Stable/Final","Completed","2019-12-31","2022-12-31","Stable/Final","Completed","2022-12-31","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Import2_1/en/index.html ",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2022-03-31","Stable/Final","Completed","N/A","N/A","Stable/Final","Not applicable","2024-11-30","Stable/Final","Completed","2024-11-30","2025-05-31","Stable/Final","In progress","2025-05-31","Stable/Final","In progress","https://www.douane.gouv.fr/services-aide/edi","The technical specifications are published since February, 2022 and are regularly  with new information.\nThe project Surveillance 3 follow the same calendar deployment with a deployement at 07/11/2024. The conformance for Surveillance is planned during Q3 and Q4 2024",null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2024-12-31","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-30","Indicative","Not started","2025-06-30","2025-06-30","Indicative","Not started","2025-06-30","Indicative","Not started","https://www.aade.gr/customs","OUR CURRENT NATIONAL IMPORT SYSTEM WILL BE UPGRADED IN ORIDER TO SEND SURVEILLANCE DATA IN UCC FORMAT. IT WILL BE PUT IN PRODUCTION ON Q2 2024","derogation request",{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"IMPORT_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2021-12-31","Stable/Final","Completed","2022-09-01","2022-12-31","Stable/Final","Completed","2023-01-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-01-01","Stable/Final","Completed","https://carina.gov.hr ",null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","hrais3@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2022-07-31","Stable/Final","Completed","2023-07-01","2023-09-17","Stable/Final","Completed","2023-10-12","Stable/Final","Completed","N/A ","N/A ","Stable/Final","Completed","2023-11-01","Stable/Final","Completed","https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D","In order to have a smooth transition we envisage to have a period (one week), during which both import systems (i.e. our current import system based on the UCC-TDA and the new import system based on Annex B UCC-DA/IA) would run in production in parallel (the new National Import System would be used in this period only by a few designated/volunteering economic operators).","The developments are in progress.",{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA IT Institute","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2023-06-23","Stable/Final","Completed","2025-06-03","2026-01-19","Stable/Final","Not started","2026-01-20","Stable/Final","Not started","2026-01-20","2026-04-20","Stable/Final","Not started","2026-04-21","Stable/Final","Not started","www.revenue.ie","Upgrade of our UCC compliant system to align with Revised Annex B in Q1 2026",null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2019-12-02","Stable/Final","Completed","2020-06-30","2021-06-30","Stable/Final","Completed","2021-07-01","Stable/Final","Completed","2021-07-01","2022-06-08","Stable/Final","Completed","2022-11-30","Stable/Final","Completed","https://www.adm.gov.it/portale/dichiarazioni-import",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2023-08-15","Stable/Final","Completed","2023-08-15","2024-02-09","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","2023-12-31","2023-12-31","Stable/Final","Completed","2024-03-11","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_IMP_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2022-01-03","Stable/Final","Completed","2022-10-01","2023-04-29","Stable/Final","Completed","2023-05-02","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-05-02","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/National_Import_System.html",null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"N/A","stable/final","Completed","2018-05-01","2018-06-01","stable/final","Completed","2018-06-03","stable/final","Completed","N/A","N/A","stable/final","Completed","2018-06-04","stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","As from 3.06.2018 National import system has been aligned with UCC DI/IA Annex B and EUCDM V2.0. New AIS aligned with the latest version of UCC and EUCDM has been implemented on 13.06.2023 and H6 has been transferred to the new AIS by the 8.08.2023. ",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started","www.customs.gov.mt",null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2021-06-22","Stable/Final","Completed","2022-02-01","2022-12-31","Stable/Final","Completed","2022-04-01","Stable/Final","Completed","2023-03-01","2023-12-31","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","https://www.nhdouane.nl/","The transition period has formally ended, but not all traders are fully migrated yet. ",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2022-07-29","Stable/Final","Completed","2023-09-30","2025-04-30","Stable/Final","In progress","2025-04-20","Stable/Final","Not started","N/A ","N/A ",null,"Not applicable","2025-05-01","Stable/Final","Not started",null,null,null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2022-07-01","Stable/Final","Completed","2022-12-01","2025-04-01","Indicative","In progress","2025-04-04","Indicative","Not started",null,null,null,null,"2025-04-07","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/STADA_Importacao_CAU/Pages/default.aspx","Derrogation request to second semester 2024"," Projects 4, 6, 8 and 9 are developed in same system;\nTest environment available to EOs;\nOngoing the activities and tests with EOs who have started testing;\nDevelopment and testing is ongoing for Webforms and Webservices.",{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2025-03-31","Indicative","In progress","2024-12-18","2025-06-30","Indicative","In progress","2025-06-30","Indicative","In progress","N/A ","N/A ",null,"Not applicable","2025-06-30","Indicative","Not started","www.customs.ro","We are reporting a delay in deployment of NIS because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 31/12/2023 ","the updated deadlines took into account the derogation decisions",{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","vama@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2021-09-15","Stable/Final","Completed","2021-12-01","2023-12-31","Stable/Final","Completed","2022-03-15","Stable/Final","Completed","2022-03-15","2023-12-31","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/importinggoods/customsdeclarationsforimports.4.21f3dd0d183a9e9ca643689.html","Concerning the declaration for Customs warehousing procedure we will perform an update from the \"current\" Annex B to the \"new\" Annex B.",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.import@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2019-07-01","Stable/Final","Completed","2021-04-01","2021-10-01","Stable/Final","Completed","2022-01-01","Stable/Final","Completed","2022-01-01","2022-01-01","Stable/Final","Completed","2022-01-01","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148",null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"2025-01-31","Indicative","Not started","2025-05-01","2025-09-30","Indicative","Not started","2025-09-30","Indicative","Not started","2025-09-30","2025-09-30","Indicative","Not started","2025-10-01","Indicative","Not started",null,null,"Request for derogation sent on 2nd of October 2023 ",{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]

{"sheet":"SP EXP","index":14,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A7","v":"UCC Special Procedures (Component 1) \"National SP EXP\""},"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"2020-12-31","Stable/Final","Completed","2024-06-10","2024-12-16","Stable/Final","Completed","2025-01-26","Stable/Final","Completed","2025-01-26","2025-05-31","Stable/Final","Not started","2025-06-01","Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/aes.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/6","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51437"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"2021-09-01","Stable/Final","Completed","2023-06-01","2023-09-01","Stable/Final","Completed","2024-06-19","Stable/Final","Completed",null,null,null,null,null,null,null,"https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2022-08-31","Stable/Final","Completed","2023-07-24","2023-08-11","Stable/Final","Completed","2023-08-28","Stable/Final","Completed",null,null,null,null,"2023-08-29","Stable/Final","Completed","https://ep.customs.bg/eportal/",null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-08-01","Stable/Final","Completed","2023-09-18","2023-11-30","Stable/Final","Completed","2023-12-18","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-12-18","Stable/Final","Completed","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2021-10-21","Stable/Final","Completed","2023-01-02","2023-09-30","Stable/Final","Completed","2023-10-01","Stable/Final","Completed",null,null,null,null,"2023-10-01","Stable/Final","Completed","https://www.celnisprava.cz/cz/clo/e-customs/ecs/Stranky/dokumentace-pro-vyrobce-SW-UCC-AES.aspx","In CZ \"big bang\". All economic operators started at the same date. ",null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"2020-10-09","Stable/Final","Completed","2021-04-19","2023-10-29","Stable/Final","Completed","2021-03-06","Stable/Final","Completed","2021-04-19","2023-11-30","Stable/Final","Completed","2023-12-01","Stable/Final","Completed","www.zoll.de","This component is implemented in line with the project \"UCC AES (Component 1) Transeuropean AES\"",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2022-08-01","Stable/Final","Completed","2023-03-01","2023-07-14","Stable/Final","Completed","2023-07-29","Stable/Final","Completed","2023-07-29","2024-05-31","Stable/Final","Completed","2024-05-31","Stable/Final","Completed","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2022-03-31","Stable/Final","Completed","2023-03-01","2023-09-01","Stable/Final","Completed","2023-09-30","Stable/Final","Completed","2023-09-30","2023-09-30","Stable/Final","Completed","2023-10-01","Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","AES-NPM-EE@emta.ee","    00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2021-04-15","Stable/Final","Completed","2021-11-10","2023-05-08","Stable/Final","Completed","2022-10-18","Stable/Final","Completed","2022-10-18","2023-05-08","Stable/Final","Completed","2023-05-09","Stable/Final","Completed","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2023-06-30","Stable/Final","Completed","2023-06-30","2024-12-31","Stable/Final","Completed","2024-11-05","Stable/Final","In progress","2024-10-05","2024-11-05","Stable/Final","Completed","2024-11-05","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Export/en/index.html ","The derogation paper has been sent for end date Q2/2024. Unfortunately we have to postpone the date until Q4/2024.  We have devided implementation into two phases. Phase 1  contains normal export, sp, simplifications, centralized clearance and EMCS integration.  Phase 2 contains exit functionalities and integration to EMSWe.  Phase 2 will be deployed Q2/2025. Phase 1 will be found in line for step 1 and phase 2 in line for step 3. Thus the line for step 2 will be empty.",null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2025-04-30","Indicative","In progress","2025-03-31","2025-09-30","Indicative","Not started","2025-10-30","Indicative","Not started","2025-10-30","2025-12-31","Indicative","Not started","2025-12-31","Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report",null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2024-09-30","Stable/Final","In progress","N/A","N/A",null,"Not applicable","2024-12-31","Stable/Final","In progress","N/A","N/A",null,"Not applicable","2024-12-16","Stable/Final","Not started","https://www.aade.gr/customs",null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"AES_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2021-12-31","Stable/Final","Completed","2022-10-01","2022-12-31","Stable/Final","Completed","2023-01-01","Stable/Final","Completed",null,null,null,null,"2023-01-01","Stable/Final","Completed","https://carina.gov.hr ","Depending on the development of the national import customs clearance system and the budget",null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","AES@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-04-03","Stable/Final","Completed","2024-05-02","2025-02-11","Indicative","In progress","2025-02-12","Indicative","Not started",null,null,null,null,"2025-02-12","Indicative","Not started","https://openkkk.nav.gov.hu/Megosztott%20dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FE%2DV%C3%81M%20specifik%C3%A1ci%C3%B3k%2FAES&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D","The developments will be implemented within the framework of AES",null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2022-01-28","Stable/Final","Completed","2022-07-31","2023-03-30","Stable/Final","Completed","2023-03-21","Stable/Final","Completed","2023-03-21","2023-05-21","Stable/Final","Completed","2023-05-21","Stable/Final","Completed","www.revenue.ie",null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2021-02-15","Stable/Final","Completed","2022-02-01","2023-05-07","Stable/Final","Completed","2023-06-08","Stable/Final","Completed","2023-06-08","2024-12-01","Stable/Final","Completed","2024-12-02","Stable/Final","Completed","https://www.adm.gov.it/portale/dichiarazioni-export",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2023-05-04","Stable/Final","Completed","2023-06-04","2023-12-01","Stable/Final","Completed","2023-12-03","Stable/Final","Completed","2023-12-03","2023-12-03","Stable/Final","Completed","2023-12-03","Stable/Final","Completed","https://lrmuitine.lt/web/guest/591 ",null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_SP_C1_EXP_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2023-07-01","Stable/Final","Completed","2024-02-01","2024-09-30","Stable/Final","Completed","2024-07-08","Stable/Final","Completed","2024-07-08","2024-12-01","Stable/Final","Completed","2024-12-02","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS.html",null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"N/A","stable/final","Completed","2023-07-10","2023-09-30","stable/final","Completed","2023-10-10","Stable/Final","Completed","N/A","N/A","stable/final","Completed","2023-10-10","Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Along with AES",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","2025-06-02","Indicative","Not started",null,null,null,null,"2025-06-02","Indicative","Not started","www.customs.gov.mt","Due to the small amount of movements that Maltese Economic Operators (EOs) have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a Graphic User Interface (GUI) where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.",null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2021-06-22","Stable/Final","Completed","2022-02-01","2022-12-31","Stable/Final","Completed","2022-04-01","Stable/Final","Completed","2023-05-08","2023-11-30","Stable/Final","Completed","2023-11-30","Stable/Final","Completed","https://www.nhdouane.nl/","The transition period has formally ended, but not all traders are fully migrated yet.",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2020-10-23","Stable/Final","Completed","2020-11-23","2021-05-04","Stable/Final","Completed","2021-07-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2022-03-28","Stable/Final","Completed","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje","The National (PL) UCC Special Procedures Project as a whole consists of some parts: \n(1) activities carried out within the National Project of UCC Automated Export System (AES) and \n(2) activities carried out within the National Project of UCC Automated Import System (AIS) and also \n(3) activities carried out within the National Project of (a new) System “RPS” concerning management & settlement of the Special Procedures.  \n\nCOMPONENT 1_(Part AES and RPS)\nHere we indicate that part of relevant functionalities regarding export issues connected with UCC Special Procedures is being implemented during the works concerning the Project of System AES – ad(1) and also the Project of System “RPS” – ad(3).\n\nExplanation:\nThe given dates of stages concern the contracts which were completed in 2022 and the selected key functionalities of UCC SP were entered into IT Components 1+2. \nSupplementation of current Components 1+2 with additional required UCC SP functions are being developed in AIS, AES and RPS systems and will be aligned with the new data matrix referred to in Annex B of the UCC-DA/UCC-IA. \nAfter necessary tests these functionalities will become operational in planned dates: 7.2024 for IMP; 12.2024 for EXP.",null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.projekt.aes.350000@mf.gov.pl \nsp_pl_project@mf.gov.pl ","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2023-02-22","Stable/Final","Completed","2023-04-01","2025-05-01","Indicative","In progress","2025-05-03","Indicative","Not started",null,null,null,null,"2025-05-06","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Sistema_exportacao_e_saida/Sistema_Automatico_Exportacao/Paginas/default.aspx","Integrated in AES component 1\nDerrogation request to second semester 2024",null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2024-03-16","Stable/Final","Completed","2023-05-15","2023-11-30","Stable/Final","Completed","2024-03-16","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-03-16","Stable/Final","Completed","https://www.customs.ro/e-customs/aes",null,null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","vama@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2022-12-15","Stable/Final","Completed","2024-01-24","2024-12-02","Stable/Final","Completed","2024-10-01","Stable/Final","Completed","2024-10-01","2024-12-02","Stable/Final","Completed","2024-12-02","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/exportinggoods.4.422c8052175b1d82769598d.html",null,null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.export@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2020-12-18","Stable/Final","Completed","2022-05-03","2023-05-23","Stable/Final","Completed","2023-05-24","Stable/Final","Completed","2023-05-24","2023-05-24","Stable/Final","Completed","2023-05-24","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148",null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"2023-02-03","stable/final","Completed","2023-10-25","2024-10-31","Stable/Final","Completed","2024-11-01","Stable/Final","Completed","2024-11-01","2024-11-01","Stable/Final","Completed","2024-11-01","Stable/Final","Completed",null,"SP (Component 1) is developed as a part of AES. ","Request for derogation sent on 2nd of October 2023 ",{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]

{"sheet":"SP IMP","index":15,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A8","v":"UCC Special Procedures (Component 2) \"National SP IMP\""},"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"2024-10-01","Stable/Final","Completed","2025-02-28","2025-09-01","Indicative","Not started","2025-09-01","Indicative","Not started","N/A","N/A","Stable/Final","Not applicable","2025-04-01","Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/7","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51438"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"2021-11-01","Stable/Final","Completed","2023-07-01","2023-10-01","Stable/Final","Completed","2024-08-28","Indicative","In progress",null,null,null,null,null,null,null,"https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2023-08-04","Stable/Final","Completed","2023-09-04","2023-10-16","Stable/Final","Completed","2023-11-10","Stable/Final","Completed",null,null,null,null,"2024-01-15","Stable/Final","Completed","https://ep.customs.bg/eportal/",null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-05-22","Stable/Final","Completed","2023-10-01","2025-03-10","Stable/Final","In progress","2025-03-31","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-03-31","Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2024-06-30","Stable/Final","Completed","2025-07-01","2025-12-14","Indicative","Not started","2025-12-15","Indicative","Not started",null,null,null,null,"2025-12-15","Indicative","Not started",null,null,"GAN, data mapping",{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"2020-10-09","Stable/Final","Completed","2021-05-01","2022-10-14","Stable/Final","Completed","2021-03-06","Stable/Final","Completed","2021-05-01","2022-10-14","Stable/Final","Completed","2022-10-31","Stable/Final","Completed","www.zoll.de","This component is implemented in the major release of the national IT-System ATLAS (Release 9.1) being part of the \"National Import Systems upgrade\".",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2024-09-01","Stable/Final","In progress","N/A","N/A","Stable/Final","Not applicable","2025-06-30","Indicative","Not started","2024-12-01","2025-10-01","Indicative","In progress","2025-10-01","Indicative","Not started","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2020-09-30","Stable/Final","Completed","2020-12-01","2021-06-30","Stable/Final","Completed","2021-07-01","Stable/Final","Completed","2021-06-30","2021-07-01","Stable/Final","Completed","2021-07-01","Stable/Final","Completed","https://www.emta.ee/ariklient/toll-\nkaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","Impulss-EE@emta.ee","    00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-03-14","Stable/Final","Completed","2023-05-16","2025-10-13","Stable/Final","In progress","2023-09-05","Stable/Final","Completed","2023-09-05","2025-10-13","Indicative","In progress","2025-10-14","Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","H1.info@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2019-06-30","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2022-12-31","Stable/Final","Completed","2022-12-31","2022-12-31","Stable/Final","Completed","2022-12-31","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Import2_1/en/index.html ",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2022-03-31","Stable/Final","Completed","N/A","N/A","Stable/Final","Not applicable","2024-11-30","Stable/Final","Completed","2024-11-30","2025-05-31","Stable/Final","In progress","2025-05-31","Stable/Final","In progress","https://www.douane.gouv.fr/services-aide/edi","The technical specifications are published since February, 2022 and are regularly  with new information.\nProgress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report",null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2025-06-30","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-30","Indicative","Not started","2025-06-30","2025-06-30","Indicative","Not started","2025-06-30","Indicative","Not started","https://www.aade.gr/customs",null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"IMPORT_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2021-12-31","Stable/Final","Completed","2022-09-01","2022-12-31","Stable/Final","Completed","2023-01-01","Stable/Final","Completed",null,null,null,null,"2023-01-01","Stable/Final","Completed","https://carina.gov.hr ",null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","hrais3@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2022-07-31","Stable/Final","Completed","2023-07-01","2023-09-17","Stable/Final","Completed","2023-10-12","Stable/Final","Completed",null,null,null,null,"2023-11-01","Stable/Final","Completed","https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D","The developments will be implemented within the framework of NIS","The developments are in progress.",{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA IT Institute","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2019-10-04","Stable/Final","Completed","2020-04-30","2021-10-04","Stable/Final","Completed","2020-11-23","Stable/Final","Completed","2020-11-23","2021-10-04","Stable/Final","Completed","2021-10-05","Stable/Final","Completed","www.revenue.ie","Will be updated to Revised Annex B in Q1 2026",null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2019-12-02","Stable/Final","Completed","2020-06-30","2021-06-30","Stable/Final","Completed","2021-07-01","Stable/Final","Completed","2021-07-01","2022-06-08","Stable/Final","Completed","2022-11-30","Stable/Final","Completed","https://www.adm.gov.it/portale/dichiarazioni-import",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2023-08-15","Stable/Final","Completed","2023-08-15","2024-02-09","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","2023-12-31","2023-12-31","Stable/Final","Completed","2024-03-11","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_SP_C2_IMP_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2022-01-03","Stable/Final","Completed","2022-10-01","2023-04-29","Stable/Final","Completed","2023-05-02","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-05-02","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS.html","The go-live of our national import system will  include Special procedures for Import.\n\nNo migration of data - big bang including big bang for traders.",null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"2017-10-30","stable/final","Completed","2018-05-01","2018-06-01","stable/final","Completed","2018-06-03","stable/final","Completed","N/A","N/A","stable/final","Completed","2018-06-04","stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","As from 3.06.2018 National import system has been aligned with UCC DI/IA Annex B and EUCDM V2.0. New national AIS aligned with the latest version of UCC and EUCDM has been implemented on 13.06.2023. ",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","2025-03-17","Indicative","Not started",null,null,null,null,"2025-03-17","Indicative","Not started","www.customs.gov.mt",null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2021-06-22","Stable/Final","Completed","2022-02-01","2022-12-31","Stable/Final","Completed","2022-04-01","Stable/Final","Completed","2022-10-01","2023-12-31","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","https://www.nhdouane.nl/","The transition period has formally ended, but not all traders are fully migrated yet.",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2020-11-16","Stable/Final","Completed","2020-11-23","2021-05-04","Stable/Final","Completed","2021-07-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2022-03-28","Stable/Final","Completed","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje","\"The National (PL) UCC Special Procedures Project as a whole consists of some parts: \n(1) activities carried out within the National Project of UCC Automated Export System (AES) and \n(2) activities carried out within the National Project of UCC Automated Import System (AIS) and also \n(3) activities carried out within the National Project of (a new) System “RPS” concerning management & settlement of the Special Procedures.  \n\nCOMPONENT 2_(Part AIS and RPS)\nHere we indicate that part of relevant functionalities regarding import issues connected with UCC Special Procedures is being implemented during the works concerning  the Project of System (AIS) – ad(2) and also the Project of System “RPS” – ad(3).\n\nExplanation:\n\nThe given dates of stages concern the contracts which were completed in 2022 and the selected key functionalities of UCC SP were entered into IT Components 1+2. \nSupplementation of current Components 1+2 with additional required UCC SP functions are being developed in AIS, AES and RPS systems and will be aligned with the new data matrix referred to in Annex B of the UCC-DA/UCC-IA. \nAfter necessary tests these functionalities will become operational in planned dates: 7.2024 for IMP; 12.2024 for EXP.\"",null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.projekt.ais.350000@mf.gov.pl \nsp_pl_project@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2022-07-01","Stable/Final","Completed","2022-12-01","2025-04-01","Indicative","In progress","2025-04-04","Indicative","Not started",null,null,null,null,"2025-04-07","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/STADA_Importacao_CAU/Pages/default.aspx","Integrated in NIS\nDerrogation request to second semester 2024","Projects 4, 6, 8 and 9 are developed in same system;\nTest environment available to EOs;\nOngoing the activities and tests with EOs who have started testing;\nDevelopment is ongoing for Webforms and Webservices.",{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2025-03-31","Indicative","In progress","2024-12-18","2025-06-30","Indicative","In progress","2025-06-30","Indicative","In progress","N/A ","N/A ",null,"Not applicable","2025-06-30","Indicative","Not started","www.customs.ro","We are reporting a delay in deployment of SP IMP because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 31/12/2023 ","the updated deadlines took into account the derogation decisions",{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","vama@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2022-06-01","Stable/Final","Completed","2022-11-01","2023-12-31","Stable/Final","Completed","2023-02-23","Stable/Final","Completed","2023-02-23","2023-12-31","Stable/Final","Completed","2023-12-31","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/importinggoods.4.422c8052175b1d82769590f.html",null,null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.import@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2019-07-01","Stable/Final","Completed","2021-04-01","2021-10-01","Stable/Final","Completed","2022-01-01","Stable/Final","Completed","2022-01-01","2022-01-01","Stable/Final","Completed","2022-01-01","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148",null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"2016-01-27","stable/final","Completed","2016-03-15","2016-06-10","stable/final","Completed","2016-06-11","stable/final","Completed","2016-06-10","2016-06-10","stable/final","Completed","2016-06-11","stable/final","Completed",null,"SP (Component 2) was developed as a part of National Import System.Our NIS and thus SP IMP are based on Annex D DA. Our understanding was that full alignment with Annex B DA is considered as fullfilment of the project requirements. However according to our communication with EC, the implementation of Annex D in our NIS is considered as fulfilment for NIS and therefore we can confirm, that SP IMP as a part of NIS, even if not be in line with Annex B DA, is already deployed.",null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]

{"sheet":"GUM-C2","index":16,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A9","v":"UCC Guarantee Management (Component 2) \"National GUM\""},"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"N/A","Stable/Final","Not applicable","2024-02-08","2024-03-07","Stable/Final","Completed","2025-09-01","Indicative","Not started","N/A","N/A","Stable/Final","Not applicable","2025-09-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/8","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51439"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","N/A","Indicative","Not applicable",null,null,null,null,null,null,null,"https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},null,null,null,"2024-11-09","2024-11-21","Stable/Final","Completed","2025-04-14","Indicative","Not started","N/A","N/A","Indicative","Not applicable","2025-04-14","Indicative","Not started","https://ep.customs.bg/eportal/","National GUM system (in production as of 07.01.2019) is going to be upgraded in order to implement UCC GUM2 project.\n CT completed with GUM1 component. No CT envisaged with the economic operators.",null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","2025-06-02","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-02","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2024-10-01","Stable/Final","Completed","2024-12-01","2025-01-01","Stable/Final","Completed","2025-01-01","Stable/Final","Completed",null,null,null,null,"2025-01-01","Stable/Final","Completed","https://forms.celnisprava.cz/aforms.php?action=fill&id_form=145","GUM2 will be connected to GUM1 in June 2025",null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,"2025-11-15","Indicative","In progress",null,null,null,null,null,null,null,"www.zoll.de","This project will be implemented as part of the major release of the national IT-System ATLAS (Release 10.2), which will be oprational in parallel to CCI.",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2025-04-01","Indicative","Not started","2025-08-01","2025-09-07","Indicative","Not started","2025-09-30","Indicative","Not started","2025-09-30","Not provided","Indicative","Not started","2025-09-30","Indicative","Not started","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","2024-06-09","Stable/Final","Completed","N/A","N/A","Stable/Final","Not applicable","2025-06-02","Stable/Final","In progress","https://www.emta.ee/ariklient/toll-\nkaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Revenue Department","GUM-NPM-EE@emta.ee","    00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2016-06-30","Stable/Final","Completed","2016-07-01","2016-08-31","Stable/Final","Completed","2016-09-01","Stable/Final","Completed","2016-09-01","2019-05-01","Stable/Final","Completed","2019-05-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","2025-05-24","Stable/Final","In progress","N/A","N/A",null,"Not applicable","2025-05-24","Stable/Final","In progress",null,"National GUM goes into production in several phases, NCTS part was deployed on Q4/2024. The final phase (integration to CRS + Import) will be in production Q2/2025",null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2025-06-01","Indicative","In progress","NA","NA",null,"Not applicable","2025-12-31","Indicative","Not started","2025-12-31","2026-03-30","Indicative","Not started","2026-03-30","Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report",null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office FIN 3 DGDDI","dg-fin3@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2025-06-30","Indicative","Not started","2025-12-31","Indicative","Indicative","Not started","2026-03-31","Indicative","Not started","N/A","N/A",null,"Not applicable","2026-03-31","Indicative","Not started","https://www.aade.gr/customs","NATIONAL GAURANTEE MANAGEMENT SYSTEM ALREADY IN PRODUCTION - IT WILL BE UPGRADED IN ORDER TO SUPPORT SOME NEW FUNCTIONALITIES",null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},"Not appointed yet"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"03/31/2025","Indicative","In progress","N/A","N/A",null,"Not applicable","2025-06-02","Indicative","Not started",null,null,null,null,"2025-06-02","Indicative","Not started","https://carina.gov.hr","Depending on the internal  resources, budget and priorities of development of other systems which have to be iplemented in the next period",null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","hrais3@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2025-03-01","Indicative","Not started","2025-04-01","2025-05-15","Indicative","Not started","2025-06-01","Indicative","Not started",null,null,null,null,"2025-06-01","Indicative","Not started","https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D",null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2019-10-04","Stable/Final","Completed","2020-04-30","2021-10-04","Stable/Final","Completed","2020-11-23","Stable/Final","Completed","2020-11-23","2021-10-04","Stable/Final","Completed","2021-10-05","Stable/Final","Completed","www.revenue.ie","Review undertaken - no requriement for IE to build additional system. ",null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2024-11-29","Indicative","In progress","2025-04-01","2025-05-16","Indicative","Not started","2025-06-02","Indicative","Not started",null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/web/guest/home",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2021-11-01","Stable/Final","Completed","2022-03-01","2022-08-31","Stable/Final","Completed","2022-11-16","Stable/Final","Completed","2022-10-17","2023-03-19","Stable/Final","Completed","2023-03-20","Stable/Final","Completed","https://lrmuitine.lt/web/guest/988",null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Tax Administration Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_GUM_C2_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","2025-06-01","indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-01","indicative","Not started",null,"The dates for GUM phase 2 are purely Indicative till now",null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"N/A","stable/final","Completed","N/A","N/A","stable/final","Completed","2018-06-03","stable/final","Completed","N/A","N/A","stable/final","Completed","2018-06-04","stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","National guarantee system has been updated along with national import system. Implementation of the interface between national GUM and central GUM component is under analysis. ",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"TBD","Indicative","Not started","TBD","TBD","Indicative","Not started","2025-06-02","Indicative","Not started",null,null,null,null,"2025-06-02","Indicative","Not started","www.customs.gov.mt","Due to the small amount of movements that Maltese EOs have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a GUI where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.",null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","2025-06-01","Indicative","In progress","N/A","N/A",null,"Not applicable","2025-06-01","Indicative","Not started","https://www.nhdouane.nl/","GUM2 is the implementation of the national guarantee management system. No conformance tests with EO's or TAXUD needed, therefor the migration (transitional period) for EO's and external communication is not applicable. ",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2021-12-31","Stable/Final","Completed","2024-12-01","2025-06-02","Indicative","Not started","2025-06-02","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-02","Indicative","Not started","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje/system-osoz2",null,null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","osoz2.admin.ias.350000@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","2025-04-04","Indicative","Not started",null,null,null,null,"2025-04-07","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Pages/default.aspx","There is no Technical Specifications to the external interface.",null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","2025-06-30","Indicative","In progress","N/A","N/A",null,"Not applicable","2025-06-30","Indicative","Not started","www.customs.ro","There is no Tehnical Specification to external communication. Updated together with national import system. ",null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Guarantee Office","vama@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2021-04-17","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2021-04-17","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/internationalbusiness/guarantee.4.3e6caad21870dc6781c37fb.html","Dates for technical spec and CT are not applcable since there will be no external domain for the Economic Operator (EO) to the system. There will be a webservice for the EO to check the reference amount. ",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Revenue Department","projekt.import@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","2025-06-01","Stable/Final","In progress","N/A","N/A",null,"Not applicable","2025-06-01","Stable/Final","Not started",null,"Conformance Testing in relation to the connection between GUM 2 and GUM 1 is planned from 01/01/2025 to 20/05/2025. The Conformance Testing on GUM 2 with the traders is not foreseen. ",null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"UP-OZP","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"2025-06-01","indicative","In progress","2025-06-01","2025-12-01","indicative","Not started","2026-01-01","indicative","Not started",null,null,null,null,"2026-01-01","indicative","Not started",null,null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (LH)","cis@financnasprava.sk","00421 2 48273232"]

{"sheet":"CCI-P1","index":17,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A10","v":"UCC Centralised Clearance for Import (Phase 1)"},"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"2024-10-01","Stable/Final","In progress","2025-02-28","2025-11-07","Indicative","Not started","2025-11-01","Indicative","Not started","N/A","N/A","Stable/Final","Not applicable","2025-11-14","Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/9","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51440"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable","N/A","N/A","","Not applicable","N/A","","Not applicable","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0","Beligum will skip phase 1 and move to phase 2 directly",null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2023-06-26","Stable/Final","Completed","2023-09-04","2023-10-16","Stable/Final","Completed","2023-11-10","Stable/Final","Completed",null,null,null,null,"2024-01-15","Stable/Final","Completed","https://ep.customs.bg/eportal/",null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-05-22","Stable/Final","Completed","N/A","N/A","","Not applicable","2025-06-02","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-06-02","Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2024-06-30","Stable/Final","Completed","2025-07-01","2025-12-14","Indicative","Not started","2025-12-15","Indicative","Not started",null,null,null,null,"2025-12-15","Indicative","Not started","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"2024-11-22","Indicative","In progress","2025-09-01","2026-10-30","Indicative","In progress","2025-11-15","Indicative","In progress","N/A","N/A","Indicative","Not applicable","2025-11-15","Indicative","In progress","www.zoll.de","This project will be implemented as part of the major release of the national IT-System ATLAS (Release 10.2) as a new trans-European system.\nNote om CT: the duration of this phase depends on the number of EO who will participate and will be extended when needed.\nNote on migration: Migration from phase 1 to phase 2 is not required.\nA first version of the technical specifications are published and will be updated and complemented following the iterative approach of the development.  ",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2025-04-01","Indicative","Not started","2025-08-01","2025-09-07","Indicative","Not started","2025-09-30","Indicative","Not started","2025-09-30","Not provided","Indicative","Not started","2025-09-30","Indicative","Not started","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2024-04-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-09","Stable/Final","Completed","2024-06-08","2024-06-09","Stable/Final","Completed","2024-06-09","Stable/Final","Completed","https://www.emta.ee/ariklient/toll-\nkaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","CCI-NPM-EE@emta.ee","    00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2022-03-14","Stable/Final","Completed","2022-07-04","tbc","Stable/Final","Completed","2022-09-30","Stable/Final","Completed","2022-10-03","2022-10-03","Stable/Final","Completed","2022-10-03","Stable/Final","Completed","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","H1.info@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2024-12-31","Stable/Final","Completed","2025-06-30",null,"Stable/Final","In progress","2025-05-24","Stable/Final","In progress","2025-05-25","N/A","Stable/Final","Not started","2025-05-24","Stable/Final","Not started",null,"Traders will start to use CCI according to their own needs, hence no end data for migration. Derogation request has been sent.",null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2025-06-30","Indicative","In progress","2026-04-01","2026-06-30","Indicative","Not started","2026-06-30","Indicative","Not started","N/A","N/A","Indicative","Not applicable","2026-06-30","Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report",null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2024-12-31","Indicative","Not started","2025-03-31","2025-06-30","Indicative","Not started","2025-06-30","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-30","Indicative","Not started","https://www.aade.gr/customs","IMPLEMENT PHASE 1 AND 2 ON THE SAME TIME","derogation request",{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"IMPORT_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2023-10-31","Stable/Final","Completed","2023-12-01","2024-09-29","Stable/Final","Completed","2024-09-30","Stable/Final","Completed",null,null,null,null,"2024-09-30","Stable/Final","Completed","https://carina.gov.hr ",null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","hrais3@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D",null,"The replanning of the developments are in progress. Probably NA_HU will request derogation.",{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2023-06-23","Stable/Final","Completed","2025-06-03","2026-01-19","Stable/Final","Not started","2026-01-20","Stable/Final","Not started","2026-01-20","2026-04-20","Stable/Final","Not started","2026-04-21","Stable/Final","Not started","www.revenue.ie","Revised trader specifications issued in June 2024",null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2023-01-31","Stable/Final","Completed","2024-07-01","2024-09-13","Stable/Final","Completed","2024-11-04","Stable/Final","Completed",null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/web/guest/home",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2023-10-31","Stable/Final","Completed","2024-03-18","2024-05-28","Stable/Final","Completed","2024-07-01","Stable/Final","Completed","2024-06-30","2024-06-30","Stable/Final","Completed","2024-07-01","Stable/Final","Completed","https://lrmuitine.lt/web/guest/591",null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_CC_IMP_P1-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2023-10-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-30","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/National_Import_System.html","NA-LU will already implement the P2 messages with the go-live of CCI P1\nNo economic operator available for conformance testing.",null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"N/A","stable/final","Completed","N/A","N/A","Stable/Final","Completed","2024-07-01","Stable/Final","Completed","N/A","N/A","stable/final","Completed","2024-07-01","Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","CCI is a part of the new national import system (AIS). GUI is provided, API will be added on later stages if needed (no business case so far).",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"N/A","Indicative","Not applicable","2024-11-18","2025-03-14","Indicative","Not started","2025-06-02","Indicative","Not started",null,null,null,null,"2025-06-02","Indicative","Not started","www.customs.gov.mt",null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2025-02-01","Indicative","Not started","2025-02-01","2025-05-01","Indicative","Not started","2025-05-01","Indicative","Not started","2025-05-01","2025-11-01","indicative","Not started","2025-11-01","Indicative","Not started","https://www.nhdouane.nl/","Impact and planning are at the moment being analysed. An update will be send as soon as the planning is more clear.",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2022-07-30","Stable/Final","Completed","2023-06-01","2024-05-30","Stable/Final","Completed","2024-07-01","Stable/Final","Completed","2024-06-30","2024-07-01","Stable/Final","Completed","2024-07-01","Stable/Final","Completed","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje  ",null,null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2022-07-01","Stable/Final","Completed","2025-03-01","2025-06-27","Indicative","In progress","2025-06-28","Indicative","Not started",null,null,null,null,"2025-07-01","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/STADA_Importacao_CAU/Pages/default.aspx","Derrogation request to second semester 2024",null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2024-05-30","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-07-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-07-01","Stable/Final","Completed","www.customs.ro",null,null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","cci.aut@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2024-12-02","Stable/Final","In progress","2025-03-01","N/A","Indicative","Not started","2025-06-02","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-02","Indicative","Not started","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/importinggoods/customsdeclarationsforimports/centralisedcustomsclearanceimport.4.26dbb8018fc32e89b7302ef.html","No need for migration since we have no authorisations today.",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.import@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2021-03-01","Stable/Final","Completed","2024-09-01","2025-03-31","Indicative","In progress","2025-05-26","Indicative","Not started","2025-05-30","2025-06-02","Indicative","Not started","2025-06-02","Indicative","Not started","https://www.fu.gov.si/carina/poslovanje_z_nami/centralizirano_carinjenje/",null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"2025-02-15","Indicative","In progress","2025-10-15","2025-12-31","Indicative","Not started","2026-01-01","Indicative","Not started","2026-01-01","2026-01-01","Indicative","Not started","2026-01-01","Indicative","Not started",null,null,"Request for derogation sent on 2nd of October 2023 ",{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]

{"sheet":"CCI-P2","index":18,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A11","v":"UCC Centralised Clearance for Import (Phase 2)"},"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"2024-10-01","Stable/Final","In progress","2025-02-28","2025-11-07","Indicative","Not started","2025-11-01","Indicative","Not started","N/A","N/A","Stable/Final","Not applicable","2025-11-14","Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/10","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51441"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"N/A","Indicative","Not applicable","2025-04-01","2025-04-01","Indicative","Not started","2025-06-02","Indicative","Not started","2025-06-02","2025-06-02","Indicative","Not started","2025-06-02","Indicative","Not started","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2024-12-13","Stable/Final","Completed","2025-02-03","2025-02-28","Indicative","Not started","2025-04-21","Indicative","Not started",null,null,null,null,"2025-04-21","Indicative","Not started","https://ep.customs.bg/eportal/",null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2024-11-30","Indicative","Completed","N/A","N/A","","Not applicable","2025-06-02","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-06-02","Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2024-06-30","Stable/Final","Completed","2025-07-01","2025-12-14","Indicative","Not started","2025-12-15","Indicative","Not started",null,null,null,null,"2025-12-15","Indicative","Not started","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"2024-11-22","Indicative","In progress","2025-09-01","2026-10-30","Indicative","In progress","2025-11-15","Indicative","In progress","N/A","N/A","Indicative","Not applicable","2025-11-15","Indicative","In progress","www.zoll.de","Please refer to CCI-Phase 1.",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2025-04-01","Indicative","Not started","2025-08-01","2025-09-07","Indicative","Not started","2025-09-30","Indicative","Not started","2025-09-30","Not provided","Indicative","Not started","2025-09-30","Indicative","Not started","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2025-03-31","Stable/Final","In progress","2025-05-05","2025-05-23","Stable/Final","Not started","2025-06-02","Stable/Final","Not started","2025-06-01","2025-06-02","Stable/Final","Not started","2025-06-02","Stable/Final","Not started","https://www.emta.ee/ariklient/toll-\nkaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","CCI-NPM-EE@emta.ee","    00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2024-06-02","Stable/Final","Completed","2025-03-03","2025-06-02","Indicative","Not started","2025-06-02","Indicative","Not started","2025-06-02","2025-06-02","Indicative","Not started","2025-06-02","Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","H1.info@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2024-12-31","Stable/Final","Completed","2025-06-30",null,"Stable/Final","In progress","2025-05-24","Stable/Final","In progress","2025-05-24","N/A","Stable/Final","Not started","2025-05-24","Stable/Final","Not started",null,"Traders will start to use CCI according to their own needs, hence no end data for migration. Derogation request has been sent.",null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2025-09-30","Indicative","Not started","2026-10-01","2026-12-31","Indicative","Not started","2026-12-31","Indicative","Not started","N/A","N/A","Indicative","Not applicable","2026-12-31","Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report",null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2024-12-31","Indicative","Not started","2025-03-31","2025-06-30","Indicative","Not started","2025-06-30","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-30","Indicative","Not started","https://www.aade.gr/customs","IMPLEMENT PHASE 1 AND 2 ON THE SAME TIME",null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"IMPORT_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2024-09-30","Stable/Final","Completed","2025-01-22","2025-02-22","Stable/Final","In progress","2025-06-02","Stable/Final","Not started",null,null,null,null,"2025-06-02","Stable/Final","Not started","https://carina.gov.hr ",null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","hrais3@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D",null,"The replanning of the developments are in progress. Probably NA_HU will request derogation.",{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2023-06-23","Stable/Final","Completed","2025-06-03","2026-01-19","Stable/Final","Not started","2026-01-20","Stable/Final","Not started","2026-01-20","2026-04-20","Stable/Final","Not started","2026-04-21","Stable/Final","Not started","www.revenue.ie","Revised trader specifications issued in June 2024",null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"TBD","Indicative","Not started","TBD","TBD","Indicative","Not started","2025-06-02","Indicative","Not started",null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/web/guest/home",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"31/07/2025","indicative","Not started","01/07/2025","21/11/2025","indicative","Not started","25/11/2025","indicative","Not started","25/11/2025","25/11/2025","indicative","Not started","25/11/2025","indicative","Not started",null,"The new procurement procedure has been started. The delay will not affect the exchange of information between LT and other Member States nor the exchange and storage of information in other Member States, because LT has not issued any authorisation for CCI and isn’t involved in the use of any CCI authorisation as participating Member State.","There will be a big bang for all economic operators. Posible risk - lack of financial resources.",{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_CC_IMP_P2-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2025-01-23","Stable/Final","Completed","TBD","TBD",null,"Not started","2025-06-01","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-06-01","indicative","Not started",null,"No economic operator yet available for conformance testing.",null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"N/A","Stable/Final","Not applicable","N/A","N/A","Stable/Final","Not applicable","2025-06-02","Indicative","Not started","N/A","N/A","stable/final","Not applicable","2025-06-02","indicative","Not started","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas",null,null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"N/A","Indicative","Not applicable","2024-11-27","2025-05-20","Indicative","Not started","2025-09-29","Indicative","Not started",null,null,null,null,"2025-09-29","Indicative","Not started","www.customs.gov.mt",null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2025-02-01","Indicative","Not started","2025-02-01","2025-05-01","Indicative","Not started","2025-05-01","Indicative","Not started","2025-05-01","2025-11-01","indicative","Not started","2025-11-01","Indicative","Not started","https://www.nhdouane.nl/","Impact and planning are at the moment being analysed. An update will be send as soon as the planning is more clear.",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2025-03-01","indicative","Not started","2025-09-01","2026-01-31","indicative","Not started","2026-06-01","indicative","Not started","N/A","N/A",null,"Not applicable","2026-06-01","indicative","Not started",null,"UCC CCI Phase 2 -  will be developed uder new contract (tendering in preparation phase)",null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2025-02-01","Indicative","In progress","2025-09-01","2025-12-20","Indicative","In progress","2025-12-21","Indicative","Not started",null,null,null,null,"2025-12-23","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/STADA_Importacao_CAU/Pages/default.aspx",null,null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2024-09-30","Stable/Final","Completed","N/A","N/A",null,"Not applicable","2025-06-02","Indicative","In progress","N/A","N/A",null,"Not applicable","2025-06-02","Indicative","In progress","www.customs.ro",null,null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","cci.aut@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2026-03-01","Indicative","In progress","2026-06-01","N/A","Indicative","Not started","2026-09-01","Indicative","Not started","N/A","N/A","","Not applicable","2026-09-01","Indicative","Not started","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/importinggoods/customsdeclarationsforimports/centralisedcustomsclearanceimport.4.26dbb8018fc32e89b7302ef.html","No need for migration since we have no authorisations today.",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.import@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2023-10-01","Stable/Final","Completed","2025-02-01","2025-05-20","Indicative","Not started","2025-05-26","Indicative","Not started","2025-05-30","2025-06-02","Indicative","Not started","2025-06-02","Indicative","Not started","https://www.fu.gov.si/carina/poslovanje_z_nami/centralizirano_carinjenje/",null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"2025-02-15","Indicative","In progress","2025-10-15","2025-12-31","Indicative","Not started","2026-01-01","Indicative","Not started","2026-01-01","2026-01-01","Indicative","Not started","2026-01-01","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]

{"sheet":"NCTS-P5","index":19,"n_rows":86,"n_cols":28,"rows_kept":86,"cut":false,"hidden":false,"merged":[[74,8,76,8],[74,9,76,9],[74,11,76,11],[74,12,76,12],[74,18,76,18],[74,19,76,19],[74,15,76,15],[74,16,76,16],[77,8,79,8],[77,12,79,12],[77,11,79,11],[77,16,79,16],[77,15,79,15],[77,19,79,19],[77,18,79,18],[77,9,79,9],[5,27,7,27],[5,25,7,25],[5,24,7,24],[5,23,7,23],[8,23,10,23],[8,24,10,24],[8,25,10,25],[8,27,10,27],[11,27,13,27],[11,25,13,25],[11,24,13,24],[11,23,13,23],[5,26,7,26],[8,26,10,26],[11,26,13,26],[14,23,16,23],[14,24,16,24],[14,25,16,25],[14,27,16,27],[17,27,19,27],[17,25,19,25],[17,24,19,24],[17,23,19,23],[26,27,28,27],[23,27,25,27],[20,27,22,27],[23,25,25,25],[23,24,25,24],[23,23,25,23],[20,23,22,23],[20,24,22,24],[20,25,22,25],[26,23,28,23],[26,24,28,24],[26,25,28,25],[14,26,16,26],[17,26,19,26],[20,26,22,26],[23,26,25,26],[26,26,28,26],[41,27,43,27],[35,27,37,27],[35,25,37,25],[41,24,43,24],[35,24,37,24],[35,23,37,23],[41,23,43,23],[38,24,40,24],[38,23,40,23],[38,27,40,27],[38,25,40,25],[32,27,34,27],[29,27,31,27],[29,25,31,25],[29,23,31,23],[29,24,31,24],[32,24,34,24],[32,23,34,23],[32,25,34,25],[29,26,31,26],[32,26,34,26],[35,26,37,26],[38,26,40,26],[62,24,64,24],[62,23,64,23],[50,24,52,24],[50,23,52,23],[47,24,49,24],[47,23,49,23],[53,25,55,25],[50,25,52,25],[50,27,52,27],[59,27,61,27],[59,25,61,25],[56,25,58,25],[56,27,58,27],[47,27,49,27],[53,27,55,27],[44,27,46,27],[65,27,67,27],[65,25,67,25],[65,24,67,24],[65,23,67,23],[68,23,70,23],[68,24,70,24],[68,25,70,25],[68,27,70,27],[50,26,52,26],[53,26,55,26],[56,26,58,26],[59,26,61,26],[62,26,64,26],[65,26,67,26],[68,26,70,26],[47,25,49,25],[44,24,46,24],[44,23,46,23],[59,24,61,24],[59,23,61,23],[56,24,58,24],[62,27,64,27],[62,25,64,25],[71,27,73,27],[71,25,73,25],[71,24,73,24],[71,23,73,23],[74,23,76,23],[74,24,76,24],[74,25,76,25],[74,27,76,27],[77,27,79,27],[77,25,79,25],[77,24,79,24],[77,23,79,23],[71,26,73,26],[74,26,76,26],[77,26,79,26],[83,27,85,27],[83,25,85,25],[83,24,85,24],[83,23,85,23],[80,23,82,23],[80,24,82,24],[80,25,82,25],[80,27,82,27],[80,26,82,26],[83,26,85,26],[83,8,85,8],[83,9,85,9],[83,11,85,11],[83,12,85,12],[83,15,85,15],[83,16,85,16],[83,18,85,18],[83,19,85,19],[80,8,82,8],[80,9,82,9],[80,11,82,11],[80,12,82,12],[80,15,82,15],[80,16,82,16],[80,18,82,18],[80,19,82,19],[71,8,73,8],[71,9,73,9],[71,11,73,11],[71,12,73,12],[71,15,73,15],[68,16,70,16],[68,18,70,18],[68,19,70,19],[68,11,70,11],[68,12,70,12],[71,16,73,16],[71,18,73,18],[71,19,73,19],[65,8,67,8],[65,9,67,9],[65,11,67,11],[65,12,67,12],[68,15,70,15],[68,8,70,8],[68,9,70,9],[62,19,64,19],[62,15,64,15],[62,16,64,16],[65,15,67,15],[65,16,67,16],[65,18,67,18],[65,19,67,19],[62,8,64,8],[62,9,64,9],[62,11,64,11],[62,12,64,12],[62,18,64,18],[56,15,58,15],[56,16,58,16],[56,11,58,11],[56,12,58,12],[59,11,61,11],[59,12,61,12],[56,8,58,8],[56,9,58,9],[59,8,61,8],[59,9,61,9],[59,16,61,16],[59,15,61,15],[53,11,55,11],[50,16,52,16],[50,18,52,18],[50,19,52,19],[53,8,55,8],[53,9,55,9],[53,12,55,12],[53,15,55,15],[53,16,55,16],[50,8,52,8],[50,9,52,9],[50,11,52,11],[50,12,52,12],[50,15,52,15],[53,18,55,18],[53,19,55,19],[47,8,49,8],[47,9,49,9],[47,11,49,11],[47,12,49,12],[47,15,49,15],[47,16,49,16],[47,18,49,18],[47,19,49,19],[44,8,46,8],[44,9,46,9],[44,11,46,11],[44,12,46,12],[44,15,46,15],[44,16,46,16],[44,18,46,18],[41,16,43,16],[41,18,43,18],[41,19,43,19],[35,18,37,18],[35,19,37,19],[32,8,34,8],[32,9,34,9],[41,11,43,11],[41,12,43,12],[41,15,43,15],[35,8,37,8],[35,9,37,9],[35,11,37,11],[35,12,37,12],[35,15,37,15],[35,16,37,16],[38,8,40,8],[38,9,40,9],[38,11,40,11],[38,12,40,12],[38,15,40,15],[38,16,40,16],[32,11,34,11],[32,15,34,15],[32,16,34,16],[32,18,34,18],[32,12,34,12],[20,19,22,19],[20,18,22,18],[20,16,22,16],[20,15,22,15],[23,19,25,19],[29,16,31,16],[29,18,31,18],[29,19,31,19],[23,18,25,18],[26,18,28,18],[26,19,28,19],[29,8,31,8],[29,9,31,9],[29,11,31,11],[29,12,31,12],[29,15,31,15],[23,12,25,12],[23,11,25,11],[23,15,25,15],[23,16,25,16],[26,11,28,11],[26,12,28,12],[26,15,28,15],[26,16,28,16],[23,9,25,9],[26,8,28,8],[26,9,28,9],[8,8,10,8],[20,12,22,12],[20,11,22,11],[17,12,19,12],[17,11,19,11],[14,12,16,12],[14,11,16,11],[17,9,19,9],[17,8,19,8],[14,9,16,9],[14,8,16,8],[11,8,13,8],[20,9,22,9],[17,19,19,19],[17,18,19,18],[17,16,19,16],[17,15,19,15],[14,19,16,19],[14,18,16,18],[14,16,16,16],[14,15,16,15],[8,19,10,19],[8,18,10,18],[8,16,10,16],[8,15,10,15],[5,18,7,18],[5,16,7,16],[5,15,7,15],[8,9,10,9],[11,19,13,19],[11,18,13,18],[11,16,13,16],[11,15,13,15],[11,9,13,9],[8,12,10,12],[8,11,10,11],[11,12,13,12],[11,11,13,11],[59,3,61,3],[56,5,58,5],[56,4,58,4],[53,5,55,5],[53,4,55,4],[53,3,55,3],[62,5,64,5],[62,4,64,4],[62,3,64,3],[59,5,61,5],[59,4,61,4],[83,5,85,5],[83,4,85,4],[83,3,85,3],[80,5,82,5],[80,4,82,4],[80,3,82,3],[68,4,70,4],[68,3,70,3],[65,5,67,5],[65,4,67,4],[65,3,67,3],[74,5,76,5],[74,4,76,4],[74,3,76,3],[71,5,73,5],[71,4,73,4],[71,3,73,3],[68,5,70,5],[77,3,79,3],[77,5,79,5],[77,4,79,4],[65,1,67,1],[62,1,64,1],[59,1,61,1],[56,1,58,1],[53,1,55,1],[5,1,7,1],[83,1,85,1],[20,1,22,1],[17,1,19,1],[14,1,16,1],[11,1,13,1],[8,1,10,1],[32,1,34,1],[29,1,31,1],[38,1,40,1],[80,1,82,1],[77,1,79,1],[74,1,76,1],[71,1,73,1],[68,1,70,1],[26,1,28,1],[23,1,25,1],[50,1,52,1],[47,1,49,1],[2,25,2,27],[2,23,2,24],[2,17,2,19],[3,3,3,5],[3,6,3,9],[3,10,3,12],[3,13,3,16],[3,17,3,19],[2,3,2,5],[2,6,2,9],[2,10,2,12],[2,13,2,16],[44,1,46,1],[41,1,43,1],[35,1,37,1],[41,5,43,5],[41,4,43,4],[41,3,43,3],[35,5,37,5],[35,4,37,4],[35,3,37,3],[44,5,46,5],[44,4,46,4],[44,3,46,3],[38,4,40,4],[38,3,40,3],[38,5,40,5],[50,5,52,5],[50,4,52,4],[50,3,52,3],[47,5,49,5],[47,4,49,4],[47,3,49,3],[5,19,7,19],[59,19,61,19],[59,18,61,18],[41,8,43,8],[41,9,43,9],[56,3,58,3],[8,5,10,5],[8,4,10,4],[8,3,10,3],[23,4,25,4],[23,3,25,3],[20,5,22,5],[20,4,22,4],[11,5,13,5],[11,4,13,4],[11,3,13,3],[20,3,22,3],[14,5,16,5],[5,3,7,3],[5,5,7,5],[5,4,7,4],[5,12,7,12],[5,11,7,11],[5,9,7,9],[5,8,7,8],[32,3,34,3],[26,5,28,5],[26,4,28,4],[26,3,28,3],[23,5,25,5],[17,5,19,5],[17,4,19,4],[17,3,19,3],[14,4,16,4],[14,3,16,3],[29,5,31,5],[29,4,31,4],[29,3,31,3],[32,5,34,5],[32,4,34,4],[20,8,22,8],[23,8,25,8],[41,26,43,26],[44,26,46,26],[47,26,49,26],[56,18,58,18],[56,19,58,19],[32,19,34,19],[44,19,46,19],[38,18,40,18],[38,19,40,19],[56,23,58,23],[53,24,55,24],[53,23,55,23],[41,25,43,25],[44,25,46,25]]}
[]
[]
[null,null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A12","v":"UCC NCTS upgrade (Phase 5)"},null,"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"Single deployment","2023-12-01","Stable/Final","Completed","2024-07-01","2024-09-19","Stable/Final","Completed","2024-12-02","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-12-01","Stable/Final","Completed","https://www.bmf.gv.at/themen/zoll/ACCS/ncts5.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/11","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51442"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"Single deployment","2021-09-01","Stable/Final","Completed",null,null,"Indicative","In progress",null,"Indicative","In progress","N/A","N/A","Stable/Final","Completed","2025-05-21","Stable/Final","Completed","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,null,"Step 1","2021-09-01",null,null,null,null,null,null,"21/01/2025"]
[null,null,"Step 2","2021-09-01",null,null,null,null,null,null,"31/12/2025"]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"Single deployment","2022-08-31","Stable/Final","Completed","2023-07-24","2023-08-11","Stable/Final","Completed","2023-08-28","Stable/Final","Completed",null,null,null,null,"2023-08-28","Stable/Final","Completed","https://ep.customs.bg/eportal/",null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","MASP_BG@customs.bg","+359 2 9859 4528"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"Single deployment","N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","N/A","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,null,"Step 1",null,null,null,"2024-03-18","2024-04-19",null,null,"2024-04-24",null,null,"N/A","N/A",null,null,"2024-04-24"]
[null,null,"Step 2",null,null,null,"2024-11-01","2024-11-29",null,null,"2025-01-20",null,null,"N/A","N/A",null,null,"2025-01-20"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"Single deployment","2021-10-21","Stable/Final","Completed","2022-03-01","2023-09-30","Stable/Final","Completed","2023-10-01","Stable/Final","Completed",null,null,null,null,"2023-10-01","Stable/Final","Completed","https://www.celnisprava.cz/cz/clo/e-customs/ncts/Stranky/dokumentace-pro-vyrobce-SW-UCC-NCTS.aspx","In CZ will be \"big bang\". All economic operators will start at the same date. ",null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"Single deployment","2020-10-09","Stable/Final","Completed","2021-04-19","2023-10-29","Stable/Final","Completed","2021-03-06","Stable/Final","Completed","2021-04-19","2023-11-30","Stable/Final","Completed","2023-10-29","Stable/Final","Completed","www.zoll.de","This component is implemented in the major release of the national IT-System ATLAS (Release 9.1)",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,null,"Step 1"]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"The functionality \"Interface with AES\" is already covered by the national IT-systems ATLAS (Release 9.1) and AES Release 3.0 and the primary requirements are activated on 21.01.2025."]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"Single deployment","2022-08-01","Stable/Final","Completed","2023-03-01","2023-05-22","Stable/Final","Completed","2023-07-29","Stable/Final","Completed","2023-07-29","2024-07-08","Stable/Final","Completed","2024-07-08","Stable/Final","Completed","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"Single deployment","2022-05-31","Stable/Final","Completed","2023-03-01","2023-09-01","Stable/Final","Completed","2023-09-30","Stable/Final","Completed","2023-09-30","2023-09-30","Stable/Final","Completed","2023-10-01","Stable/Final","Completed","https://www.emta.ee/ariklient/e-teenused-koolitused/e-teenuste-kasutamine/teenuste-tehniline-info#ncts",null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","NCTS-NPM-EE@emta.ee","00 372 8800 814"]
[null,null,"Step 1","2022-05-31"]
[null,null,"Step 2","2022-05-31"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"Single deployment","2022-06-30","Stable/Final","Completed","2022-12-19","2024-03-11","Stable/Final","Completed","2023-10-03","Stable/Final","Completed","2023-10-03","2024-03-11","Stable/Final","Completed","2024-03-12","Stable/Final","Completed","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"NCTS P5 Information","NCTSP5.info@correo.aeat.es"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"Single deployment","2022-03-31","Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","In progress",null,null,"Stable/Final","Completed",null,"Stable/Final","In progress","https://finnishcustoms-suomentulli.github.io/MIGs/Transit/en/index.html","The first step  contains all except integration to AES, prior decl and reduced dataset decl . Those will be implemented in step 2 which will be deployed in Q4/2024.Progress column indicates step 1.",null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,null,"Step 1",null,null,null,"2023-06-30","2023-12-31",null,null,"2023-12-31",null,null,"2023-12-31","2023-12-31",null,null,"2023-12-31"]
[null,null,"Step 2",null,null,null,"2024-06-30","2024-12-31",null,null,"2024-10-05",null,null,"2024-10-05","2024-10-05",null,null,"2024-10-05"]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"Single deployment","2021-11-01","Stable/Final","Completed","2024-05-01","2024-10-15","Stable/Final","Completed","2024-11-23","Stable/Final","Completed","2024-11-23","2025-01-22","Stable/Final","Completed","2025-01-22","Stable/Final","Completed","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report","Updated planning",{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-transit@douane.finances.gouv.fr"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"Single deployment","2024-08-31","Stable/Final","In progress","2024-07-29","2024-11-29","Stable/Final","Not started","2024-12-16","Stable/Final","Not started","N/A","N/A","Stable/Final","Not applicable","2024-12-16","Stable/Final","Not started","https://www.aade.gr/customs",null,"derogation request",{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"NCTS_NPM@AADE.GR"]
[null,null,"Step 1",null,null,null,"N/A","N/A",null,null,null,null,null,null,null,null,null,"N/A"]
[null,null,"Step 2",null,null,null,"N/A","N/A",null,null,null,null,null,null,null,null,null,"N/A"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"Single deployment","2022-01-02","Stable/Final","Completed","2023-01-30","2023-05-31","Stable/Final","Completed","2023-06-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-06-01","Stable/Final","Completed","https://carina.gov.hr",null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","NCTS@carina.hr",38516102333]
[null,null,"Step 1","2022-01-02"]
[null,null,"Step 2","2022-01-02"]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"Single deployment","2024-03-28","Stable/Final","Completed","2024-07-01","2024-11-15","Stable/Final","Completed","2025-01-21","Stable/Final","Completed",null,null,null,null,"2025-01-21","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,null,"Step 1","2024-01-01"]
[null,null,"Step 2","2024-01-01"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"Single deployment","2022-08-19","Stable/Final","Completed",null,null,"Stable/Final","In progress"," ","Stable/Final","In progress"," "," ","Stable/Final","In progress"," ","Stable/Final","In progress","www.revenue.ie",null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,null,"Step 1",null,null,null,"2023-05-26","2025-01-21",null,null,"2023-11-30",null,null,"2024-07-01","2024-12-31",null,null,"2025-01-01"]
[null,null,"Step 2",null,null,null,"2024-04-08","2025-06-27",null,null,"2025-06-30",null,null,"2025-06-30","2025-06-30",null,null,"2025-06-30"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"Single deployment","2021-02-15","Stable/Final","Completed","2022-02-01","2023-05-07","Stable/Final","Completed","2023-11-29","Stable/Final","Completed","2023-07-13","2024-12-01","Stable/Final","Completed","2024-12-01","Stable/Final","Completed","https://www.adm.gov.it/portale/dichiarazioni-transito",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"Single deployment","2024-02-01","Stable/Final","Completed","2024-08-01","28/11/2024","Stable/Final","Completed","02/11/2024","Stable/Final","Completed","2024-09-01","28/11/2024","Stable/Final","Completed","01/12/2024","Stable/Final","Completed","https://lrmuitine.lt/web/guest/599 ","There will be a big bang for all economic operators.",null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_NCTS_C1-LT@lrmuitine.lt","370 5 236 2302"]
[null,null,"Step 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Single deployment"]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Single deployment"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"Single deployment","2022-02-22","Stable/Final","Completed","2022-09-01","2024-10-01","Stable/Final","Completed","2023-05-10","Stable/Final","Completed","2023-05-23","2024-12-02","Stable/Final","Completed","2024-12-02","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/NCTS-phase-5.html",null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"Single deployment","2021-03-01","Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas",null,null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","nctshelpdesk@vid.gov.lv","+371 67120000"]
[null,null,"Step 1",null,null,null,"2023-02-01","2023-11-24",null,null,"2023-11-27",null,null,"N/A","N/A",null,null,"2023-11-27"]
[null,null,"Step 2",null,null,null,"2024-08-01","2024-11-30",null,null,"2024-12-01",null,null,"N/A","N/A",null,null,"2024-12-01",null,null,null,"Interface with AES and functionality of \"D type\" declaration is implemented in national NCTS5 production environment in 2024 Q4, the development of the national legislation for the use of the functionalities will be completed in Q1 2025"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"Single deployment","N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","2025-02-04","Indicative","Not started",null,null,null,null,"2025-02-04","Indicative","Not started","www.customs.gov.mt","Due to the small amount of movements that Maltese EOs have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a GUI where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.",null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"Single deployment","2023-12-11","Stable/Final","Completed","2024-03-01","2024-05-30","Stable/Final","Completed","2024-10-29","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-10-31","Stable/Final","Completed","https://www.nhdouane.nl/",null,null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,null,"Step 1"]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"The interface between NCTS P5 and AES has not been completed yet"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"Single deployment","2021-05-31","Stable/Final","Completed","2023-01-16","2023-12-21","Stable/Final","Completed","2024-10-31","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-10-31","Stable/Final","Completed","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje/#ncts2","RfC.41 implemented",null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","ncts.hd@mf.gov.pl","48 (22) 694 50 05"]
[null,null,"Step 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Jacek Krysztofiak","jacek.krysztofiak@mf.gov.pl",48426388012]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Jacek Krysztofiak","jacek.krysztofiak@mf.gov.pl",48426388012]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"Single deployment","2023-01-10","Stable/Final","Completed","2023-03-15","2024-12-31","Stable/Final","Completed","2025-01-20","Stable/Final","Completed",null,null,null,null,"2025-01-21","Stable/Final","Completed","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Stada_Transito_CAU/Paginas/default.aspx",null,null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"Single deployment","2023-01-06","Stable/Final","Completed","2023-05-15","2023-11-30","Stable/Final","Completed","2023-05-15","Stable/Final","Completed",null,null,null,null,"2024-05-17","Stable/Final","Completed","www.customs.ro","NCTS5 is fully operational ",null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Tranzit office","tranzitcentraloffice@customs.ro",40213155858]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"Single deployment","2022-09-01","Stable/Final","Completed","2023-03-10","2024-01-28","Stable/Final","Completed","2024-01-28","Stable/Final","Completed","2024-01-28","2024-01-28","Stable/Final","Completed","2024-01-28","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/updateofthenewcomputerisedtransitsystemncts.4.21f3dd0d183a9e9ca643a08.html",null,null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.transit@tullverket.se",46771520520]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"Single deployment","2020-02-15","Stable/Final","Completed","2021-09-01","2023-01-20","Stable/Final","Completed","2023-02-22","Stable/Final","Completed","2023-02-22","2023-02-22","Stable/Final","Completed","2023-02-22","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148","A single deployment approach",null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OUT","sd.fu@gov.si","01 478 3800"]
[null,null,"Step 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"A single deployment approach"]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"A single deployment approach"]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"Single deployment","2022-12-19","Stable/Final","Completed","2023-10-25","2024-07-13","Stable/Final","Completed","2024-07-28","Stable/Final","Completed","2024-07-28","2024-07-28","Stable/Final","Completed","2024-07-28","Stable/Final","Completed","https://www.financnasprava.sk/sk/elektronicke-sluzby/elektronicka-komunikacia/elektr-komunikacia-clo-emcs/projekty-cku/projekt-nctsp5",null,"Request for derogation sent on 2nd of October 2023 ",{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (IL)","cis@financnasprava.sk","00421-905-418188"]
[null,null,"Step 1"]
[null,null,"Step 2"]

{"sheet":"(CTC) NCTS-P5","index":20,"n_rows":44,"n_cols":28,"rows_kept":44,"cut":false,"hidden":false,"merged":[[38,27,40,27],[38,9,40,9],[38,11,40,11],[38,12,40,12],[38,15,40,15],[38,16,40,16],[38,18,40,18],[41,25,43,25],[41,26,43,26],[41,27,43,27],[41,1,43,1],[41,3,43,3],[41,4,43,4],[41,5,43,5],[41,8,43,8],[41,9,43,9],[38,19,40,19],[38,23,40,23],[38,24,40,24],[41,23,43,23],[41,24,43,24],[41,11,43,11],[41,12,43,12],[41,15,43,15],[41,16,43,16],[41,18,43,18],[41,19,43,19],[35,23,37,23],[35,24,37,24],[35,25,37,25],[35,26,37,26],[35,27,37,27],[38,1,40,1],[38,3,40,3],[38,4,40,4],[38,5,40,5],[38,8,40,8],[35,11,37,11],[35,12,37,12],[35,15,37,15],[35,16,37,16],[35,18,37,18],[35,19,37,19],[35,1,37,1],[35,3,37,3],[35,4,37,4],[35,5,37,5],[35,8,37,8],[35,9,37,9],[38,25,40,25],[38,26,40,26],[32,24,34,24],[32,25,34,25],[32,26,34,26],[32,27,34,27],[32,9,34,9],[32,11,34,11],[32,12,34,12],[32,15,34,15],[32,16,34,16],[32,18,34,18],[29,23,31,23],[29,24,31,24],[29,25,31,25],[29,26,31,26],[29,27,31,27],[32,1,34,1],[32,3,34,3],[32,4,34,4],[32,5,34,5],[32,8,34,8],[29,11,31,11],[29,12,31,12],[29,15,31,15],[29,16,31,16],[29,18,31,18],[29,19,31,19],[29,1,31,1],[29,3,31,3],[29,4,31,4],[29,5,31,5],[29,8,31,8],[29,9,31,9],[32,19,34,19],[32,23,34,23],[26,24,28,24],[26,25,28,25],[26,26,28,26],[26,27,28,27],[26,9,28,9],[26,11,28,11],[26,12,28,12],[26,15,28,15],[26,16,28,16],[26,18,28,18],[23,23,25,23],[23,24,25,24],[23,25,25,25],[23,26,25,26],[23,27,25,27],[26,1,28,1],[26,3,28,3],[26,4,28,4],[26,5,28,5],[26,8,28,8],[23,11,25,11],[23,12,25,12],[23,15,25,15],[23,16,25,16],[23,18,25,18],[23,19,25,19],[23,1,25,1],[23,3,25,3],[23,4,25,4],[23,5,25,5],[23,8,25,8],[23,9,25,9],[26,19,28,19],[26,23,28,23],[20,24,22,24],[20,25,22,25],[20,26,22,26],[20,27,22,27],[20,9,22,9],[20,11,22,11],[20,12,22,12],[20,15,22,15],[20,16,22,16],[20,18,22,18],[17,23,19,23],[17,24,19,24],[17,25,19,25],[17,26,19,26],[17,27,19,27],[20,1,22,1],[20,3,22,3],[20,4,22,4],[20,5,22,5],[20,8,22,8],[17,11,19,11],[17,12,19,12],[17,15,19,15],[17,16,19,16],[17,18,19,18],[17,19,19,19],[17,1,19,1],[17,3,19,3],[17,4,19,4],[17,5,19,5],[17,8,19,8],[17,9,19,9],[20,19,22,19],[20,23,22,23],[14,24,16,24],[14,25,16,25],[14,26,16,26],[14,27,16,27],[14,9,16,9],[14,11,16,11],[14,12,16,12],[14,15,16,15],[14,16,16,16],[14,18,16,18],[11,23,13,23],[11,24,13,24],[11,25,13,25],[11,26,13,26],[11,27,13,27],[14,1,16,1],[14,3,16,3],[14,4,16,4],[14,5,16,5],[14,8,16,8],[11,11,13,11],[11,12,13,12],[11,15,13,15],[11,16,13,16],[11,18,13,18],[11,19,13,19],[11,1,13,1],[11,3,13,3],[11,4,13,4],[11,5,13,5],[11,8,13,8],[11,9,13,9],[14,19,16,19],[14,23,16,23],[8,24,10,24],[8,25,10,25],[8,26,10,26],[8,27,10,27],[8,9,10,9],[8,11,10,11],[8,12,10,12],[8,15,10,15],[8,16,10,16],[8,18,10,18],[5,23,7,23],[5,24,7,24],[5,25,7,25],[5,26,7,26],[5,27,7,27],[8,1,10,1],[8,3,10,3],[8,4,10,4],[8,5,10,5],[8,8,10,8],[5,11,7,11],[5,12,7,12],[5,15,7,15],[5,16,7,16],[5,18,7,18],[5,19,7,19],[5,1,7,1],[5,3,7,3],[5,4,7,4],[5,5,7,5],[5,8,7,8],[5,9,7,9],[8,19,10,19],[8,23,10,23],[2,25,2,27],[3,3,3,5],[3,6,3,9],[3,10,3,12],[3,13,3,16],[3,17,3,19],[2,3,2,5],[2,6,2,9],[2,10,2,12],[2,13,2,16],[2,17,2,19],[2,23,2,24]]}
[]
[]
[null,null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A12","v":"UCC NCTS upgrade (Phase 5)"},null,"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,"AD - Andorra","Single deployment","2020-02-01",null,null,"2022-10-15","2024-09-30",null,null,"2024-06-10",null,null,"2024-06-10","2024-09-30",null,null,"2024-09-30",null,null,null,null,null,4,"2023-12-14"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"CH - Schweiz","Single deployment","2022-06-30",null,null,"2021-12-01","2024-04-30",null,null,"2023-06-01",null,null,"2023-06-01","2024-04-30",null,null,"2024-04-30",null,null,null,null,null,4,"2023-12-01"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"ME - Crna Gora","Single deployment","2020-09-30",null,null,"2022-05-05","2022-06-16",null,null,"2022-05-16",null,null,"2022-05-16","2022-06-16",null,null,"2022-06-16",null,null,null,null,null,4,"2023-12-20"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"MK -  Severna Makedonija","Single deployment","2023-09-21",null,null,"2024-01-11","2024-03-29",null,null,"2024-03-29",null,null,"2024-03-29","2024-03-29",null,null,"2024-03-29",null,null,null,null,null,4,"2023-06-20"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"RS - Srbija","Single deployment","2022-11-15",null,null,"2023-01-09","2024-01-28",null,null,"2024-01-28",null,null,"2024-01-28","2024-01-28",null,null,"2024-01-28",null,null,null,null,null,4,"2024-01-28"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"NO - Norge","Single deployment","2021-06-16",null,null,"2023-04-15","2024-05-31",null,null,"2023-03-06",null,null,"2023-03-06","2024-05-31",null,null,"2024-05-31",null,null,null,null,null,4,"2024-01-16"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"SM - San Marino","Single deployment","N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","N/A",null,"Not applicable",null,null,null,4,"2023-03-08"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"TR - Türkiye","Single deployment","2022-03-30",null,null,"2023-09-12","2024-06-18",null,null,"2024-06-18",null,null,"2024-06-18","2024-06-18",null,null,"2024-06-18",null,null,null,null,null,4,"2023-10-02"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"UA - Ukraïna","Single deployment","2023-01-15",null,null,"2023-08-10","2024-05-01",null,null,"2024-05-01",null,null,"2024-05-01","2024-05-01",null,null,"2024-05-01",null,null,null,null,null,4,"2023-12-01"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"UK - The United Kingdom","Single deployment","2022-08-16",null,null,"2023-05-22","2024-07-01",null,null,"2024-07-01",null,null,"2024-07-01","2024-07-01",null,null,"2024-07-01",null,null,null,null,null,4,"2023-11-29"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"XI - Northern Ireland","Single deployment","2022-08-16",null,null,"2023-05-22","2024-07-01",null,null,"2024-07-01",null,null,"2024-07-01","2024-07-01",null,null,"2024-07-01",null,null,null,null,null,4,"2023-11-29"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"GE - Georgia","Single deployment","2023-04-03",null,null,"2022-11-01","2024-04-03",null,null,"2023-04-03",null,null,"2024-04-03","2024-04-03",null,null,"2024-04-03",null,null,null,null,null,4,"2023-07-18"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,"MD - Moldavia","Single deployment","2024-03-02",null,null,"2024-07-02","2025-04-01",null,null,"2025-04-01",null,null,"2025-04-01","2025-04-01",null,null,"2025-04-01",null,null,null,null,null,4,"2023-11-10"]
[null,null,"Step 1"]
[null,null,"Step 2"]

{"sheet":"NCTS-P6","index":21,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A13","v":"UCC NCTS upgrade (Phase 6)"},"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"2024-10-01","Indicative","Completed",null,null,null,null,"2025-05-31","Indicative","Not started",null,null,null,null,"2025-05-31","Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ncts5.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/12","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51443"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","N/A","Indicative","Not applicable",null,null,null,null,"2025-01-09","Indicative","Not started","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2024-10-25","Stable/Final","Completed","2025-01-20","2025-06-06","Stable/Final","Not started","2025-06-23","Indicative","Not started",null,null,null,null,"2025-06-23","Indicative","Not started","https://ep.customs.bg/eportal/",null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"N/A",null,"Not applicable","2025-07-01","2025-08-15","Stable/Final","Not started","2025-09-01","Stable/Final","Not started","N/A","N/A",null,"Not applicable","2025-09-01","Stable/Final","Not started",null,null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2025-02-28","Stable/Final","In progress","2025-04-01","2025-08-31","Stable/Final","Not started","2025-09-01","Stable/Final","Not started",null,null,null,null,"2025-09-01","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Not applicable, i.e. no impact on EO due to the decision not to make use of the \"combined declaration\" following Art. 130 UCC (NCTS Phase 6).",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2025-04-01","Indicative","Not started","2025-08-01","2025-09-07","Indicative","Not started","2025-09-30","Indicative","Not started","2025-09-30","2025-12-31","Indicative","Not started","2025-09-30","Indicative","Not started","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2025-02-28","Stable/Final","In progress","2025-04-28","2025-08-15","Stable/Final","Not started","2025-08-16","Stable/Final","Not started","N/A","N/A","Stable/Final","Not applicable","2025-08-16","Stable/Final","Not started","https://www.emta.ee/ariklient/toll-kau\nbavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele","We have determined that NCTS phase 6 is closely linked to project.\nICS2 Release 3 and hence the project deadlines should be amended accordingly.",null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","NCTS-NPM-EE@emta.ee","    00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2024-10-03","Indicative","Not started","2025-03-04","2025-06-03","Indicative","Not started","2025-06-03","Indicative","Not started","2025-06-03","2025-09-01","Indicative","Not started","2025-09-02","Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"NCTS P5 Information","NCTSP5.info@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2024-12-31","Stable/Final","Completed","2025-06-30","2025-06-30","Stable/Final","In progress","2025-05-24","Stable/Final","In progress","2025-05-24","N/A","Stable/Final","Not started","2025-05-24","Stable/Final","Not started",null,"Deployment as opt-out. Decision for possible opt-in functionalities foreseen on Q2/2025. ",null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"2025-03-30","Indicative","Not started","2025-07-01","2025-09-30","Indicative","Not started","2025-10-31","Indicative","Not started","2025-10-31","2026-01-31","Indicative","Not started","2026-01-31","Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report","Updated planning",{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-transit@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2025-03-31","Indicative","Not started","2025-06-30","2025-09-30","Indicative",null,"2025-09-30","Indicative","Not started","2025-09-30","2025-09-30","Indicative","Not started","2025-09-30","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"NCTS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2025-03-01","Indicative","Not started","2025-04-01","2025-08-01","Indicative","Not started","2025-09-01","Indicative","Not started","N/A","N/A",null,"Not applicable","2025-09-01","Indicative","Not started","https://carina.gov.hr ",null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","NCTS@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2025-02-20","Indicative","Not started","2025-07-01","2025-08-31","Indicative","Not started","2025-09-01","Indicative","Not started","2025-09-01","2025-09-01","Indicative","Not started","2025-09-01","Indicative","Not started","https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D",null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2025-02-28","Stable/Final","In progress","2025-06-15","2025-08-31","Stable/Final","Not started","2025-09-01","Stable/Final","Not started","2025-09-01","2025-09-01","Stable/Final","Not started","2025-09-01","Stable/Final","Not started","www.revenue.ie",null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2025-04-15","Indicative","In progress",null,null,null,null,"2025-09-01","Indicative","Not started",null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/dichiarazioni-transito",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"30/01/2025","Stable/Final","Completed","02/08/2025","29/08/2025","indicative","Not started","01/09/2025","indicative","Not started","01/09/2025","01/09/2025","indicative","Not started","01/09/2025","indicative","Not started",null,"There will be a big bang for all economic operators. ",null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_NCTS-C2-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2025-06-16","Indicative","In progress","TBD","TBD",null,"Not started","2025-12-01","indicative","Not started","TBD","TBD",null,"Not started","2025-12-01","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"2025-03-01","Indicative","In progress","2025-06-01","2025-08-30","Indicative","Not started","2025-09-01","Indicative","Not started","N/A","N/A","Stable/Final","Not applicable","2025-09-01","Indicative","Not started","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Medium risk of delay",null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","nctshelpdesk@vid.gov.lv","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","2025-09-01","Indicative","Not started",null,null,null,null,"2025-09-01","Indicative","Not started","www.customs.gov.mt","Due to the small amount of movements that Maltese EOs have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a GUI where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.",null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"N/A","Indicative","Not applicable","2025-01-01","2025-03-02","Indicative","Not started","2025-03-03","Indicative","Not started","2025-03-03","2025-08-31","Indicative","Not started","2025-09-01","Indicative","Not started","https://www.nhdouane.nl/",null,null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2026-02-02","Indicative","Not started","2026-04-01","2026-05-29","Indicative","Not started","2026-06-22","Indicative","Not started","2026-06-15","2026-06-19","Indicative","Not started","2026-06-22","Indicative","Not started","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje/#ncts2","NCTS-P6 will be developed uder new contract (tendering in preparation phase)",null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","ncts.hd@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2025-02-01","Indicative","Not started","2025-04-01","2025-08-30","Indicative","Not started","2025-08-31","Indicative","Not started",null,null,null,null,"2025-09-01","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Stada_Transito_CAU/Paginas/default.aspx",null,null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2022-12-31","Indicative","Not started","2026-03-01","2026-06-01","Indicative","Not started","2026-06-01","Indicative","Not started","N/A","N/A",null,"Not applicable","2026-06-01","Indicative","Not started","www.customs.ro","Considering that the entry into production of NCTS phase 5 will take place on May 15, 2024, the implementation date of NCTS phase 6 will be postponed by at least 9 months",null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Tranzit office","tranzitcentraloffice@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2025-01-20","Stable/Final","Completed","2025-03-17","2025-05-17","Indicative","Not started","2025-05-17","Indicative","Not started","2025-05-17","2025-05-17","Indicative","Not started","2025-05-17","Indicative","Not started","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/updateofthenewcomputerisedtransitsystemncts.4.21f3dd0d183a9e9ca643a08.html","The deployment will be a \"big bang\". We are dependent of the delivarables from our contractor so the date 17th of May can still not be defenitaly confirmed. ",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.transit@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2025-03-01","Stable/Final","In progress","2025-05-01","2025-07-30","Stable/Final","Not started","2025-09-01","Stable/Final","Not started","2025-09-01","2025-09-01","Stable/Final","Not started","2025-09-01","Stable/Final","Not started","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148","Opt-out approch",null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OUT","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"2025-03-01","Indicative","In progress","2025-09-01","2026-02-28","Indicative","Not started","2026-03-01","Indicative","Not started",null,null,null,null,"2026-03-01","Indicative","Not started",null,null,"Project is still in planning phase. Once the NCTSP5 is finished, we will provide specific dates.",{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (IL)","cis@financnasprava.sk","00421-905-418188"]

{"sheet":"AES-C1","index":22,"n_rows":113,"n_cols":28,"rows_kept":113,"cut":false,"hidden":false,"merged":[[89,3,92,3],[85,3,88,3],[81,3,84,3],[73,3,76,3],[77,3,80,3],[101,19,104,19],[101,18,104,18],[101,9,104,9],[93,18,96,18],[93,19,96,19],[93,11,96,11],[101,4,104,4],[101,5,104,5],[101,16,104,16],[89,12,92,12],[89,18,92,18],[89,19,92,19],[89,15,92,15],[89,16,92,16],[89,4,92,4],[89,5,92,5],[89,8,92,8],[89,9,92,9],[89,11,92,11],[109,3,112,3],[105,3,108,3],[97,3,100,3],[93,3,96,3],[101,3,104,3],[97,12,100,12],[97,15,100,15],[97,16,100,16],[97,4,100,4],[97,5,100,5],[97,8,100,8],[97,9,100,9],[97,11,100,11],[101,8,104,8],[101,12,104,12],[101,11,104,11],[101,15,104,15],[93,12,96,12],[93,15,96,15],[93,16,96,16],[93,4,96,4],[93,5,96,5],[93,8,96,8],[93,9,96,9],[5,27,8,27],[5,25,8,25],[17,25,20,25],[17,27,20,27],[13,27,16,27],[13,25,16,25],[5,24,8,24],[5,23,8,23],[9,24,12,24],[9,23,12,23],[13,24,16,24],[13,23,16,23],[5,26,8,26],[17,24,20,24],[17,23,20,23],[29,24,32,24],[29,23,32,23],[9,25,12,25],[25,25,28,25],[29,27,32,27],[29,25,32,25],[37,25,40,25],[37,27,40,27],[9,26,12,26],[13,26,16,26],[17,26,20,26],[21,26,24,26],[25,26,28,26],[29,26,32,26],[9,27,12,27],[25,27,28,27],[21,27,24,27],[21,25,24,25],[21,24,24,24],[21,23,24,23],[25,24,28,24],[25,23,28,23],[49,27,52,27],[49,25,52,25],[45,25,48,25],[45,27,48,27],[41,27,44,27],[41,25,44,25],[33,27,36,27],[49,24,52,24],[49,23,52,23],[33,23,36,23],[33,24,36,24],[45,24,48,24],[45,23,48,23],[41,24,44,24],[41,23,44,23],[37,24,40,24],[37,23,40,23],[33,26,36,26],[37,26,40,26],[41,26,44,26],[45,26,48,26],[49,26,52,26],[33,25,36,25],[57,27,60,27],[57,25,60,25],[53,24,56,24],[53,23,56,23],[53,27,56,27],[53,25,56,25],[65,27,68,27],[65,25,68,25],[61,25,64,25],[61,27,64,27],[65,24,68,24],[65,23,68,23],[61,24,64,24],[61,23,64,23],[57,24,60,24],[57,23,60,23],[53,26,56,26],[57,26,60,26],[61,26,64,26],[65,26,68,26],[69,25,72,25],[69,27,72,27],[81,27,84,27],[81,25,84,25],[77,25,80,25],[77,27,80,27],[77,23,80,23],[77,24,80,24],[73,24,76,24],[73,23,76,23],[69,24,72,24],[69,23,72,23],[69,26,72,26],[73,26,76,26],[77,26,80,26],[81,26,84,26],[81,24,84,24],[81,23,84,23],[85,26,88,26],[89,26,92,26],[93,26,96,26],[97,26,100,26],[101,26,104,26],[73,27,76,27],[73,25,76,25],[93,25,96,25],[89,25,92,25],[85,25,88,25],[89,27,92,27],[85,27,88,27],[109,27,112,27],[105,27,108,27],[101,27,104,27],[97,27,100,27],[109,25,112,25],[105,25,108,25],[101,25,104,25],[97,25,100,25],[93,27,96,27],[105,26,108,26],[109,26,112,26],[109,18,112,18],[109,19,112,19],[85,23,88,23],[85,24,88,24],[89,24,92,24],[89,23,92,23],[93,24,96,24],[93,23,96,23],[97,24,100,24],[97,23,100,23],[101,24,104,24],[101,23,104,23],[105,24,108,24],[105,23,108,23],[109,24,112,24],[97,18,100,18],[97,19,100,19],[85,18,88,18],[85,19,88,19],[109,23,112,23],[105,18,108,18],[105,19,108,19],[105,16,108,16],[109,16,112,16],[85,4,88,4],[85,5,88,5],[85,8,88,8],[85,9,88,9],[85,11,88,11],[85,12,88,12],[85,15,88,15],[105,8,108,8],[105,9,108,9],[105,11,108,11],[105,12,108,12],[105,15,108,15],[105,4,108,4],[105,5,108,5],[109,4,112,4],[109,5,112,5],[109,8,112,8],[109,9,112,9],[109,11,112,11],[109,12,112,12],[109,15,112,15],[81,12,84,12],[81,18,84,18],[85,16,88,16],[81,19,84,19],[81,15,84,15],[81,16,84,16],[81,4,84,4],[81,5,84,5],[81,8,84,8],[81,9,84,9],[81,11,84,11],[77,16,80,16],[77,15,80,15],[77,19,80,19],[77,18,80,18],[77,12,80,12],[77,11,80,11],[77,9,80,9],[77,8,80,8],[77,4,80,4],[77,5,80,5],[73,16,76,16],[73,18,76,18],[73,19,76,19],[73,4,76,4],[73,5,76,5],[73,8,76,8],[73,9,76,9],[73,15,76,15],[69,11,72,11],[69,12,72,12],[69,8,72,8],[69,9,72,9],[73,11,76,11],[73,12,76,12],[69,4,72,4],[69,5,72,5],[69,15,72,15],[69,16,72,16],[69,18,72,18],[69,19,72,19],[61,19,64,19],[65,11,68,11],[65,12,68,12],[65,15,68,15],[65,16,68,16],[65,18,68,18],[65,19,68,19],[61,11,64,11],[61,12,64,12],[61,15,64,15],[61,16,64,16],[61,18,64,18],[53,11,56,11],[49,15,52,15],[49,16,52,16],[49,18,52,18],[49,19,52,19],[57,16,60,16],[57,18,60,18],[57,19,60,19],[57,11,60,11],[57,12,60,12],[53,12,56,12],[53,15,56,15],[53,16,56,16],[53,18,56,18],[53,19,56,19],[57,15,60,15],[49,8,52,8],[49,9,52,9],[49,11,52,11],[49,12,52,12],[45,8,48,8],[41,9,44,9],[41,11,44,11],[41,12,44,12],[41,8,44,8],[41,19,44,19],[37,11,40,11],[37,12,40,12],[37,15,40,15],[37,16,40,16],[37,18,40,18],[37,19,40,19],[45,11,48,11],[45,12,48,12],[45,15,48,15],[45,16,48,16],[45,18,48,18],[45,19,48,19],[33,4,36,4],[33,5,36,5],[33,8,36,8],[33,9,36,9],[33,11,36,11],[33,12,36,12],[33,15,36,15],[33,16,36,16],[33,18,36,18],[57,5,60,5],[53,9,56,9],[5,15,8,15],[21,16,24,16],[21,18,24,18],[21,19,24,19],[25,8,28,8],[25,9,28,9],[25,11,28,11],[25,12,28,12],[25,15,28,15],[25,16,28,16],[25,18,28,18],[25,19,28,19],[21,8,24,8],[21,9,24,9],[21,11,24,11],[21,12,24,12],[21,15,24,15],[13,11,16,11],[13,12,16,12],[13,15,16,15],[9,11,12,11],[9,12,12,12],[57,8,60,8],[57,9,60,9],[53,8,56,8],[9,18,12,18],[9,19,12,19],[5,16,8,16],[5,19,8,19],[5,18,8,18],[5,12,8,12],[5,11,8,11],[9,15,12,15],[9,16,12,16],[29,16,32,16],[29,18,32,18],[29,19,32,19],[33,19,36,19],[29,8,32,8],[29,9,32,9],[29,11,32,11],[29,12,32,12],[29,15,32,15],[41,15,44,15],[41,16,44,16],[41,18,44,18],[5,9,8,9],[13,16,16,16],[13,18,16,18],[13,19,16,19],[17,8,20,8],[17,9,20,9],[17,11,20,11],[17,12,20,12],[17,15,20,15],[17,16,20,16],[17,18,20,18],[17,19,20,19],[13,8,16,8],[9,9,12,9],[65,8,68,8],[65,9,68,9],[61,8,64,8],[61,9,64,9],[13,9,16,9],[25,4,28,4],[25,3,28,3],[17,3,20,3],[45,1,48,1],[37,3,40,3],[49,3,52,3],[41,1,44,1],[65,4,68,4],[65,5,68,5],[17,5,20,5],[17,4,20,4],[29,5,32,5],[29,4,32,4],[53,1,56,1],[61,4,64,4],[61,5,64,5],[37,9,40,9],[37,8,40,8],[45,9,48,9],[69,3,72,3],[65,3,68,3],[61,3,64,3],[57,3,60,3],[53,3,56,3],[45,3,48,3],[41,3,44,3],[21,5,24,5],[21,4,24,4],[21,3,24,3],[45,4,48,4],[45,5,48,5],[37,4,40,4],[37,5,40,5],[53,4,56,4],[53,5,56,5],[49,5,52,5],[49,4,52,4],[41,4,44,4],[41,5,44,5],[33,3,36,3],[29,3,32,3],[25,5,28,5],[57,4,60,4],[2,25,2,27],[3,3,3,5],[3,6,3,9],[3,10,3,12],[3,13,3,16],[3,17,3,19],[2,3,2,5],[2,6,2,9],[2,10,2,12],[2,13,2,16],[2,17,2,19],[2,23,2,24],[5,3,8,3],[5,8,8,8],[13,5,16,5],[13,4,16,4],[13,3,16,3],[9,5,12,5],[9,4,12,4],[9,3,12,3],[9,8,12,8],[5,5,8,5],[5,4,8,4],[5,1,8,1],[9,1,12,1],[13,1,16,1],[17,1,20,1],[21,1,24,1],[65,1,68,1],[69,1,72,1],[109,1,112,1],[105,1,108,1],[85,1,88,1],[89,1,92,1],[93,1,96,1],[97,1,100,1],[101,1,104,1],[25,1,28,1],[29,1,32,1],[33,1,36,1],[49,1,52,1],[37,1,40,1],[73,1,76,1],[77,1,80,1],[81,1,84,1],[57,1,60,1],[61,1,64,1]]}
[]
[]
[null,null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A14","v":"UCC AES (Component 1) \"Trans-European AES\""},null,"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"Single deployment","2020-12-31","Stable/Final","Completed","2024-06-10","2024-12-16","Stable/Final","Completed","2025-01-26","Stable/Final","Completed","2025-01-26","2025-05-31","Stable/Final","Not started","2025-06-01","Indicative","In progress","https://www.bmf.gv.at/themen/zoll/ACCS/aes.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/13","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51444"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"Single deployment","2021-09-01","Stable/Final","Completed","2023-06-23","2024-04-12","Stable/Final","Completed","2024-06-23","Stable/Final","Completed","2024-06-23","17/12/2024","Stable/Final","Completed","2024-12-18","Stable/Final","Completed","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,null,"Step 1","2021-09-01"]
[null,null,"Step 2","2021-09-01"]
[null,null,"Step 3","2021-09-01"]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"Single deployment","2022-08-31","Stable/Final","Completed","2023-07-24","2023-08-11","Stable/Final","Completed","2023-08-28","Stable/Final","Completed",null,null,null,null,"2023-08-29","Stable/Final","Completed","https://ep.customs.bg/eportal/",null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"Single deployment","2023-08-01","Stable/Final","Completed","N/A","N/A","Indicative","In progress","N/A","Stable/Final","Completed","N/A","N/A",null,"Not applicable","N/A","Stable/Final","Completed","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,null,"Step 1",null,null,null,"2023-09-18","2023-11-30",null,null,"2023-12-18",null,null,"N/A","N/A",null,null,"2023-12-18"]
[null,null,"Step 2",null,null,null,"N/A","N/A",null,null,"2024-07-31",null,null,"N/A","N/A",null,null,"2024-07-31"]
[null,null,"Step 3",null,null,null,"2025-01-06","N/A",null,null,"2025-01-20",null,null,"N/A","N/A",null,null,"2025-01-20"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"Single deployment","2021-10-21","Stable/Final","Completed","2023-01-02","2023-09-30","Stable/Final","Completed","2023-10-01","Stable/Final","Completed",null,null,null,null,"2023-10-01","Stable/Final","Completed","https://www.celnisprava.cz/cz/clo/e-customs/ecs/Stranky/dokumentace-pro-vyrobce-SW-UCC-AES.aspx","In CZ will be \"big bang\". All economic operators will start at the same date. ",null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"Single deployment","2020-10-09","Stable/Final","Completed","2021-04-19","2023-10-29","Stable/Final","Completed","2021-03-06","Stable/Final","Completed","2021-04-19","2023-11-30","Stable/Final","Completed","2023-10-29","Stable/Final","Completed","www.zoll.de","This component is already implemented in the major release of the national Export System (AES Release 3.0)",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,null,"Step 1"]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"The functionality \"Interface with EMCS\" was activated on 14.02.2024."]
[null,null,"Step 3",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"The functionalities Centralised Clearance and  \"Interface with NCTS\" are already covered by by the national IT-systems ATLAS (Release 9.1) and AES Release 3.0. CCE was activated on 02.12.20224 and the the primary requirements for the \"Interface with NCTS\" were activated on 21.01.2025."]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"Single deployment","2022-08-01","Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed",null,null,"Stable/Final","Completed","2024-05-31","Stable/Final","Completed","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,null,"Step 1",null,null,null,"2023-03-01","2023-07-17",null,null,"2023-07-29",null,null,"2023-07-29","2024-05-31"]
[null,null,"Step 2",null,null,null,"2023-12-06","2023-12-12",null,null,"2024-02-13",null,null,"2024-02-13","2024-05-31"]
[null,null,"Step 3",null,null,null,"2023-12-06","2023-12-12",null,null,"2025-01-21",null,null,"2023-07-29","2024-05-31"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"Single deployment","2022-03-31","Stable/Final","Completed","2023-03-01","2023-09-01","Stable/Final","Completed","2023-09-30","Stable/Final","Completed","2023-09-30","2023-09-30","Stable/Final","Completed","2023-10-01","Stable/Final","Completed","https://www.emta.ee/ariklient/e-teenused-koolitused/e-teenuste-kasutamine/teenuste-tehniline-info#aes\n",null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","AES-NPM-EE@emta.ee","00 372 8800 814"]
[null,null,"Step 1","2022-03-31"]
[null,null,"Step 2","2022-03-31"]
[null,null,"Step 3","2022-03-31"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"Single deployment","2021-04-15","Stable/Final","Completed","2021-11-10","2023-05-08","Stable/Final","Completed","2022-02-22","Stable/Final","Completed","2022-10-18","2023-05-08","Stable/Final","Completed","2023-05-09","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"Single deployment","2023-06-30","Stable/Final","Completed","N/A","N/A","Stable/Final","In progress","N/A","Stable/Final","In progress","N/A","N/A","Stable/Final","Not started","N/A","Stable/Final","Not started","https://finnishcustoms-suomentulli.github.io/MIGs/Export/fi/index.html","The derogation paper has been sent for end date Q2/2024. Unfortunately we have to postpone the date until Q4/2024.  We have devided implementation into two phases. Phase 1  contains normal export, sp, simplifications, centralized clearance and EMCS integration.  Phase 2 contains exit functionalities and integration to EMSWe.  Phase 2 will be deployed Q2/2025. Phase 1 will be found in line for step 1 and phase 2 in line for step 3. Thus the line for step 2 will be empty.",null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,null,"Step 1",null,null,null,"2023-06-30","2024-12-31",null,null,"2024-11-05",null,null,"2024-10-04","2024-11-05",null,null,"2024-11-05",null,null,"https://finnishcustoms-suomentulli.github.io/MIGs/Export/fi/index.html"]
[null,null,"Step 2",null,null,null,"N/A","N/A",null,null,"N/A",null,null,"N/A","N/A",null,null,"N/A"]
[null,null,"Step 3",null,null,null,"2025-03-31","2025-06-30",null,null,"2025-05-24",null,null,"2025-05-24","2025-05-24",null,null,"2025-05-24",null,null,"https://finnishcustoms-suomentulli.github.io/MIGs/Export/fi/index.html"]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"Single deployment","2025-04-30","Indicative","In progress",null,null,"Indicative","Not started",null,"Indicative","Not started",null,null,"Indicative","Not started",null,"Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Deployment of a partial perimeter \nProgress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report","Updated planning",{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-delta@douane.finances.gouv.fr"]
[null,null,"Step 1","Q1 2023",null,null,"2025-03-31","2025-09-30",null,null,"2025-10-30",null,null,"2025-10-30","2025-12-31",null,null,"2025-12-31",null,null,null,null,"Updated planning"]
[null,null,"Step 2","Q1 2023",null,null,"2025-11-01","2025-12-31",null,null,"2026-02-01",null,null,"N/A","N/A",null,null,"2025-12-31",null,null,null,null,"Updated planning"]
[null,null,"Step 3","Q1 2023",null,null,"2027-04-01","2027-09-30",null,null,"2027-09-30",null,null,"2027-09-30","2028-03-30",null,null,"2028-03-30",null,null,null,null,"Updated planning"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"Single deployment","2024-08-31","Stable/Final","In progress","2024-07-29","2024-11-29","Stable/Final","Not started","2024-12-16","Stable/Final","Not started","N/A","N/A","Stable/Final","Not applicable","2024-12-16","Stable/Final","Not started","https://www.aade.gr/customs",null,"derogation request",{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"AES_NPM@AADE.GR"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"Single deployment","2021-12-31","Stable/Final","Completed","2022-10-01","2023-03-10","Stable/Final","Completed","2023-05-02","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-05-03","Stable/Final","Completed","https://carina.gov.hr",null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","AES@carina.hr",38516102333]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"Single deployment","2023-04-03","Stable/Final","Completed",null,null,"Stable/Final","In progress",null,"Indicative","Not started",null,null,null,null,null,"Indicative","Not started","https://openkkk.nav.gov.hu/Megosztott%20dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FE%2DV%C3%81M%20specifik%C3%A1ci%C3%B3k%2FAES&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D",null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,null,"Step 1","2023-03-31",null,null,"2024-05-02","2025-02-11",null,null,"2025-02-12",null,null,null,null,null,null,"2025-02-12"]
[null,null,"Step 2","2023-03-31",null,null,"2024-05-02","2025-02-11",null,null,"2025-02-12",null,null,null,null,null,null,"2025-02-12"]
[null,null,"Step 3","2023-03-31",null,null,"2025-06-01","2025-09-29",null,null,"2025-09-30",null,null,null,null,null,null,"2025-09-30",null,null,null,null,"The CCE, Re-export notification and the EIDR functionalities won't be ready until 2nd December 2024."]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"Single deployment","2022-01-28","Stable/Final","Completed",null,null,"Stable/Final","In progress",null,"Stable/Final","In progress",null,null,"Stable/Final","In progress",null,"Stable/Final","In progress","www.revenue.ie",null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,null,"Step 1",null,null,null,"2022-07-31","2023-03-30",null,null,"2023-03-21",null,null,"2023-03-21","2023-05-21",null,null,"2023-05-21",null,null,null,"Step 1 is complete"]
[null,null,"Step 2",null,null,null,"2022-07-31","2024-12-01",null,null,"2024-02-13",null,null,"2024-02-13","2024-02-13",null,null,"2024-02-13",null,null,null,"Step 2 is complete"]
[null,null,"Step 3",null,null,null,"2024-04-08","2025-06-27",null,null,"2025-06-30",null,null,"2025-06-30","2025-06-30",null,null,"2025-06-30",null,null,null,"CCE is available but EFBT to be completed"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"Single deployment","2021-02-15","Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed","https://www.adm.gov.it/portale/dichiarazioni-export",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,null,"Step 1",null,null,null,"2022-02-01","2023-05-07",null,null,"2023-11-29",null,null,"2023-03-01","2023-05-07",null,null,"2023-06-08"]
[null,null,"Step 2",null,null,null,"N/A","N/A",null,null,"2024-02-13",null,null,"N/A","N/A",null,null,"N/A"]
[null,null,"Step 3",null,null,null,"2024-09-16","2024-11-29",null,null,"2024-12-01",null,null,"2024-11-25","2024-12-01",null,null,"2024-12-01"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"Single deployment","2023-05-04","Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed","https://www.lrmuitine.lt/web/guest/591 ","There will be a big bang for all economic operators.",null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_AES_C1-LT@lrmuitine.lt","370 5 236 2302"]
[null,null,"Step 1",null,null,null,"2023-06-04","2023-12-01",null,null,"2023-12-03",null,null,"2023-12-03","2023-12-03",null,null,"2023-12-03"]
[null,null,"Step 2",null,null,null,"2023-12-03","2023-12-01",null,null,"2023-12-03",null,null,"2023-12-03","2023-12-03",null,null,"2023-12-03"]
[null,null,"Step 3",null,null,null,"2024-03-18","2024-08-31",null,null,"2024-12-01",null,null,"2024-12-01","2024-12-01",null,null,"2024-12-01"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"Single deployment","2023-07-01","Stable/Final","Completed","2024-02-01","2024-09-30","Stable/Final","Completed","2024-07-08","Stable/Final","Completed","2024-07-08","2024-12-01","Stable/Final","Completed","2024-12-02","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/aes.html",null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"Single deployment","N/A","Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas",null,null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,null,"Step 1",null,null,null,"2023-07-10","2023-09-30",null,null,"2023-10-10",null,null,"N/A","N/A",null,null,"2023-10-10",null,null,null,"Full funcionality according to the EU technical specifications including standart and simplified procedures, EXS, REN and Centralised clerance for export has been implemented (GUI)"]
[null,null,"Step 2",null,null,null,"N/A","N/A",null,null,"2024-02-13",null,null,"N/A","N/A",null,null,"2024-02-13",null,null,null,"Adjustsments in the interface with EMCS according the the changes in EMCS"]
[null,null,"Step 3",null,null,null,"N/A","N/A",null,null,"2024-12-01",null,null,"N/A","N/A",null,null,"2024-12-01",null,null,null,"Interface with NCTS is implemented in national AES production environment in 2024 Q4, the development of the national legislation for the use of the functionality will be completed in Q1 2025"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"Single deployment","N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","2025-06-02","Indicative","Not started",null,null,null,null,"2025-06-02","Indicative","Not started","www.customs.gov.mt","Due to the small amount of movements that Maltese EOs have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a GUI where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.",null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"Single deployment","2021-06-22","Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed","https://www.nhdouane.nl/",null,null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,null,"Step 1",null,null,null,"2022-09-20","2022-09-21",null,null,"2023-05-08",null,null,"2023-05-08","2023-11-30",null,null,"2023-12-01"]
[null,null,"Step 2",null,null,null,"2024-01-01","2024-02-12",null,null,"2024-02-13",null,null,"N/A","N/A",null,null,"2024-02-13"]
[null,null,"Step 3",null,null,null,"2024-08-01","2024-12-01",null,null,"2024-12-02",null,null,"N/A","N/A",null,null,"2024-12-02",null,null,null,"CCE and the interface between NCTS P5 and AES have not been completed yet"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"Single deployment","2021-05-15","Stable/Final","Completed","2023-01-16","2024-03-15","Stable/Final","Completed","2024-10-31","Indicative","Completed","N/A","N/A","Stable/Final","Completed","2024-10-31","Stable/Final","Completed","https://puesc.gov.pl/en/uslugi/eksport",null,null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.projekt.ias.350000@mf.gov.pl","48 (22) 694 50 05"]
[null,null,"Step 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Krzysztof Gil","aes.ais.projekt.ias.350000@mf.gov.pl",48126290112]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Krzysztof Gil","aes.ais.projekt.ias.350000@mf.gov.pl",48126290112]
[null,null,"Step 3",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Krzysztof Gil","aes.ais.projekt.ias.350000@mf.gov.pl",48126290112]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"Single deployment","2023-02-22","Stable/Final","Completed","2023-04-01","2025-05-01","Indicative","In progress","2025-05-03","Indicative","Not started",null,null,null,null,"2025-05-06","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Sistema_exportacao_e_saida/Sistema_Automatico_Exportacao/Paginas/default.aspx","Test environment available to EOs. \nDeployment of core and non core funcionalities in the same date.\nDerrogation request to second semester 2024",null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"Single deployment","2023-01-06","Stable/Final","Completed","2023-05-15","2023-11-30","Stable/Final","Completed","2023-05-15","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-03-16","Stable/Final","Completed","https://www.customs.ro/e-customs/aes","AES system is fully operational ",null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","ro_ecshd@customs.ro",40213155858]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"Single deployment","2022-12-15","Stable/Final","Completed","2024-01-24","2024-12-02","Stable/Final","Completed","2024-10-01","Stable/Final","Completed","2024-10-01","2024-12-02","Stable/Final","Completed","2024-12-02","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/exportinggoods.4.422c8052175b1d82769598d.html",null,null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.export@tullverket.se",46771520520]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"Single deployment","2020-12-18","Stable/Final","Completed","2022-05-03","2023-05-23","Stable/Final","Completed","2023-05-24","Stable/Final","Completed","2023-05-24","2023-05-24","Stable/Final","Completed","2023-05-24","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148","A single deployment approach",null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si","01 478 3800"]
[null,null,"Step 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"A single deployment approach"]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"A single deployment approach"]
[null,null,"Step 3",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"A single deployment approach"]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"Single deployment","2023-02-03","Stable/Final","Completed","2023-10-25","2024-10-13","Stable/Final","Completed","2024-11-01","Stable/Final","Completed","2024-11-01","2024-11-01","Stable/Final","Completed","2024-11-01","Stable/Final","Completed","https://www.financnasprava.sk/sk/elektronicke-sluzby/elektronicka-komunikacia/elektr-komunikacia-clo-emcs/projekty-cku/projekt-aes",null,"Request for derogation sent on 2nd of October 2023 ",{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]

{"sheet":"AES-C2","index":23,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null," "]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A15","v":"UCC AES (Component 2) \"National Export Systems upgrade\""},"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"2020-12-31","Stable/Final","Completed","2024-06-10","2024-12-16","Stable/Final","Completed","2025-01-26","Stable/Final","Completed","2025-01-26","2025-05-31","Stable/Final","Not started","2025-06-01","Indicative","In progress","https://www.bmf.gv.at/themen/zoll/ACCS/aes.html",null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/14","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51445"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"2021-09-01","Stable/Final","Completed","2023-06-23","2024-12-17","Stable/Final","Completed","2024-06-23","Stable/Final","Completed","2024-06-23","17/12/2024","Stable/Final","Completed","2024-12-18","Stable/Final","Completed","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"2022-08-31","Stable/Final","Completed","2023-07-24","2023-08-11","Stable/Final","Completed","2023-08-28","Stable/Final","Completed",null,null,null,null,"2023-08-29","Stable/Final","Completed","https://ep.customs.bg/eportal/",null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"2023-08-01","Stable/Final","Completed","2023-09-18","2023-11-30","Stable/Final","Completed","2023-12-18","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-12-18","Stable/Final","Completed","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"2021-10-21","Stable/Final","Completed","2023-01-02","2023-09-30","Stable/Final","Completed","2023-10-01","Stable/Final","Completed",null,null,null,null,"2023-10-01","Stable/Final","Completed","https://www.celnisprava.cz/cz/clo/e-customs/ecs/Stranky/dokumentace-pro-vyrobce-SW-UCC-AES.aspx","In CZ \"big bang\". All economic operators started at the same date. ",null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"2020-10-09","Stable/Final","Completed","2021-04-19","2023-10-29","Stable/Final","Completed","2021-03-06","Stable/Final","Completed","2021-04-19","2023-11-30","Stable/Final","Completed","2023-10-29","Stable/Final","Completed","www.zoll.de","This component is implemented in line with the project \"UCC AES (Component 1) Transeuropean AES\"",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"2022-08-01","Stable/Final","Completed","2023-03-01","2023-12-12","Stable/Final","Completed","2024-02-13","Stable/Final","Completed","2023-07-29","2024-05-31","Stable/Final","Completed","2024-05-31","Stable/Final","Completed","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"2022-03-31","Stable/Final","Completed","2023-03-01","2023-09-01","Stable/Final","Completed","2023-09-30","Stable/Final","Completed","2023-09-30","2023-09-30","Stable/Final","Completed","2023-10-01","Stable/Final","Completed","https://www.emta.ee/ariklient/e-teenused-koolitused/e-teenuste-kasutamine/teenuste-tehniline-info#aes",null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","AES-NPM-EE@emta.ee","    00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2021-04-15","Stable/Final","Completed","2021-11-10","2023-05-08","Stable/Final","Completed","2022-10-18","Stable/Final","Completed","2022-10-18","2023-05-08","Stable/Final","Completed","2023-05-09","Stable/Final","Completed","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"2023-06-30","Stable/Final","Completed","2024-06-30","2024-12-31","Stable/Final","Completed","2024-11-05","Stable/Final","Completed","2024-10-04","2024-11-05","Stable/Final","Completed","2024-11-05","Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Export/en/index.html ","The derogation paper has been sent for end date Q2/2024. Unfortunately we have to postpone the date until Q4/2024.  We have divided implementation into two phases. Phase 1  contains normal export, sp, simplifications, centralized clearance and EMCS integration.  Phase 2 contains exit functionalities and integration to EMSWe.  Phase 2 will be deployed Q2/2025. Phase 1 will be found in line for step 1 and phase 2 in line for step 3. Thus the line for step 2 will be empty.",null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","N/A","Indicative","Not applicable","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report","Updated planning",{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-delta@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"2024-09-30","Stable/Final","In progress","N/A","N/A",null,"Not applicable","2024-12-31","Indicative","Not started","2024-12-31","2024-12-31","Stable/Final","Not started","2024-12-16","Indicative","Not started","https://www.aade.gr/customs",null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"AES_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"2022-01-01","Stable/Final","Completed","2022-10-01","2023-03-10","Stable/Final","Completed","2023-05-02","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2023-05-02","Stable/Final","Completed","https://carina.gov.hr",null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","AES@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"2023-04-03","Stable/Final","Completed","2024-05-02","2025-02-11","Indicative","In progress","2025-02-12","Indicative","Not started",null,null,null,null,"2025-02-12","Indicative","Not started","https://openkkk.nav.gov.hu/Megosztott%20dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FE%2DV%C3%81M%20specifik%C3%A1ci%C3%B3k%2FAES&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D",null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"2022-01-28","Stable/Final","Completed","2022-07-31","2023-03-30","Stable/Final","Completed","2023-03-21","Stable/Final","Completed","2023-03-21","2023-05-21","Stable/Final","Completed","2023-05-21","Stable/Final","Completed","www.revenue.ie",null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"2021-02-15","Stable/Final","Completed","2022-02-01","2023-05-07","Stable/Final","Completed","2023-11-29","Stable/Final","Completed","2023-03-01","2023-05-07","Stable/Final","Completed","2023-06-08","Stable/Final","Completed","https://www.adm.gov.it/portale/dichiarazioni-export",null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"2023-05-04","Stable/Final","Completed","2023-06-04","2023-12-01","Stable/Final","Completed","2023-12-03","Stable/Final","Completed","2023-12-03","2023-12-03","Stable/Final","Completed","2023-12-03","Stable/Final","Completed","https://www.lrmuitine.lt/web/guest/591 ",null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_AES_C2_N-LT@lrmuitine.lt","370 5 236 2302"]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"2023-07-01","Stable/Final","Completed","2024-02-01","2024-09-30","Stable/Final","Completed","2024-07-08","Stable/Final","Completed","2024-07-08","2024-12-01","stable/final","Completed","2024-12-02","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/aes.html",null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"N/A","stable/final","Completed","N/A","N/A","stable/final","Completed","2023-10-10","stable/final","Completed","N/A","N/A","stable/final","Completed","2023-10-10","stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas",null,null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable","2025-06-02","Indicative","Not started",null,null,null,null,"2025-06-02","Indicative","Not started","www.customs.gov.mt","Due to the small amount of movements that Maltese EOs have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a GUI where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.",null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"2021-06-22","Stable/Final","Completed","2022-09-20","2023-12-01","Stable/Final","Completed","2023-05-08","Stable/Final","Completed","2023-05-08","2023-11-30","Stable/Final","Completed","2023-12-01","Stable/Final","Completed","https://www.nhdouane.nl/","CCE and the interface between NCTS P5 and AES have not been completed yet",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2021-05-15","Stable/Final","Completed","2023-01-16","2024-03-15","Stable/Final","Completed","2024-10-31","Stable/Final","Completed","N/A","N/A","Indicative","Not applicable","2024-10-31","Stable/Final","Completed","https://puesc.gov.pl/en/uslugi/eksport",null,null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","aes.ais.projekt.ias.350000@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"2023-02-22","Stable/Final","Completed","2023-04-01","2025-05-01","Indicative","In progress","2025-05-03","Indicative","Not started",null,null,null,null,"2025-05-06","Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Sistema_exportacao_e_saida/Sistema_Automatico_Exportacao/Paginas/default.aspx","Test environment available to EOs. \nDeployment of core and non core funcionalities in the same date.",null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"2023-01-06","Stable/Final","Completed","2023-05-15","2023-11-30","Stable/Final","Completed","2023-05-15","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-03-16","Stable/Final","Completed","https://www.customs.ro/e-customs/aes","AES system is fully operational ",null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Customs procedures department","ro_ecshd@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"2022-12-15","Stable/Final","Completed","2024-01-24","2024-12-02","Stable/Final","Completed","2024-10-01","Stable/Final","Completed","2024-10-01","2024-12-02","Stable/Final","Completed","2024-12-02","Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/exportinggoods.4.422c8052175b1d82769598d.html"," According to our plan we will have a phased implementation and we will deploy EIDR the 1 October 2025 and the re export notification and exit summary declaration at the end of 2025. ",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Control Department","projekt.export@tullverket.se",46771520520]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"2020-12-18","Stable/Final","Completed","2022-05-03","2023-05-23","Stable/Final","Completed","2023-05-24","Stable/Final","Completed","2023-05-24","2023-05-24","Stable/Final","Completed","2023-05-24","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c7148",null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"2023-02-03","stable/final","Completed","2023-10-25","2024-10-13","Stable/Final","Completed","2024-11-01","Stable/Final","Completed","2024-11-01","2024-11-01","Stable/Final","Completed","2024-11-01","Stable/Final","Completed","https://www.financnasprava.sk/sk/elektronicke-sluzby/elektronicka-komunikacia/elektr-komunikacia-clo-emcs/projekty-cku/projekt-aes",null,"Request for derogation sent on 2nd of October 2023 ",{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]

{"sheet":"ICS2-R3","index":24,"n_rows":113,"n_cols":28,"rows_kept":113,"cut":false,"hidden":false,"merged":[[109,25,112,25],[109,27,112,27],[109,18,112,18],[109,19,112,19],[109,23,112,23],[109,24,112,24],[105,25,108,25],[105,27,108,27],[105,18,108,18],[105,19,108,19],[105,23,108,23],[105,24,108,24],[105,26,108,26],[109,26,112,26],[89,9,92,9],[89,11,92,11],[89,12,92,12],[85,15,88,15],[109,15,112,15],[73,12,76,12],[73,11,76,11],[101,19,104,19],[101,18,104,18],[101,9,104,9],[93,15,96,15],[93,16,96,16],[101,12,104,12],[101,11,104,11],[101,16,104,16],[77,11,80,11],[77,9,80,9],[69,3,72,3],[73,3,76,3],[105,3,108,3],[109,3,112,3],[81,3,84,3],[85,3,88,3],[89,3,92,3],[89,5,92,5],[81,4,84,4],[93,3,96,3],[101,3,104,3],[101,4,104,4],[101,5,104,5],[85,4,88,4],[85,5,88,5],[77,8,80,8],[77,16,80,16],[77,15,80,15],[81,8,84,8],[81,9,84,9],[109,1,112,1],[109,4,112,4],[109,5,112,5],[109,8,112,8],[109,9,112,9],[109,11,112,11],[109,12,112,12],[105,15,108,15],[105,16,108,16],[105,1,108,1],[105,4,108,4],[105,5,108,5],[105,8,108,8],[105,9,108,9],[105,11,108,11],[105,12,108,12],[101,15,104,15],[109,16,112,16],[85,1,88,1],[101,23,104,23],[101,24,104,24],[97,25,100,25],[97,27,100,27],[101,1,104,1],[97,15,100,15],[97,16,100,16],[97,18,100,18],[97,19,100,19],[97,23,100,23],[97,24,100,24],[101,25,104,25],[101,27,104,27],[97,3,100,3],[97,1,100,1],[97,4,100,4],[97,5,100,5],[97,8,100,8],[97,9,100,9],[97,11,100,11],[97,12,100,12],[101,8,104,8],[101,26,104,26],[93,25,96,25],[93,27,96,27],[93,18,96,18],[93,19,96,19],[93,23,96,23],[93,24,96,24],[89,1,92,1],[89,4,92,4],[93,1,96,1],[93,4,96,4],[93,5,96,5],[93,8,96,8],[93,9,96,9],[93,11,96,11],[93,12,96,12],[89,15,92,15],[89,16,92,16],[89,25,92,25],[89,8,92,8],[89,27,92,27],[89,18,92,18],[89,19,92,19],[89,23,92,23],[89,24,92,24],[81,27,84,27],[81,18,84,18],[81,19,84,19],[81,23,84,23],[81,24,84,24],[85,25,88,25],[85,27,88,27],[85,18,88,18],[85,19,88,19],[85,23,88,23],[85,24,88,24],[81,25,84,25],[85,8,88,8],[85,9,88,9],[85,11,88,11],[85,12,88,12],[81,15,84,15],[81,16,84,16],[81,1,84,1],[81,5,84,5],[81,11,84,11],[81,12,84,12],[85,16,88,16],[73,25,76,25],[73,27,76,27],[77,1,80,1],[73,15,76,15],[73,16,76,16],[73,18,76,18],[73,19,76,19],[73,23,76,23],[73,24,76,24],[77,25,80,25],[77,27,80,27],[77,23,80,23],[77,24,80,24],[73,1,76,1],[73,4,76,4],[73,5,76,5],[73,8,76,8],[73,9,76,9],[77,3,80,3],[77,4,80,4],[77,5,80,5],[77,12,80,12],[77,19,80,19],[77,18,80,18],[65,24,68,24],[65,25,68,25],[65,27,68,27],[69,1,72,1],[69,4,72,4],[69,5,72,5],[69,8,72,8],[69,9,72,9],[65,11,68,11],[65,12,68,12],[65,15,68,15],[65,16,68,16],[65,18,68,18],[65,19,68,19],[69,23,72,23],[69,24,72,24],[69,25,72,25],[69,27,72,27],[69,18,72,18],[65,1,68,1],[65,5,68,5],[69,15,72,15],[65,23,68,23],[65,8,68,8],[65,9,68,9],[61,11,64,11],[61,12,64,12],[61,15,64,15],[61,16,64,16],[61,1,64,1],[61,4,64,4],[61,19,64,19],[61,3,64,3],[65,3,68,3],[57,27,60,27],[61,5,64,5],[61,8,64,8],[61,9,64,9],[57,11,60,11],[57,12,60,12],[57,15,60,15],[57,16,60,16],[57,18,60,18],[57,19,60,19],[61,23,64,23],[61,24,64,24],[61,25,64,25],[61,27,64,27],[61,18,64,18],[57,23,60,23],[57,5,60,5],[57,8,60,8],[57,9,60,9],[57,26,60,26],[61,26,64,26],[53,27,56,27],[53,18,56,18],[53,19,56,19],[53,1,56,1],[53,4,56,4],[53,5,56,5],[53,8,56,8],[53,9,56,9],[53,3,56,3],[53,11,56,11],[53,12,56,12],[53,15,56,15],[53,16,56,16],[53,26,56,26],[57,1,60,1],[57,4,60,4],[45,23,48,23],[45,24,48,24],[45,25,48,25],[45,18,48,18],[45,19,48,19],[53,23,56,23],[53,24,56,24],[53,25,56,25],[45,11,48,11],[45,12,48,12],[45,15,48,15],[57,24,60,24],[57,25,60,25],[49,3,52,3],[45,3,48,3],[57,3,60,3],[49,23,52,23],[49,24,52,24],[49,25,52,25],[49,18,52,18],[49,1,52,1],[49,4,52,4],[37,23,40,23],[37,24,40,24],[37,25,40,25],[37,27,40,27],[41,23,44,23],[41,24,44,24],[41,25,44,25],[41,27,44,27],[49,27,52,27],[45,27,48,27],[37,26,40,26],[41,26,44,26],[45,26,48,26],[49,26,52,26],[41,1,44,1],[41,4,44,4],[41,5,44,5],[41,8,44,8],[41,9,44,9],[45,1,48,1],[45,4,48,4],[45,5,48,5],[45,8,48,8],[45,9,48,9],[41,3,44,3],[49,5,52,5],[49,8,52,8],[49,9,52,9],[33,11,36,11],[33,12,36,12],[33,15,36,15],[33,16,36,16],[37,1,40,1],[37,4,40,4],[37,5,40,5],[37,8,40,8],[37,9,40,9],[33,3,36,3],[37,3,40,3],[33,1,36,1],[33,4,36,4],[33,5,36,5],[33,8,36,8],[33,9,36,9],[37,12,40,12],[37,11,40,11],[41,11,44,11],[41,12,44,12],[41,15,44,15],[29,11,32,11],[29,12,32,12],[29,15,32,15],[29,16,32,16],[29,1,32,1],[29,3,32,3],[29,4,32,4],[29,5,32,5],[29,8,32,8],[29,9,32,9],[33,24,36,24],[25,24,28,24],[25,25,28,25],[25,27,28,27],[25,9,28,9],[25,11,28,11],[25,12,28,12],[25,15,28,15],[25,16,28,16],[25,18,28,18],[29,23,32,23],[29,24,32,24],[29,25,32,25],[29,27,32,27],[29,18,32,18],[29,19,32,19],[33,23,36,23],[33,25,36,25],[33,27,36,27],[33,18,36,18],[33,19,36,19],[25,26,28,26],[29,26,32,26],[33,26,36,26],[21,23,24,23],[21,24,24,24],[21,25,24,25],[21,27,24,27],[25,1,28,1],[25,3,28,3],[25,4,28,4],[25,5,28,5],[25,8,28,8],[21,11,24,11],[21,12,24,12],[21,15,24,15],[21,16,24,16],[21,18,24,18],[21,19,24,19],[21,1,24,1],[21,3,24,3],[21,4,24,4],[21,5,24,5],[21,8,24,8],[21,9,24,9],[25,19,28,19],[25,23,28,23],[21,26,24,26],[17,23,20,23],[17,24,20,24],[17,25,20,25],[17,27,20,27],[17,9,20,9],[17,11,20,11],[17,12,20,12],[17,15,20,15],[17,16,20,16],[17,18,20,18],[17,26,20,26],[13,18,16,18],[13,19,16,19],[17,1,20,1],[17,3,20,3],[17,4,20,4],[17,5,20,5],[17,8,20,8],[13,11,16,11],[13,12,16,12],[13,15,16,15],[13,16,16,16],[17,19,20,19],[13,4,16,4],[13,5,16,5],[13,8,16,8],[13,9,16,9],[9,12,12,12],[9,15,12,15],[9,16,12,16],[9,1,12,1],[9,3,12,3],[9,4,12,4],[9,5,12,5],[9,8,12,8],[9,9,12,9],[9,11,12,11],[5,1,8,1],[9,24,12,24],[9,18,12,18],[9,19,12,19],[9,23,12,23],[41,19,44,19],[65,4,68,4],[5,19,8,19],[5,18,8,18],[37,19,40,19],[37,18,40,18],[37,16,40,16],[37,15,40,15],[5,12,8,12],[5,11,8,11],[5,9,8,9],[5,8,8,8],[5,3,8,3],[5,4,8,4],[5,5,8,5],[5,16,8,16],[5,15,8,15],[13,1,16,1],[13,3,16,3],[2,25,2,27],[3,3,3,5],[3,6,3,9],[3,10,3,12],[3,13,3,16],[3,17,3,19],[2,3,2,5],[2,6,2,9],[2,10,2,12],[2,13,2,16],[2,17,2,19],[2,23,2,24],[5,25,8,25],[5,27,8,27],[9,25,12,25],[9,27,12,27],[13,23,16,23],[13,24,16,24],[13,25,16,25],[5,23,8,23],[5,24,8,24],[13,27,16,27],[5,26,8,26],[9,26,12,26],[13,26,16,26],[41,16,44,16],[41,18,44,18],[45,16,48,16],[69,19,72,19],[69,16,72,16],[69,11,72,11],[69,12,72,12],[49,19,52,19],[49,11,52,11],[49,12,52,12],[49,15,52,15],[49,16,52,16],[65,26,68,26],[69,26,72,26],[73,26,76,26],[77,26,80,26],[81,26,84,26],[85,26,88,26],[89,26,92,26],[93,26,96,26],[97,26,100,26]]}
[]
[]
[null,null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,"UCC Import Control System 2 – Release 3",null,"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},"Single operations","2022-04-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Not applicable","2024-06-03","Indicative","Completed","N/A","N/A","Stable/Final","Not applicable",null,"Stable/Final","In progress","https://www.bmf.gv.at/themen/zoll/ACCS/ics2-import-control-system.html","In Austria there is only air traffic. For other modes of transport Austria acts only as an involved member state (IMS)","None",{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/15","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51446"]
[null,null,"Step 1","open",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-12-04"]
[null,null,"Step 2","open",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-04-01"]
[null,null,"Step 3","open",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-09-01"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},"Single operations",null,null,null,null,null,null,null,"2024-06-03","Stable/Final","Completed","2024-06-03","2025-09-01","Stable/Final","In progress","2025-09-01","Stable/Final","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,null,"Step 1"]
[null,null,"Step 2"]
[null,null,"Step 3"]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},"Single deployment","2022-03-28","Stable/Final","Completed","2024-02-19","2024-02-20","Stable/Final","Completed","2024-06-03","Stable/Final","Completed",null,null,null,null,"2024-06-03","Stable/Final","Completed","https://ep.customs.bg/eportal/","COMMISSION IMPLEMENTING DECISION (EU) o2023/2879 f 15.12.2023 establishing the Work Programme relating to the development and deployment for the electronic systems provided for in the Union Customs Code",null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,null,"Step 1","2022-03-28"]
[null,null,"Step 2","2022-03-28"]
[null,null,"Step 3","2022-03-28"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},"Single operations","2023-09-15","Stable/Final","Completed","N/A","N/A","Stable/Final","In progress","N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","In progress","N/A","Stable/Final","In progress",null,null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,null,"Step 1","2023-09-15",null,null,"2024-05-06","2024-11-30",null,null,"2024-06-03",null,null,"2024-06-03","2024-12-04",null,null,"2024-12-04"]
[null,null,"Step 2","2023-09-15",null,null,"2024-05-06","2025-03-26",null,null,"2024-06-03",null,null,"2024-06-03","2025-04-01",null,null,"2025-04-01"]
[null,null,"Step 3","2023-09-15",null,null,"N/A",null,null,null,"N/A",null,null,"N/A",null,null,null,"N/A"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},"Single operations","N/A","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-06-01","Stable/Final","Completed",null,null,null,null,"2024-06-01","Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},"Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
[null,null,"Step 1","2023-06-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Lenka Kubíková",null,"420/261332631"]
[null,null,"Step 2","2023-06-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Lenka Kubíková",null,"420/261332631"]
[null,null,"Step 3","2023-06-30",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Lenka Kubíková",null,"420/261332631"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},"Single operations",null,null,null,null,null,null,null,"2024-06-03","Stable/Final","In progress",null,null,null,null,null,null,null,null,"The national IT-System ATLAS is conform wiht ICS2-R3 will require no change compared to ICS2-Release 2. All Milestones relating to EO will be published by EU-COM. The Technical Specs for the external communication via STI-ICS2 will be provided by EU-COM. CT between EO and EU-COM will be scheduled individually in co-ordinaton with EU-MS concerned. ",null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,null,"Step 1",null,null,null,null,null,null,null,"2024-06-03",null,null,null,null,null,null,"2024-12-04",null,null,null,"The date of Deployment and End of Transition Period are determined by the UCC-Work Programme and indicated for completeness."]
[null,null,"Step 2",null,null,null,null,null,null,null,"2024-12-04",null,null,null,null,null,null,"2025-04-01",null,null,null,"The date of Deployment and End of Transition Period are determined by the UCC-Work Programme and indicated for completeness."]
[null,null,"Step 3",null,null,null,null,null,null,null,"2025-04-01",null,null,null,null,null,null,"2025-09-01",null,null,null,"The date of Deployment and End of Transition Period are determined by the UCC-Work Programme and indicated for completeness."]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},"Single operations","2023-12-21","Stable/Final","Completed",null,null,"Stable/Final","In progress","2024-05-25","Stable/Final","Completed",null,null,"Stable/Final","In progress","2025-09-01","Indicative","In progress","www.toldst.dk ",null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"},"Business Development Unit","forretning@toldst.dk"]
[null,null,"Step 1",null,null,null,"2023-12-22","2024-12-04",null,null,null,null,null,"2024-06-03","2024-12-04"]
[null,null,"Step 2",null,null,null,"2024-12-04","2025-04-01",null,null,null,null,null,"2024-12-04","2025-04-01"]
[null,null,"Step 3",null,null,null,"2024-04-01","2025-09-01",null,null,null,null,null,"2025-04-01","2025-09-01"]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},"Single operations","2023-06-01","Stable/Final","Completed",null,null,"Stable/Final","In progress",null,"Stable/Final","Completed",null,null,"Stable/Final","In progress",null,"Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo","We have determined that NCTS phase 6 is closely linked to project ICS2 Release 3 and hence the project deadlines should be amended accordingly.",null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","ICS2-NPM-EE@emta.ee","00 372 8800 814"]
[null,null,"Step 1","2023-06-01",null,null,"2023-11-01","2025-04-01",null,null,"2024-06-03",null,null,"2024-06-03","2025-04-01",null,null,"2025-04-01",null,null,"https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo"]
[null,null,"Step 2","2023-06-01",null,null,"2024-01-02","2025-04-01",null,null,"2024-06-03",null,null,"2024-12-04","2025-04-01",null,null,"2025-04-01",null,null,"https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo"]
[null,null,"Step 3","2023-06-01",null,null,"2024-12-04","2025-09-01",null,null,"2024-06-03",null,null,"2025-04-01","2025-09-01",null,null,"2025-09-01",null,null,"https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele#nes-uldinfo"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"Single operations","2022-03-01","Stable/Final","Completed",null,null,"Stable/Final","In progress",null,"Stable/Final","In progress",null,null,"Stable/Final","In progress",null,"Stable/Final","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/entrada-salida-mercancias/declaraciones-sumarias-ens.html","ICS2 R3 Deployment window has been increased",null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"Helpdesk ICS","ics.helpdesk@correo.aeat.es"]
[null,null,"Step 1","2022-03-01",null,null,"2023-12-01","2024-12-04",null,null,"2024-06-03",null,null,"2024-06-03","2024-12-04",null,null,"2024-12-04"]
[null,null,"Step 2","2022-03-01",null,null,"2023-12-01","2025-04-01",null,null,"2024-12-04",null,null,"2024-12-04","2025-04-01",null,null,"2025-04-01"]
[null,null,"Step 3","2022-03-01",null,null,"2023-12-01","2025-09-01",null,null,"2025-04-01",null,null,"2025-04-01","2025-09-01",null,null,"2025-09-01"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},"Single operations","2022-03-31","Stable/Final","Completed",null,null,"Stable/Final","In progress","2024-06-30","Stable/Final","Completed",null,null,"Stable/Final","In progress",null,"Stable/Final","In progress","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,null,"Step 1","2022-03-31",null,null,"2024-06-30","2024-12-31",null,null,"N/A",null,null,"2024-06-03","2025-04-01",null,null,"2025-04-01",null,null,null,null,null,null,null,"Leila Lappalainen"]
[null,null,"Step 2","2022-03-31",null,null,"2024-06-30","2025-03-31",null,null,"N/A",null,null,"2024-12-04","2025-04-01",null,null,"2025-04-01",null,null,null,null,null,null,null,"Leila Lappalainen"]
[null,null,"Step 3","2022-03-31",null,null,"2024-06-30","2025-09-30",null,null,"N/A",null,null,"2025-04-01","2025-09-01",null,null,"2025-09-01",null,null,null,null,null,null,null,"Leila Lappalainen"]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},"Single operations","N/A","Stable/Final","Not applicable",null,null,"Indicative","Not applicable",null,"Stable/Final","In progress",null,null,"Indicative","In progress",null,"Indicative","In progress","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report",null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office JCF 2 DGDDI","Veille-ics-dg@douane.finances.gouv.fr"]
[null,null,"Step 1","2023-03-31",null,null,"N/A","N/A",null,null,"2024-06-03",null,null,"2024-06-03","2025-04-01",null,null,"2025-04-01",null,null,null,null,"Updated planning",null,null,"Office JCF 2 DGDDI"]
[null,null,"Step 2","2023-03-31",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Office JCF 2 DGDDI"]
[null,null,"Step 3","2023-03-31",null,null,"N/A","N/A",null,null,"2025-04-01",null,null,"2025-04-01","2025-09-30",null,null,"2025-09-30",null,null,null,null,"Updated planning",null,null,"Office JCF 2 DGDDI"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},"Single operations","2023-10-01","Stable/Final","Completed","2023-09-30","2024-12-31","Stable/Final","Completed","2024-06-14","Stable/Final","Completed","2024-06-03","2024-12-04","Stable/Final","Completed","2024-06-14","Stable/Final","Completed","https://www.aade.gr/customs",null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"ICS_NPM@AADE.GR"]
[null,null,"Step 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Mr Katagis",null,"0030210 6987434"]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Mr Katagis",null,"0030210 6987434"]
[null,null,"Step 3",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Mr Katagis",null,"0030210 6987434"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},"Single operations","2023-05-01","Stable/Final","Completed","2024-06-03","2025-09-01","Stable/Final","In progress","2024-06-30","Stable/Final","In progress","2024-06-30","2025-09-01","Stable/Final","In progress","2025-09-01","Indicative","In progress","https://carina.gov.hr","ICS2 R3 starts 03.06.2024. for maritime. The roll-out of Release 3 will occur in the following way: first maritime carriers will be phasing in (step 1  03. 06. 2024 for MS), then the house level filers (step 2), and then the road and rail carriers (step 3 from 01. 04. 2025 for MS). ICS2 R3 steps 1, 2 are nationally implemented and in full application. Step 3 will be implemented from 01.04.2025. Economic operators will use the transition period for step 2 until 01.04.2025. (maritime house level filers). Economic operators will use the transition period for step 3 until 01.09.2025.","Derogation for ICS2 R3 (steps 1,2,3)Derogation for ICS2 R3 (steps 1,2,3 in line COMMISSION IMPLEMENTING DECISION (EU) 2023/2879)",{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","ICS2@carina.hr",38516102333]
[null,null,"Step 1","2023-05-01",null,null,"2024-06-03","2024-12-04",null,null,"2024-06-03",null,null,"2024-06-03","2024-12-04",null,null,"2024-12-04",null,null,"https://carina.gov.hr","Completed (MS and EOs)",null,null,null,"Albert Đurđević",null,38516211536]
[null,null,"Step 2","2023-05-01",null,null,"2024-06-03","2025-04-01",null,null,"2024-06-03",null,null,"2024-06-03","2025-04-01",null,null,"2025-04-01",null,null,"https://carina.gov.hr","In progress (MS completed, EO in progres -house level filers) ",null,null,null,"Albert Đurđević",null,38516211536]
[null,null,"Step 3","2023-05-01",null,null,"2025-01-28","2025-09-01",null,null,"2025-04-01",null,null,"2024-06-03","2025-09-01",null,null,"2025-09-01",null,null,"https://carina.gov.hr","Not started (MS start on 01.04.2025, Eos DW - 01.09.2025)",null,null,null,"Albert Đurđević",null,38516211536]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},"Single operations","2023-11-25","Stable/Final","Completed",null,null,null,null,"2023-03-01","Stable/Final","Completed",null,null,null,null,null,"Indicative","Not started",null,"No development task in connection with the R3 phase. The deployment date provided corresponds to the R2 phase.",null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,null,"Step 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-12-04",null,null,null,"The system is already available.",null,null,null,"Jenes Barbara"]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-04-01",null,null,null,"The carriers concerned with R3 (inland waterways, road and rail carriers) haven’t started to use the system yet.",null,null,null,"Jenes Barbara"]
[null,null,"Step 3",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-09-01",null,null,null,null,null,null,null,"Jenes Barbara"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},"Single operations","2022-01-28","Stable/Final","Completed",null,null,"Stable/Final","In progress",null,"Stable/Final","In progress",null,null,"Stable/Final","In progress",null,"Stable/Final","In progress","www.revenue.ie","Link to EU Specs from Revenue Website",null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"},"eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
[null,null,"Step 1",null,null,null,"2023-12-01","2024-11-30",null,null,"2024-06-03",null,null,"2024-06-03","2024-12-04",null,null,"2024-12-04"]
[null,null,"Step 2",null,null,null,"2023-12-01","2025-03-31",null,null,"2024-12-04",null,null,"2024-12-04","2025-04-01",null,null,"2025-04-01",null,null,null,"RoRo traffic both Accompanied and Un-accompanied will now be in a deployment window of Apr-Sept 2025"]
[null,null,"Step 3",null,null,null,"2023-12-01","2025-07-31",null,null,"2025-04-01",null,null,"2025-04-01","2025-09-01",null,null,"2025-09-01",null,null,null,"RoRo traffic both Accompanied and Un-accompanied will now be in a deployment window of Apr-Sept 2025"]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},"Single operations","2024-03-27","Stable/Final","Completed",null,null,"Stable/Final","Completed",null,"Stable/Final","Completed",null,null,null,"Not applicable",null,null,"Not applicable","https://www.adm.gov.it/portale/-/ics2","Technical Specs provided by EU",null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,null,"Step 1",null,null,null,"2024-05-03","2024-05-31",null,null,"2024-06-03"]
[null,null,"Step 2",null,null,null,"2024-05-03","2024-05-31",null,null,"2024-06-03"]
[null,null,"Step 3",null,null,null,"N/A","N/A",null,null,"N/A",null,null,"N/A","N/A",null,null,"N/A"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},"Single operations","2023-07-30","Stable/Final","Completed",null,null,"Stable/Final","In progress",null,"Stable/Final","Completed",null,null,"Stable/Final","In progress",null,"Stable/Final","In progress",null,null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"},"Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_ICS2_R1R2R3-LT@lrmuitine.lt","370 5 236 2302"]
[null,null,"Step 1",null,null,null,"2023-10-15","2024-11-04",null,null,"2024-06-01",null,null,"2024-03-01","2024-11-04",null,null,"2024-12-04",null,null,null,"Web Address for EO is Central ICS2 system ",null,null,null,"Vitalis Vareikis",null,37052666144]
[null,null,"Step 2",null,null,null,"2023-10-15","2025-03-01",null,null,"2024-06-01",null,null,"2024-03-01","2025-03-01",null,null,"2025-04-01",null,null,null,"Web Address for EO is Central ICS2 system ",null,null,null,"Vitalis Vareikis",null,37052666144]
[null,null,"Step 3",null,null,null,"2023-10-15","2025-08-01",null,null,"2024-06-01",null,null,"2024-03-01","2025-08-01",null,null,"2025-09-01",null,null,null,"Web Address for EO is Central ICS2 system ",null,null,null,"Vitalis Vareikis",null,37052666144]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},"Single operations","2024-02-01","Stable/Final","Completed","2024-03-01","2024-12-31","Stable/Final","Completed","2024-07-01","Stable/Final","Completed","N/A","N/A","Stable/Final","Completed","2024-07-01","Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/ics2.html","The impact of ICS2R3 very limited for NA-LU with minor adaptions since NA-LU is involved MS.",null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,null,"Step 1",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Not applicable since no land nor sea borders with 3rd country "]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Not applicable since no land nor sea borders with 3rd country "]
[null,null,"Step 3",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Not applicable since no land nor sea borders with 3rd country "]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},"Single operations","2022-01-10","Stable/Final","Completed",null,null,"Indicative","Not started","2023-03-01","Stable/Final","Completed",null,null,"Indicative","Not started",null,"Indicative","Not started","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas ",null,null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"},"eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
[null,null,"Step 1",null,null,null,"N/A","N/A",null,null,null,null,null,"2024-07-03","2024-12-04",null,null,"2024-12-04"]
[null,null,"Step 2",null,null,null,"N/A","N/A",null,null,null,null,null,"2024-12-04","2025-04-01",null,null,"2025-04-01"]
[null,null,"Step 3",null,null,null,"2025-03-03","2025-03-28",null,null,null,null,null,"2025-04-01","2025-09-01",null,null,"2025-09-01"]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},"Single operations","N/A","Indicative","Not applicable","N/A","N/A","Indicative","Not applicable",null,"Indicative","In progress",null,null,null,null,null,"Stable/Final","In progress","https://customs.gov.mt/electronic-systems/import-control-system-2",null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,null,"Step 1","N/A",null,null,null,null,null,null,"2024-07-15",null,null,null,null,null,null,"2024-12-04"]
[null,null,"Step 2","N/A",null,null,null,null,null,null,"2024-07-15",null,null,null,null,null,null,"2025-04-01"]
[null,null,"Step 3","N/A",null,null,null,null,null,null,"2024-07-15",null,null,null,null,null,null,"2025-09-01"]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},"Single operations","2023-09-01","Stable/Final","Completed","2024-03-01","2024-05-24","Stable/Final","Completed","2024-05-27","Stable/Final","Completed",null,null,"Indicative","In progress",null,"Indicative","In progress","https://www.nhdouane.nl/","Technical specs are NA PN TS maritime",null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,null,"Step 1","2023-09-01",null,null,null,null,null,null,null,null,null,"2024-06-03","2024-12-04",null,null,"2024-12-04",null,null,null,null,null,null,null,"National Helpdesk Dutch Customs",null,"(+31)(0)88 156 6655"]
[null,null,"Step 2","2023-09-01",null,null,null,null,null,null,null,null,null,"2024-12-04","2025-04-01",null,null,"2025-04-01",null,null,null,null,null,null,null,"National Helpdesk Dutch Customs",null,"(+31)(0)88 156 6655"]
[null,null,"Step 3","2023-09-01",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"National Helpdesk Dutch Customs",null,"(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"Single operations","2022-09-19","Stable/Final","Completed","2023-12-11","2025-08-31","Stable/Final","In progress",null,"Stable/Final","In progress","N/A","N/A",null,"Not applicable",null,"Stable/Final","Not started","https://puesc.gov.pl/en/puesc",null,null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","helpdesk.satos@mf.gov.pl","48 (22) 694 50 05"]
[null,null,"Step 1","not scheduled yet",null,null,null,null,null,null,"2024-06-03",null,null,null,null,null,null,"2024-12-04",null,null,null,null,null,null,null,"Beata Utylska",null,48126290201]
[null,null,"Step 2","not scheduled yet",null,null,null,null,null,null,"2024-12-04",null,null,null,null,null,null,"2025-04-01",null,null,null,null,null,null,null,"Beata Utylska",null,48126290201]
[null,null,"Step 3","not scheduled yet",null,null,null,null,null,null,"2025-04-01",null,null,null,null,null,null,"2025-09-01",null,null,null,null,null,null,null,"Beata Utylska",null,48126290201]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},"Single operations","2023-09-01","Stable/Final","Completed","2023-12-15","2024-05-01","Stable/Final","Completed","2024-06-03","Stable/Final","Completed",null,null,null,null,"2024-06-03","Stable/Final","Completed","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/ICS2/Paginas/default.aspx","There is no National Technical Specifications to the external interface.\nNot expetect any delay.",null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,null,"Step 1","2023-09-01"]
[null,null,"Step 2","2023-09-01"]
[null,null,"Step 3","2023-09-01"]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},"Single operations","2022-11-07","Stable/Final","Completed","2024-12-16","2025-09-01","Indicative","In progress","2024-12-16","Stable/Final","Completed",null,null,"Indicative","In progress","2025-09-01","Indicative","Not started","www.customs.ro",null,null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Security and Safety Risk Analysis Service","ro.helpdesk.ics2@customs.ro",40216373051]
[null,null,"Step 1",null,null,null,null,null,null,null,null,null,null,"2024-12-16","2025-04-01",null,null,null,null,null,null,null,null,null,null,"Andrei-Cristian PÂRVU",null,40723220158]
[null,null,"Step 2",null,null,null,null,null,null,null,null,null,null,"2024-12-16","2025-04-01",null,null,null,null,null,null,null,null,null,null,"Andrei-Cristian PÂRVU",null,40723220158]
[null,null,"Step 3",null,null,null,null,null,null,null,null,null,null,"2025-04-01","2025-09-01",null,null,null,null,null,null,null,null,null,null,"Andrei-Cristian PÂRVU",null,40723220158]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},"Single operations","N/A",null,"Not applicable",null,null,null,"Not applicable",null,"Indicative","In progress",null,null,"Indicative","In progress",null,"Indicative","In progress","https://www.tullverket.se/en/startpage/business/declarationaccordingtotheucc/entrysummarydeclaration.4.422c8052175b1d8276959dc.html"," Dates for technical spec and CT are not applicable since the central ICS/STI will be used.",null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},"Intelligence Department","underrattelseavd.npm.ics2@tullverket.se",46771520520]
[null,null,"Step 1",null,null,null,"N/A","N/A",null,null,"2024-06-03",null,null,"2024-06-03","2024-12-04",null,null,"2024-12-04"]
[null,null,"Step 2",null,null,null,"N/A","N/A",null,null,"2024-12-04",null,null,"2024-12-04","2025-04-01",null,null,"2025-04-01"]
[null,null,"Step 3",null,null,null,"N/A","N/A",null,null,"2025-04-01",null,null,"2025-04-01","2025-09-01",null,null,"2025-09-01"]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},"Single operations","2023-10-01","Stable/Final","Completed","N/A",null,"Stable/Final","Completed","2024-06-02","Stable/Final","Completed","2024-06-02","2024-06-02","Stable/Final","Completed","2024-06-03","Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/#c4719","A single deployment approach",null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OPU","sd.fu@gov.si","01 478 3800"]
[null,null,"Step 1",null,null,null,"N/A",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"A single deployment approach"]
[null,null,"Step 2",null,null,null,"N/A",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"A single deployment approach"]
[null,null,"Step 3",null,null,null,"N/A",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"A single deployment approach"]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},"Single operations","2023-01-01","Stable/Final","Completed",null,null,"Indicative","Not started","2024-06-03","Indicative","Completed",null,null,"Stable/Final","In progress",null,"Indicative","In progress","https://www.financnasprava.sk/sk/elektronicke-sluzby/elektronicka-komunikacia/elektr-komunikacia-clo-emcs/podavanie-cv-dovoz-vyvoz/elektronicke-colne-konanie",null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"},"Customs division (IL)","cis@financnasprava.sk","00421-905-418188"]
[null,null,"Step 1",null,null,null,"N/A","N/A",null,null,null,null,null,"2024-06-03","2024-12-04",null,null,"2024-12-04",null,null,null,null,null,null,null,"Igor Lalík"]
[null,null,"Step 2",null,null,null,"N/A","N/A",null,null,null,null,null,"2024-12-04","2025-04-01",null,null,"2025-04-01",null,null,null,null,null,null,null,"Igor Lalík"]
[null,null,"Step 3",null,null,null,"2025-01-01","2025-03-31",null,null,null,null,null,"2025-04-01","2025-09-01",null,null,"2025-09-01",null,null,null,null,null,null,null,"Igor Lalík"]

{"sheet":"PoUS-P1","index":25,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A17","v":"UCC Proof of Union Status (PoUS) - Phase 1"},"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/16","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51447"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},null,"NPP.MASP@cs.mfcr.cz"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"}]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","PoUS-NPM-EE@emta.ee","    00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2023-01-15","Stable/Final","Completed","2023-04-12","2024-02-28","Stable/Final","Completed","2024-01-15","Stable/Final","Completed","2024-01-15","2024-02-28","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","https://sede.agenciatributaria.gob.es/Sede/aduanas/estatuto-aduanero-mercancia.html?faqId=e91cc7756ab39710VgnVCM100000dc381e0aRCRD",null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"POuS Information","POUS.info@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-transit@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"NCTS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-01-03","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","pous@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"}]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"}]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"}]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"2023-09-15","Stable/Final","Completed","2023-09-16","2024-02-29","Stable/Final","Completed","2024-03-01","Stable/Final","Completed","N/A","N/A",null,"Not applicable","2024-09-15","Stable/Final","Completed","https://puesc.gov.pl/en/puesc",null,null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","Aes.ais.projekt@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Tranzit office","tranzitcentraloffice@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},null,"ecustoms@tullverket.se"]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OCP","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},null,null,null,null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,null,"2024-03-01","Stable/Final","Completed",null,null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"}]

{"sheet":"PoUS-P2","index":26,"n_rows":32,"n_cols":27,"rows_kept":32,"cut":false,"hidden":false,"merged":[[2,24,2,26],[3,2,3,4],[3,5,3,8],[3,9,3,11],[3,12,3,15],[3,16,3,18],[2,2,2,4],[2,5,2,8],[2,9,2,11],[2,12,2,15],[2,16,2,18],[2,22,2,23]]}
[]
[]
[null,null,"Technical Specifications",null,null,"Conformance Testing",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web","Notes","Derogations","Version information and issue date",null,"Project Manager Details"]
[null,null,"The date of publication of the technical specifications for the external communication on the electronic system",null,null,"The period of conformance testing with economic operators",null,null,null,"The date of deployment of the electronic system",null,null,"Where applicable, the period during which the economic operators are allowed to carry out migration",null,null,null,"Start of Operations for all economic operators (end of transition period)",null,null,"Web address of specifications for EO's",null,"If a derogation under Art 6(4) UCC was granted, please indicate the activities carried out and the state of development in order to reach the derogation deadline."]
[null,{"$f":"formats!A18","v":"UCC Proof of Union Status (PoUS) - Phase 2"},"Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Start Date","End Date","Status","Progress","Date","Status","Progress","Web address","Note/Comment","Note/Comment","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
[null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W6","v":15},{"$f":"'AN - Air'!X6","v":"2025-02-12"},"Federal ministry of finance, division I/17","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51448"]
[null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W7","v":3.2},{"$f":"'AN - Air'!X7","v":"2025-01-30"}]
[null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W8","v":10.3},{"$f":"'AN - Air'!X8","v":"2025-02-05"},"National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
[null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W9","v":8},{"$f":"'AN - Air'!X9","v":"2025-02-10"},"1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
[null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W10","v":1.7},{"$f":"'AN - Air'!X10","v":"2025-02-04"},null,"NPP.MASP@cs.mfcr.cz"]
[null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W11","v":7.01},{"$f":"'AN - Air'!X11","v":"2025-01-31"},"Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
[null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W12","v":1},{"$f":"'AN - Air'!X12","v":"2025-02-14"}]
[null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W13","v":20},{"$f":"'AN - Air'!X13","v":"2025-02-10"},"Customs Manegement Department","PoUS-NPM-EE@emta.ee","    00 372 8800 814"]
[null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},"2025-02-17","Indicative","In progress","2025-05-16","2025-08-15","Indicative","Not started","2025-07-14","Indicative","Not started","2025-07-14","2025-08-15","Indicative","Not started","2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W14","v":3.2},{"$f":"'AN - Air'!X14","v":"2025-02-06"},"POuS Information","POUS.info@correo.aeat.es"]
[null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W15","v":17},{"$f":"'AN - Air'!X15","v":"2025-01-27"}]
[null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W16","v":2},{"$f":"'AN - Air'!X16","v":"2025-02-04"},"Office COMINT 1 DGDDI","dg-comint1-transit@douane.finances.gouv.fr"]
[null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W17","v":7},{"$f":"'AN - Air'!X17","v":"2024-06-28"},null,"NCTS_NPM@AADE.GR"]
[null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W18","v":9.5},{"$f":"'AN - Air'!X18","v":"2025-01-31"},"Sector for customs system","pous@carina.hr",38516102333]
[null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W19","v":1.1000000000000001},{"$f":"'AN - Air'!X19","v":"2025-01-31"},"NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
[null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W20","v":17},{"$f":"'AN - Air'!X20","v":"2025-02-07"}]
[null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W21","v":1},{"$f":"'AN - Air'!X21","v":"2025-02-12"},"Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
[null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W22","v":14},{"$f":"'AN - Air'!X22","v":"2025-01-31"}]
[null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W23","v":2},{"$f":"'AN - Air'!X23","v":"2025-01-30"},"Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
[null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W24","v":3.2},{"$f":"'AN - Air'!X24","v":"2025-01-27"}]
[null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W25","v":3.04},{"$f":"'AN - Air'!X25","v":"2025-02-10"}]
[null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W26","v":1.01},{"$f":"'AN - Air'!X26","v":"2025-02-10"},"National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
[null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},"N/A",null,"Not applicable","N/A","N/A",null,"Not applicable","2027-06-30","indicative","Not started","N/A","N/A",null,"Not applicable","2027-06-30","indicative","Not started","https://puesc.gov.pl/en/puesc","Indicative dates of deployment and operation depend on the preparation of the modified NSW in tfe framowork of EMSWe and  are out of action of Customs Administration.",null,{"$f":"'AN - Air'!W27","v":0.2},{"$f":"'AN - Air'!X27","v":"2025-02-05"},"Ministry of Finance Customs Department","Aes.ais.projekt@mf.gov.pl","48 (22) 694 50 05"]
[null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W28","v":7.5},{"$f":"'AN - Air'!X28","v":"2025-02-03"},null,"dsra@at.gov.pt",351218813890]
[null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W29","v":"3.00"},{"$f":"'AN - Air'!X29","v":"2025-02-10"},"Tranzit office","tranzitcentraloffice@customs.ro",40213155858]
[null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W30","v":24},{"$f":"'AN - Air'!X30","v":"2025-01-27"},null,"ecustoms@tullverket.se"]
[null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W31","v":18},{"$f":"'AN - Air'!X31","v":"2025-02-05"},"OCP","sd.fu@gov.si"," 01 478 3800 "]
[null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},null,null,null,null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,null,"2025-08-15","Indicative","Not started",null,null,null,{"$f":"'AN - Air'!W32","v":1.04},{"$f":"'AN - Air'!X32","v":"2025-01-27"}]

{"sheet":"Consolidation","index":27,"n_rows":597,"n_cols":47,"rows_kept":597,"cut":false,"hidden":true,"merged":[]}
["ID","Project","MSs","Derogation status","TS Date","TS Status","TS Progress","Single CT Start Date","Step 1 - CT Start Date","Step 2 - CT Start Date","Step 3 - CT Start Date","Single CT End Date","Step 1 - CT End Date","Step 2 - CT End Date","Step 3 - CT End Date","CT Status","CT Progress","Single D Date","Step 1 - D Date","Step 2 - D Date","Step 3 - D Date","D Status","D Progress","Single M Start Date","Step 1 - M Start Date","Step 2 - M Start Date","Step 3 - M Start Date","Single M End Date","Step 1 - M End Date","Step 2 - M End Date","Step 3 - M End Date","M Status","M Progress","Single O Date","Step 1 - O Date","Step 2 - O Date","Step 3 - O Date","O Status","O Progress","Web address","Notes","Derogations","Version Number","Issue Date","Project Mgr Name","e-Mail","Phone"]
["AT-Österreich:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","AT-Österreich","Granted","2021-11-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2023-07-01",null,null,null,"Stable/Final","Completed","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/2","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51433"]
["BE-Belgique/België:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","BE-Belgique/België","Granted","2021-10-12","Stable/Final","Completed","2023-03-01",null,null,null,"2023-06-30",null,null,null,"Stable/Final","Completed","2023-06-30",null,null,null,"Stable/Final","Completed","2023-06-30",null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","BG-България","Granted","2022-03-28","Stable/Final","Completed","2022-12-01",null,null,null,"2022-12-15",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-03-01",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/",null,"The Commission implementing decision granting a derogation is applying from 1.3.2023 in respect of goods entering the customs territorry of the Union by air and from 1.3.2024 in respect of goods entering the customs territorry of the Union by maritime transport or inland waterways.",10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","CY-Κύπρος","Granted","2023-05-22","Stable/Final","Completed","2023-10-01",null,null,null,"2025-03-10",null,null,null,"Stable/Final","In progress","2025-03-31",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-03-31",null,null,null,"Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,"Derogation was granted.",8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","CZ-Česká republika","Granted","2023-09-01","Stable/Final","Completed","2023-11-01",null,null,null,"2023-12-01",null,null,null,"Stable/Final","Completed","2023-12-05",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-12-05",null,null,null,"Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"This \"message\" will be covered by the transeuropean system ICS2.  All Milestones affecting EO need to be considered in line with the ICS2 planning for Release 2 and Release 3 provided by EU-COM, especially in relation to the STI. ",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","DK-Danmark","Granted","2021-09-01","Stable/Final","Completed","2023-06-15",null,null,null,"2023-11-01",null,null,null,"Stable/Final","Completed","2023-11-06",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"2023-10-31",null,null,null,"Stable/Final","Completed","2023-10-31",null,null,null,"Stable/Final","Completed","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","EE-Eesti","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2023-10-01",null,null,null,"Stable/Final","Not applicable","2023-10-01",null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele","Development according to ICS2 project plan.","A derogation request was accordingly submitted by EE on 06.07.2022.",20,"2025-02-10","Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","ES-España","Granted","2022-03-01","Stable/Final","Completed","2022-09-01",null,null,null,"2023-10-02",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","2023-10-02",null,null,null,"Stable/Final","Completed",null,null,null,3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","FI-Suomi/Finland","None","2022-06-30","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-03-31",null,null,null,"Stable/Final","Completed","2023-03-31",null,null,null,"2023-09-30",null,null,null,"Stable/Final","Completed","2023-03-31",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","FR-France","Granted","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2023-06-30",null,null,null,"Stable/Final","Completed","2023-06-30",null,null,null,"2024-06-01",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"Stable/Final","Completed","https://www.douane.gouv.fr/services-aide/edi","Proposed via ICS release 2\nProgress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report","Updated planning",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","GR-Ελλάδα","Granted","2023-09-30","Stable/Final","Completed","2023-09-30",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","https://www.aade.gr/customs","THE FUNCTIONALITY OR COMMON REPOSITORY IS USED","derogation request",7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","HR-Hrvatska","Granted","2022-04-01","Stable/Final","Completed","2023-03-01",null,null,null,"2023-07-01",null,null,null,"Stable/Final","Completed","2023-07-01",null,null,null,"Stable/Final","Completed","2023-07-01",null,null,null,"2023-10-02",null,null,null,"Stable/Final","Completed","2023-10-02",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/","EOs used DW for ICS2 R2 and R3, this was the period of inclusion in submitting AN via STI. As a rule, when an EO starts in ICS2 R2 or R3 (AIR and Maritime), he is required to submit AN via STI. DW expired.  ","Derogation for AN ",9,"2025-01-31","Sector for customs system","ICS2@carina.hr",38516102333]
["HU-Magyarország:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","HU-Magyarország","Granted","2023-07-03","Stable/Final","Completed","2023-12-16",null,null,null,"2024-03-29",null,null,null,"Stable/Final","Completed","2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-04-02",null,null,null,"Stable/Final","Completed","https://openkkk.nav.gov.hu/Megosztott dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FANPNTS&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D",null,"The developments are in progress.",1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","IE-Éire/Ireland","None","2022-01-28","Stable/Final","Completed","2023-04-01",null,null,null,"2023-06-01",null,null,null,"Stable/Final","Completed","2023-07-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2023-07-01",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/",null,null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","IT-Italia","None","2022-06-01","Stable/Final","Completed","2022-09-05",null,null,null,"2022-12-12",null,null,null,"Stable/Final","Completed","2022-12-13",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/an-pn-ts",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","LT-Lietuva","None","2020-06-01","Stable/Final","Completed","2022-10-15",null,null,null,"2023-03-01",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"Stable/Final","Completed","2022-11-30",null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed","https://lrmuitine.lt/web/guest/1000","Lithuania will use central ICS2 R2 functionalinty for AN and not creating national system. ",null,14,"2025-01-31","Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_NA_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","LU-Luxembourg","Granted","2021-12-14","Stable/Final","Completed","2022-10-01",null,null,null,"2023-07-01",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-03-01",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS.html",null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","LV-Latvija","None","N/A","stable/final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2017-09-24",null,null,null,"stable/final","Completed","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2017-09-25",null,null,null,"stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Notification of arrival is now a part of ICS2.\n",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","MT-Malta","Granted","2024-02-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/",null,null,3,"2025-02-10"]
["NL-Nederland:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","NL-Nederland","Granted","2021-12-31","Stable/Final","Completed","2023-03-01",null,null,null,"2023-06-30",null,null,null,"Stable/Final","Completed","2023-06-30",null,null,null,"Stable/Final","Completed","2023-06-30",null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed","https://www.nhdouane.nl/",null,null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","PL-Polska","Granted","2023-01-01","Stable/Final","Completed","2023-06-01",null,null,null,"2023-09-30",null,null,null,"Stable/Final","Completed","2023-07-01",null,null,null,"Stable/Final","Completed","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","2023-09-30",null,null,null,"Stable/Final","Completed",null,null,"Poland was granted a derogation decision.AN functionalities are being developed within ICS2 system and according to its schedule.",0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","PT-Portugal","Granted/Requested","2022-07-31","Stable/Final","Completed","2022-12-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-04-04",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-04-07",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024","Projects 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nOngoing the activities and tests with airports Authorities;\nDevelopment and testing is ongoing.",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","RO-România ","Granted","2022-04-13","Stable/Final","Completed","2024-05-01",null,null,null,"2024-05-31",null,null,null,"Stable/Final","Completed","2024-05-01",null,null,null,"Stable/Final","Completed","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","2024-05-01",null,null,null,"Stable/Final","Completed","https://www.customs.ro/e-customs/ICS2/reglementari",null,null,3,"2025-02-10","Security and Safety Risk Analysis Service","ro.helpdesk.ics2@customs.ro",40216373051]
["SE-Sverige:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","SE-Sverige","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-03-01",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"2023-03-01",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/arrivalnotificationformeansoftransport.4.422c8052175b1d8276959ea.html","We are going to use the central functionalities developed by the COM within the ICS2 project and the date of deployment and operational date follow the expected timelines from the different releases in this project. ",null,24,"2025-01-27","Intelligence Department","underrattelseavd.npm.ics2@tullverket.se",46771520520]
["SI-Slovenija:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","SI-Slovenija","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-03-01",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/","Use in ICS2 Arrival process for air cargo and STI foreseen to be in use for maritime in 2024 and other means of transport in 2025. No national solution is nedeed.",null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Notification of Arrival (AN) - Aircraft","UCC Notification of Arrival (AN) - Aircraft","SK-Slovensko","Granted","2022-10-01","Stable/Final","Completed","2022-12-01",null,null,null,"2023-02-14",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-03-01",null,null,null,"Stable/Final","Completed",null,"We use central solution via STI/HTI in ICS2-CR",null,1,"2025-01-27","Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]
["AT-Österreich:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","AT-Österreich","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html","Not applicabale because only air traffic in Austria",null,15,"2025-02-12","Federal ministry of finance, division I/2","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51433"]
["BE-Belgique/België:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","BE-Belgique/België","Granted","2021-10-12","Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2025-09-01",null,null,null,"Stable/Final","In progress",null,null,null,3,"2025-01-30"]
["BG-България:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","BG-България","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-06-03",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-06-03",null,null,null,"Stable/Final","Completed",null,null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","CY-Κύπρος","Granted","2023-05-22","Stable/Final","Completed","2023-10-01",null,null,null,"2025-03-10",null,null,null,"Stable/Final","In progress","2025-03-31",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-03-31",null,null,null,"Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","CZ-Česká republika","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2023-12-05",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-12-05",null,null,null,"Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"This \"message\" will be covered by the transeuropean system ICS2.  All Milestones affecting EO need to be considered in line with the ICS2 planning for Release 2 and Release 3 provided by EU-COM, especially in relation to the STI. ",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","DK-Danmark","Granted","2021-09-01","Stable/Final","Completed","2023-12-11",null,null,null,"2024-12-04",null,null,null,"Stable/Final","Completed","2024-05-25",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2024-12-04",null,null,null,"Stable/Final","Completed","2025-03-31",null,null,null,"Stable/Final","In progress",null,null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","EE-Eesti","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2025-04-01",null,null,null,"Stable/Final","In progress","2025-04-01",null,null,null,"Stable/Final","In progress",null,null,"A derogation request was accordingly submitted by EE on 06.07.2022.",20,"2025-02-10","Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","ES-España","Granted","2022-03-01","Stable/Final","Completed","2023-10-01",null,null,null,"2024-12-04",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2024-12-04",null,null,null,"Stable/Final","Completed","2024-12-04",null,null,null,"Stable/Final","Completed",null,"NA for Martime aligned with ICS2 R3",null,3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","FI-Suomi/Finland","None","2022-06-30","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-06-30",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"2024-06-30",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","FR-France","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2025-04-01",null,null,null,"Stable/Final","In progress","2025-04-01",null,null,null,"Stable/Final","In progress",null,null,"Updated planning",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","GR-Ελλάδα","Granted","2023-09-30","Stable/Final","Completed","2023-09-30",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"Stable/Final","In progress","2024-03-31",null,null,null,"2025-03-31",null,null,null,"Stable/Final","In progress","2024-06-30",null,null,null,"Stable/Final","In progress","https://www.aade.gr/customs",null,null,7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","HR-Hrvatska","Granted","2022-11-07","Stable/Final","Completed","2024-06-03",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2024-12-04",null,null,null,"Stable/Final","Completed","2023-06-03",null,null,null,"2024-12-04",null,null,null,"Stable/Final","Completed","2024-12-04",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/","For maritime transport start on 04.12.2024.regarding ICS2 R3 step 1.   EOs use STI for submission AN like for ISC R2.",null,9,"2025-01-31","Sector for customs system","ICS2@carina.hr",38516102333]
["HU-Magyarország:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","HU-Magyarország","Granted","2023-07-03","Stable/Final","Completed","2023-12-16",null,null,null,"2024-03-29",null,null,null,"Stable/Final","Completed","2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","IE-Éire/Ireland","None","2022-01-28","Stable/Final","Completed","2023-12-01",null,null,null,"2025-07-31",null,null,null,"Stable/Final","In progress","2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2025-07-31",null,null,null,"Stable/Final","In progress","2025-07-31",null,null,null,"Stable/Final","In progress","https://www.revenue.ie/","In accordance with Article 133 of UCC, where the informationon arrival is available to the customs authorities they may waive this notification. In IE we are provided with this information from our port and airport authorities and will not, therefore, require the operators to submit notifications of arrival to the STI until the implementation of ICS2 R3",null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","IT-Italia","None","2024-03-27","Stable/Final","Completed","2024-05-03",null,null,null,"2024-05-31",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","LT-Lietuva","None","2020-06-01","Stable/Final","Completed","2022-10-15",null,null,null,"2024-06-01",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2025-04-01",null,null,null,"Stable/Final","In progress","2025-04-01",null,null,null,"Stable/Final","In progress","https://lrmuitine.lt/web/guest/1000","Lithuania will use central ICS2 R2 functionalinty for AN and not creating national system. Economic operators ask to postpone the beginning of operation in accordance with ICS2 R2 deployment window. ",null,14,"2025-01-31","Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_NA_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","LU-Luxembourg","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable",null,null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","LV-Latvija","None","2022-01-10","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2023-03-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-09-01",null,null,null,"Stable/Final","In progress","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Information related to arrival is available to customs via International freight logistic and port information system administred by the Ministry of Transport. The process will be adjusted along with the end of transition for ICS2 R3 (systems is already operational in customs) for trade and implementation of Maritime SW",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","MT-Malta","Granted","2024-06-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started",null,null,null,3,"2025-02-10"]
["NL-Nederland:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","NL-Nederland","Granted","2023-09-01","Stable/Final","Completed","2024-01-01",null,null,null,"29/02/2025",null,null,null,"Indicative","In progress","2024-05-27",null,null,null,"Stable/Final","Completed","2024-08-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-09-01",null,null,null,"Indicative","In progress",null,"NL is considering to combine the migration for traders for AN maritime with ICS2 R3, following a request from Trade",null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","PL-Polska","Granted","2023-01-01","Stable/Final","Completed","2024-04-01",null,null,null,"2024-12-04",null,null,null,"Indicative","In progress","2024-06-03",null,null,null,"Stable/Final","Completed","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","2024-12-04",null,null,null,"Stable/Final","Completed",null,null,"Poland was granted a derogation decision.AN functionalities are being developed within ICS2 system and according to its schedule.",0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","PT-Portugal","Granted/Requested","2022-07-31","Stable/Final","Completed","2022-12-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-04-04",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-04-07",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024","Projects 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nOngoing the activities and tests with ports Authorities;\nEOs started testing;\nDevelopment and testing is ongoing.",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","RO-România ","Granted","2023-07-12","Indicative","In progress","2024-12-16",null,null,null,"2025-09-01",null,null,null,"Indicative","In progress","2024-12-16",null,null,null,"Stable/Final","Completed","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","2025-04-01",null,null,null,"Indicative","In progress",null,null,null,3,"2025-02-10","Security and Safety Risk Analysis Service","ro.helpdesk.ics2@customs.ro",40216373051]
["SE-Sverige:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","SE-Sverige","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/arrivalnotificationformeansoftransport.4.422c8052175b1d8276959ea.html","We are going to use the central functionalities developed by the COM within the ICS2 project and the date of deployment and operational date follow the expected timelines from the different releases in this project. ",null,24,"2025-01-27","Intelligence Department","underrattelseavd.npm.ics2@tullverket.se",46771520520]
["SI-Slovenija:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","SI-Slovenija","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-06-02",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/","Use in ICS2 Arrival process for air cargo and STI foreseen to be in use for maritime in 2024 and other means of transport in 2025. No national solution is nedeed.",null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Notification of Arrival (AN) - Maritime","UCC Notification of Arrival (AN) - Maritime","SK-Slovensko","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable",null,null,null,null,null,null,null,null,null,null,"N/A",null,null,null,null,"Not applicable",null,null,null,1,"2025-01-27","Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]
["AT-Österreich:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","AT-Österreich","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html","Not applicabale because only air traffic in Austria",null,15,"2025-02-12","Federal ministry of finance, division I/2","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51433"]
["BE-Belgique/België:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","BE-Belgique/België","Granted","N/A","","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable",null,null,null,3,"2025-01-30"]
["BG-България:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","BG-България","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","CY-Κύπρος","Granted","N/A","","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable",null,null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","CZ-Česká republika","Granted","2024-06-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-06-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-06-01",null,null,null,"Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"This \"message\" will be covered by the transeuropean system ICS2.  All Milestones affecting EO need to be considered in line with the ICS2 planning for Release 2 and Release 3 provided by EU-COM, especially in relation to the STI. ",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","DK-Danmark","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"N/A","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable",null,"In reference to UCC article 133, notification of arrival is only applicable for a sea-going vessel or an aircraft entering the customs territory. \n ",null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","EE-Eesti","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,20,"2025-02-10","Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","ES-España","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"There is no Notification of Arrival in Road and Rail",null,3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","FI-Suomi/Finland","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","FR-France","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","GR-Ελλάδα","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","HR-Hrvatska","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","https://carina.gov.hr/","N/A","N/A",9,"2025-01-31","Sector for customs system","ICS2@carina.hr",38516102333]
["HU-Magyarország:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","HU-Magyarország","Granted","2023-07-03","Stable/Final","Completed","2023-12-16",null,null,null,"2024-03-29",null,null,null,"Stable/Final","Completed","2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","IE-Éire/Ireland","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable",null,"N/A  Arrival for ICS2 Road is not required",null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","IT-Italia","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","LT-Lietuva","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,14,"2025-01-31","Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_NA_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","LU-Luxembourg","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","LV-Latvija","None","2022-01-10","Stable/Final","Completed","2025-03-03",null,null,null,"2025-09-01",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-09-01",null,null,null,"Indicative","Not started","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas",null,null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","MT-Malta","Granted","2024-06-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started",null,null,null,3,"2025-02-10"]
["NL-Nederland:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","NL-Nederland","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable",null,null,null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","PL-Polska","Granted","2022-09-19","Stable/Final","Completed","2023-12-11",null,null,null,"2025-08-31",null,null,null,"Stable/Final","In progress","2025-04-01",null,null,null,"Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-09-01",null,null,null,"Stable/Final","Not started",null,null,"Poland was granted a derogation decision.AN functionalities are being developed within ICS2 system and according to its schedule.",0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","PT-Portugal","Granted/Requested",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","RO-România ","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-09-01",null,null,null,"Indicative","Not started",null,null,null,3,"2025-02-10","Security and Safety Risk Analysis Service","ro.helpdesk.ics2@customs.ro",40216373051]
["SE-Sverige:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","SE-Sverige","Granted","N/A",null,"Not applicable","N/A",null,null,null,null,null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/arrivalnotificationformeansoftransport.4.422c8052175b1d8276959ea.html","We are going to use the central functionalities developed by the COM within the ICS2 project and the date of deployment and operational date follow the expected timelines from the different releases in this project. ",null,24,"2025-01-27","Intelligence Department","underrattelseavd.npm.ics2@tullverket.se",46771520520]
["SI-Slovenija:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","SI-Slovenija","Granted","N/A","","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable",null,null,null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Notification of Arrival (AN) - Road and rail transport","UCC Notification of Arrival (AN) - Road and rail transport","SK-Slovensko","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable",null,null,null,null,null,null,null,null,null,null,"N/A",null,null,null,null,"Not applicable",null,null,null,1,"2025-01-27","Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]
["AT-Österreich:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","AT-Österreich","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/3","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51434"]
["BE-Belgique/België:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","BE-Belgique/België","Granted","2021-10-12","Stable/Final",null,"2023-03-01",null,null,null,"2023-06-30",null,null,null,"Stable/Final","Completed","2023-07-05",null,null,null,"Stable/Final","Completed","2023-07-05",null,null,null,"2023-12-31",null,null,null,"Indicative","In progress","2023-12-31",null,null,null,"Indicative","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","BG-България","None","2023-08-04","Stable/Final","Completed","2023-09-04",null,null,null,"2023-10-16",null,null,null,"Stable/Final","Completed","2023-11-10",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-01-15",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/","In rеlation with the update of NIS, which was aligned with the requirements of the new Annex B.",null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","CY-Κύπρος","Granted","2023-05-22","Stable/Final","Completed","2023-10-01",null,null,null,"2025-03-10",null,null,null,"Stable/Final","In progress","2025-03-31",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-03-31",null,null,null,"Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,"Derogation was granted.",8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","CZ-Česká republika","Granted","2023-09-01","Stable/Final","Completed","2023-11-01",null,null,null,"2023-12-01",null,null,null,"Stable/Final","Completed","2023-12-05",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-12-05",null,null,null,"Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","DE-Deutschland","None","2020-10-09","Stable/Final","Completed","2021-05-01",null,null,null,"2022-10-14",null,null,null,"Stable/Final","Completed","2021-03-06",null,null,null,"Stable/Final","Completed","2021-05-01",null,null,null,"2022-10-14",null,null,null,"Stable/Final","Completed","2022-10-31",null,null,null,"Stable/Final","Completed","https://www.zoll.de/","This \"message\" is updated as part of \"National Entry System\" of the national IT-System ATLAS (Release 9.1). The scope covers all modes of transport.",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","DK-Danmark","Granted","2021-09-01","Stable/Final","Completed","2023-06-15",null,null,null,"2023-11-01",null,null,null,"Stable/Final","Completed","2023-11-06",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"2024-07-15",null,null,null,"Stable/Final","Completed","2024-07-15",null,null,null,"Stable/Final","Completed","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","EE-Eesti","Granted","2020-12-31","Stable/Final","Completed","2020-12-01",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2021-03-15",null,null,null,"Stable/Final","Completed","2021-03-15",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2021-03-15",null,null,null,"Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,"A derogation request was accordingly submitted by EE on 06.07.2022.",20,"2025-02-10","Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","ES-España","Granted","2022-06-30","Stable/Final","Completed","2023-10-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2024-01-01",null,null,null,"Stable/Final","Completed","2024-01-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2026-01-01",null,null,null,"Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,"Aligned with the granted derogation date.",3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","FI-Suomi/Finland","None","2020-03-31","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2021-03-31",null,null,null,"Stable/Final","Completed","2021-03-31",null,null,null,"2021-03-31",null,null,null,"Stable/Final","Completed","2021-03-31",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","FR-France","Granted","2023-03-31","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2024-03-06",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2024-12-04",null,null,null,"Stable/Final","Completed","2024-12-04",null,null,null,"Stable/Final","Completed","https://www.douane.gouv.fr/services-aide/edi","Development in France of a notification of dischargement (like UCC Presentation Notification) – reassessment of business process on board – for 2019\nNA for TS and  CT as we use the European application\nProgress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report","Updated planning",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","GR-Ελλάδα","Granted","2023-09-30","Stable/Final","Completed","2023-09-30",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","https://www.aade.gr/customs","SOME INFORMATION OF G3 ARE NOT PRESENT","derogation request",7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","HR-Hrvatska","Granted","2022-03-31","Stable/Final","Completed","2022-11-01",null,null,null,"2023-04-16",null,null,null,"Stable/Final","Completed","2023-04-17",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-04-17",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/","This answer applies only within the presentation system that is being developed for the needs of ICS2. PN will be implemented as part of ICS2 for ICS2 R2 and R3(only for goods subject to ICS2) The implementation will be done in a step-by-step approach for the relevant modes of transport. The decision to develop PN as part of ICS2 inevitably leads to delays.  EOs will use DW for ICS2 R2 and R3 and will engage in electronic PN activities accordingly (AIR and MARITIME FINSHED).Other systems such as TS or the import system have their own presentation messages. \nThe mentioned activities refer to the Presentation Notification within the framework of Temporary Storage.","Derogation for PN ",9,"2025-01-31","Sector for customs system","PNTS@carina.hr",38516102333]
["HU-Magyarország:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","HU-Magyarország","Granted","2023-07-03","Stable/Final","Completed","2023-12-16",null,null,null,"2024-03-29",null,null,null,"Stable/Final","Completed","2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-04-02",null,null,null,"Stable/Final","Completed","https://openkkk.nav.gov.hu/Megosztott dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FANPNTS&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D",null,"The developments are in progress.",1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","IE-Éire/Ireland","None","2019-10-04","Stable/Final","Completed","2020-04-30",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2021-10-05",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/","Will be updated to Revised Annex B in Q1 2026",null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","IT-Italia","None","2022-06-01","Stable/Final","Completed","2022-09-05",null,null,null,"2022-12-12",null,null,null,"Stable/Final","Completed","2022-12-13",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/an-pn-ts",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","LT-Lietuva","None","2022-07-01","Stable/Final","Completed","2022-10-15",null,null,null,"2023-03-01",null,null,null,"Stable/Final","Completed","2023-02-28",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed","https://lrmuitine.lt/web/guest/1000","All modes of transport is in production.",null,14,"2025-01-31","Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_PN_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","LU-Luxembourg","Granted","2021-12-14","stable/final","Completed","2022-10-01",null,null,null,"2023-07-01",null,null,null,"Stable/Final","Completed","2023-01-10",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-01-10",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS.html",null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","LV-Latvija","None","2017-06-05","Stable/Final","Completed","2017-08-01",null,null,null,"2017-09-22",null,null,null,"stable/final","Completed","2017-09-24",null,null,null,"stable/final","Completed","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2017-09-25",null,null,null,"stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Information related to presentation notification is a part of TS declaration. Since implementation of ICS R2 PN is also being submitted in ICS2 R2. ",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","MT-Malta","Granted","2024-02-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/",null,null,3,"2025-02-10"]
["NL-Nederland:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","NL-Nederland","Granted","2022-09-01","Stable/Final","Completed","2023-11-06",null,null,null,"2024-02-29",null,null,null,"Stable/Final","Completed","2023-12-01",null,null,null,"Stable/Final","Completed","2023-12-01",null,null,null,"2024-02-29",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","https://www.nhdouane.nl/",null,null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","PL-Polska","Granted","2022-07-29","Stable/Final","Completed","2023-09-30",null,null,null,"2025-04-30",null,null,null,"Stable/Final","In progress","2025-04-20",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A ",null,null,null,null,"Not applicable","2025-05-01",null,null,null,"Stable/Final","Not started",null,null,"Poland was granted a derogation decision. PN functionalities are being developed within national import system and according to its schedule.",0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","PT-Portugal","Granted/Requested","2022-07-31","Stable/Final","Completed","2023-03-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-04-04",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-04-07",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024"," Projects 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nDevelopment and testing is ongoing.",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","RO-România ","Granted","2024-09-30","Stable/Final","Completed","2024-09-30",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Completed","2024-11-14",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-11-14",null,null,null,"Stable/Final","Completed","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn",null,null,3,"2025-02-10","Customs procedures department","vama@customs.ro",40213155858]
["SE-Sverige:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","SE-Sverige","Granted","2022-12-01","Stable/Final","Completed","2023-09-27",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-09-27",null,null,null,"Stable/Final","Completed","2023-09-27",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html",null,null,24,"2025-01-27","Control Department","projekt.ava.dtl@tullverket.se",46771520520]
["SI-Slovenija:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","SI-Slovenija","Granted","2022-10-01","Stable/Final","Completed","2022-11-01",null,null,null,"2023-02-01",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-12-01",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/","","completed within the deadlines set by the derogation regulation",18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Presentation Notification (PN) - Aircraft","UCC Presentation Notification (PN) - Aircraft","SK-Slovensko","Granted/Requested","2023-02-01","Stable/Final","Completed","2023-02-01",null,null,null,"2023-08-31",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed",null,"No standalone national presentation system. PN functionalities are implemented in all impacted systems.",null,1,"2025-01-27","Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]
["AT-Österreich:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","AT-Österreich","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html","Not applicabale",null,15,"2025-02-12","Federal ministry of finance, division I/3","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51434"]
["BE-Belgique/België:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","BE-Belgique/België","Granted","2021-10-12","Stable/Final","In progress","2023-08-01",null,null,null,"2024-02-28",null,null,null,"Stable/Final","In progress","2023-07-05",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2024-12-31",null,null,null,"Indicative","In progress","2024-12-31",null,null,null,"Indicative","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","BG-България","None","2023-08-04","Stable/Final","Completed","2023-09-04",null,null,null,"2023-10-16",null,null,null,"Stable/Final","Completed","2023-11-10",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-01-15",null,null,null,"Stable/Final","Completed",null,null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","CY-Κύπρος","Granted","2023-05-22","Stable/Final","Completed","2023-10-01",null,null,null,"2025-03-10",null,null,null,"Stable/Final","In progress","2025-03-31",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not started","2025-03-31",null,null,null,"Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","CZ-Česká republika","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-12-05",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-12-05",null,null,null,"Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Please refer to \"Air transport\".",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","DK-Danmark","Granted","2024-03-01","Stable/Final","Completed","2024-04-15",null,null,null,"2024-05-24",null,null,null,"Stable/Final","Completed","2024-05-25",null,null,null,"Stable/Final","Completed","2024-05-25",null,null,null,"2024-07-15",null,null,null,"Stable/Final","Completed","2024-07-15",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","EE-Eesti","Granted","2020-12-31","Stable/Final","Completed","2023-11-01",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2021-03-15",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2025-09-01",null,null,null,"Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele","We would like to draw your attention on the fact that  this project is closely linked to project ICS2 and the project deadlines should be amended accordingly. It means that end date of the deployment window of PN should be 01/09/2025.",null,20,"2025-02-10",null,"AN-PN-TS-NPM-EE@emta.ee"]
["ES-España:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","ES-España","Granted","2022-06-30","Stable/Final","Completed","2023-10-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2024-03-01",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2026-01-01",null,null,null,"Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html","Final date for Migration and the date for Operations depend on the deployment date of EMSWe ","Aligned with the granted derogation date. Although the EO are encouraged to continue filing in the national single maritime window until the EMSWe replaces it.",3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","FI-Suomi/Finland","None","2022-06-30","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-06-30",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"2024-06-30",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","FR-France","Granted","2023-03-31","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2025-04-01",null,null,null,"Stable/Final","In progress","2025-04-01",null,null,null,"Indicative","In progress",null,null,"Updated planning",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","GR-Ελλάδα","Granted","2023-09-30","Stable/Final","Completed","2023-09-30",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"Stable/Final","In progress","2024-03-31",null,null,null,"2025-03-31",null,null,null,"Stable/Final","In progress","2024-06-30",null,null,null,"Stable/Final","In progress","https://www.aade.gr/customs",null,null,7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","HR-Hrvatska","Granted","2022-03-31","Stable/Final","Completed","2023-01-02",null,null,null,"2023-04-16",null,null,null,"Stable/Final","Completed","2023-04-17",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-04-17",null,null,null,"Stable/Final","Completed",null,"The mentioned activities refer to the Presentation Notification within the framework of temporary storage",null,9,"2025-01-31","Sector for customs system","PNTS@carina.hr",38516102333]
["HU-Magyarország:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","HU-Magyarország","Granted","2023-07-03","Stable/Final","Completed","2023-12-16",null,null,null,"2024-03-29",null,null,null,"Stable/Final","Completed","2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","IE-Éire/Ireland","None","2019-10-04","Stable/Final","Completed","2020-04-30",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2021-10-05",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/",null,null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","IT-Italia","None","2024-03-27","Stable/Final","Completed","2024-05-03",null,null,null,"2024-05-31",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","LT-Lietuva","None","2022-07-01","Stable/Final","Completed","2022-10-15",null,null,null,"2025-08-30",null,null,null,"Stable/Final","In progress","2023-02-28",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"2025-04-01",null,null,null,"Stable/Final","In progress","2025-04-01",null,null,null,"Stable/Final","In progress","https://lrmuitine.lt/web/guest/1000","For Other modes of transport the deployment windows will be granted for EO the same as fr ICS2 R3 economic operators. For traders using the ICS2-R3 deployment window, the migration is expected from 03/06/2024.",null,14,"2025-01-31","Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_PN_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","LU-Luxembourg","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable",null,null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","LV-Latvija","None","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-09-01",null,null,null,"Stable/Final","In progress","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Currently depending on the business case PN is as a part of TS or NIS or Port system administrered by the Ministry of Transport for goods coming by maritime transport (according to the Article 190 of IA of the UCC) where notification for unloading (incl. PN data set) is submitted. When trade will join ICS3 R3 - PN will be also a part of ICS2 ",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","MT-Malta","Granted","2024-06-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started",null,null,null,3,"2025-02-10"]
["NL-Nederland:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","NL-Nederland","Granted","2023-09-01","Stable/Final","Completed","2024-01-01",null,null,null,"29/02/2025",null,null,null,"Stable/Final","In progress","2024-05-27",null,null,null,"Stable/Final","Completed","2024-08-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-04-01",null,null,null,"Indicative","Not started",null,"NL is considering to combine the migration for traders for PN maritime with ICS2 R3, following a request from Trade",null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","PL-Polska","Granted","2022-07-29","Stable/Final","Completed","2023-09-30",null,null,null,"2025-04-30",null,null,null,"Stable/Final","In progress","2025-04-20",null,null,null,"Stable/Final","Not started","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","2025-05-01",null,null,null,"Stable/Final","Not started",null,null,"Poland was granted a derogation decision.PN functionalities are being developed within national import system and according to its schedule.",0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","PT-Portugal","Granted","2022-07-31","Stable/Final","Completed","2023-03-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-04-04",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-04-07",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024","Projects 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nDevelopment and testing is ongoing.",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","RO-România ","Granted","2024-09-30","Stable/Final","Completed","2024-09-30",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Completed","2024-11-14",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-11-14",null,null,null,"Stable/Final","Completed","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn",null,null,3,"2025-02-10","Customs procedures department","vama@customs.ro",40213155858]
["SE-Sverige:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","SE-Sverige","Granted/Requested","2022-12-01","Stable/Final","Completed","2023-09-27",null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-06-03",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html","From 3 June 2024 presentation notifications of goods transported by sea should be submitted. The requirement to present goods to customs only applies to goods that are unloaded in Sweden. The presentation notification should refer to the entry summary declaration. To submit presentation notifications for goods, additional information will be required in the MSW from 3 June 2024. Any information that is not provided in structured form when calling at a port, will be collected in an Excel file which is uploaded to MSW Reportal. This information should be provided when unloading goods from third countries (with the exception of goods arriving from Norway).\n\nProvide the following additional information:\n\nENS reference\nTransport document reference at Master and/or House consignment level\nContainer\nReceptacle.","Concerning maritime traffic we have asked for derogation until the 15 August 2025. We are for the moment analysing the consequences for the customs formalities since the deployment of MNSW In Sweden will be delayed Q1 2027.  ",24,"2025-01-27","Control Department","projekt.ava.dtl@tullverket.se",46771520520]
["SI-Slovenija:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","SI-Slovenija","Granted","2022-10-01","Stable/Final","Completed","2022-01-01",null,null,null,"2024-02-28",null,null,null,"Stable/Final","Completed","2024-02-29",null,null,null,"Stable/Final","Completed","2024-01-01",null,null,null,"2024-02-29",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/","","completed within the deadlines set by the derogation regulation",18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Presentation Notification (PN) - Maritime","UCC Presentation Notification (PN) - Maritime","SK-Slovensko","Granted/Requested","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable",null,null,null,null,null,null,null,null,null,null,"N/A",null,null,null,null,"Not applicable",null,null,null,1,"2025-01-27","Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]
["AT-Österreich:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","AT-Österreich","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","https://www.bmf.gv.at/themen/zoll/uzk-it-anwendungen/ics2-import-control-system.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/3","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51434"]
["BE-Belgique/België:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","BE-Belgique/België","Granted","N/A","","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable",null,null,null,3,"2025-01-30"]
["BG-България:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","BG-България","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","CY-Κύπρος","Granted","N/A","","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable",null,null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","CZ-Česká republika","Granted","2024-06-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-06-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-06-01",null,null,null,"Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Please refer to \"Air transport\".",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","DK-Danmark","Granted","2022-08-01","Stable/Final","Completed","2023-03-01",null,null,null,"2023-05-22",null,null,null,"Stable/Final","Completed","2023-07-29",null,null,null,"Stable/Final","Completed","2023-07-29",null,null,null,"2024-07-08",null,null,null,"Stable/Final","Completed","2024-07-08",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","EE-Eesti","Granted","2020-12-31","Stable/Final","Completed","2024-06-03",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2021-03-15",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2025-09-01",null,null,null,"Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,20,"2025-02-10","Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","ES-España","Granted","2022-06-30","Stable/Final","Completed","2023-10-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2024-03-01",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2026-01-01",null,null,null,"Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","FI-Suomi/Finland","None","2022-06-30","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-06-30",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"2024-06-30",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","FR-France","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","GR-Ελλάδα","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","HR-Hrvatska","Granted","2022-03-31","Stable/Final","Completed","2023-01-02",null,null,null,"2023-04-16",null,null,null,"Stable/Final","Completed","2023-04-17",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-04-17",null,null,null,"Stable/Final","Completed","https://openkkk.nav.gov.hu/Megosztott dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FANPNTS&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D","The mentioned activities refer to the Presentation Notification within the framework of temporary storage",null,9,"2025-01-31","Sector for customs system","PNTS@carina.hr",38516102333]
["HU-Magyarország:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","HU-Magyarország","Granted","2023-07-03","Stable/Final","Completed","2023-12-16",null,null,null,"2024-03-29",null,null,null,"Stable/Final","Completed","2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","IE-Éire/Ireland","None","2019-10-04","Stable/Final","Completed","2020-04-30",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2021-10-05",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/",null,null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","IT-Italia","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","LT-Lietuva","None","01/07/2022","Stable/Final","Completed","2022-10-15",null,null,null,"2025-08-30",null,null,null,"Stable/Final","In progress","2023-02-28",null,null,null,"Stable/Final","Completed","2024-11-01",null,null,null,"2025-04-01",null,null,null,"Stable/Final","In progress","2025-09-01",null,null,null,"Stable/Final","In progress","https://lrmuitine.lt/web/guest/1000",null,null,14,"2025-01-31","Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_PN_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","LU-Luxembourg","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","LV-Latvija","None","2022-01-10","Stable/Final","Completed","2025-03-03",null,null,null,"2025-09-01",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-09-01",null,null,null,"Indicative","Not started","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas",null,null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","MT-Malta","Granted","2024-06-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started",null,null,null,3,"2025-02-10"]
["NL-Nederland:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","NL-Nederland","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable",null,null,null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","PL-Polska","Granted","2022-07-29","Stable/Final","Completed","2023-09-30",null,null,null,"2025-08-31",null,null,null,"Stable/Final","In progress","2025-04-20",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-09-01",null,null,null,"Stable/Final","Not started",null,null,"Poland was granted a derogation decision. PN functionalities are being developed within national import and ICS2 systems and according to its schedule.",0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","PT-Portugal","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","RO-România ","Granted","2024-09-30","Stable/Final","Completed","2024-09-30",null,null,null,"2024-12-31",null,null,null,"Stable/Final","In progress","2025-06-30",null,null,null,"Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Stable/Final","In progress","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn","We are reporting a delay in depolyment of PN because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 12/31/2023. Also, this system is depending by ICS 2 ","the updated deadlines took into account the derogation decisions",3,"2025-02-10","Customs procedures department","vama@customs.ro",40213155858]
["SE-Sverige:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","SE-Sverige","Granted/Requested","2022-12-01","Stable/Final","Completed","2023-09-27",null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-03-01",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html","For goods that arrive by road from Norway, it will be possible to digitally present goods at customs offices from 1 March 2024. It will also be possible to submit a digital I2 message. However, during a transition period the practical procedure will consist of the driver submitting a manual presentation in the form of the single administrative document (SAD) on paper, .",null,24,"2025-01-27","Control Department","projekt.ava.dtl@tullverket.se",46771520520]
["SI-Slovenija:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","SI-Slovenija","Granted","N/A","","Not applicable","N/A",null,null,null,"",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable","N/A",null,null,null,"",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable",null,null,null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Presentation Notification (PN) - Road and rail transport","UCC Presentation Notification (PN) - Road and rail transport","SK-Slovensko","Granted/Requested","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable",null,null,null,null,null,null,null,null,null,null,"N/A",null,null,null,null,"Not applicable",null,null,null,1,"2025-01-27","Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]
["AT-Österreich:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","AT-Österreich","Granted","2024-10-01","Stable/Final","Completed","2025-02-28",null,null,null,"2025-09-01",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-09-15",null,null,null,"Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/4","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51435"]
["BE-Belgique/België:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","BE-Belgique/België","Granted","2021-10-12","Stable/Final","In progress","2023-08-01",null,null,null,"2025-09-30",null,null,null,"Stable/Final","In progress","2023-11-29",null,null,null,"Stable/Final","Completed","2023-11-29",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2025-12-31",null,null,null,"Indicative","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0","Will be aligned with the releases of ICS2, which means that the transportmodi that are part of ICS 2 Part 3 will only start on 1/3/2024.",null,3,"2025-01-30"]
["BG-България:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","BG-България","None","2023-08-04","Stable/Final","Completed","2023-09-04",null,null,null,"2023-10-16",null,null,null,"Stable/Final","Completed","2023-11-10",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-01-15",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/","In rеlation with the update of NIS, which was aligned with the requirements of the new Annex B.",null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","CY-Κύπρος","Granted","2023-05-22","Stable/Final","Completed","2023-10-01",null,null,null,"2025-03-10",null,null,null,"Stable/Final","In progress","2025-03-31",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-03-31",null,null,null,"Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,"Derogation was granted.",8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","CZ-Česká republika","Granted","2023-09-01","Stable/Final","Completed","2023-11-01",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-05",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-12-05",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","DE-Deutschland","None","2020-10-09","Stable/Final","Completed","2021-05-01",null,null,null,"2022-10-14",null,null,null,"Stable/Final","Completed","2021-03-06",null,null,null,"Stable/Final","Completed","2021-05-01",null,null,null,"2022-10-14",null,null,null,"Stable/Final","Completed","2022-10-31",null,null,null,"Stable/Final","Completed","https://www.zoll.de/","This \"message\" is updated as part of \"National Entry System\" of the national IT-System ATLAS (Release 9.1). The scope covers all modes of transport.\nPlease note, that the datamodel is not in line with EU-CDM (FMS) and will be updated following the approach of CCI and the national import system being the basis for the new and modernized import application.",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","DK-Danmark","Granted","2024-09-01","Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-06-30",null,null,null,"Indicative","Not started","2024-12-01",null,null,null,"2025-10-01",null,null,null,"Indicative","In progress","2025-10-01",null,null,null,"Indicative","Not started","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","EE-Eesti","Granted","2020-12-31","Stable/Final","Completed","2021-01-04",null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele","Estonia has deployed Temporary Storage/Presentation Notification (TS/PN) systems.\n However, not all traders will be using TS/PN system from the 1st of January 2023. The system is open for the migration for the traders. We have previously repeatedly informed Commission that the deadlines for TS and ICS2 should be synchronized (mainly because of the datasets). In that case, traders dealing with air cargo would migrate at the latest accordingly to the national deployment date of ICS2 release 2 and other traders accordingly to the ICS2 release 3.","A derogation request was accordingly submitted by EE on 06.07.2022.",20,"2025-02-10","Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","ES-España","Granted","2022-06-30","Stable/Final","Completed","2023-10-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2024-01-01",null,null,null,"Stable/Final","Completed","2024-01-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2026-01-01",null,null,null,"Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,"Aligned with the granted derogation date.  Some functionallity not yet available, like G5 for G4 filings.",3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","FI-Suomi/Finland","None","2020-12-31","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2022-12-31",null,null,null,"Stable/Final","Completed","2022-12-31",null,null,null,"2022-12-31",null,null,null,"Stable/Final","Completed","2022-12-31",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","FR-France","Granted","2023-03-31","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2024-03-06",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2024-12-04",null,null,null,"Stable/Final","Completed","2024-12-04",null,null,null,"Stable/Final","Completed","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report","Updated planning",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","GR-Ελλάδα","Granted","2024-12-31","Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Indicative","Not started","2025-06-30",null,null,null,"2025-06-30",null,null,null,"Indicative","Not started","2025-06-30",null,null,null,"Indicative","Not started",null,null,"derogation request",7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","HR-Hrvatska","Granted","2022-03-31","Stable/Final","Completed","2022-11-01",null,null,null,"2023-04-16",null,null,null,"Stable/Final","Completed","2023-04-17",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-04-17",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/","TS deployment and operation completed on 17.04.2023. The system is fully operational and in use by traders and customs from that date. ",null,9,"2025-01-31","Sector for customs system","PNTS@carina.hr",38516102333]
["HU-Magyarország:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","HU-Magyarország","Granted","2023-03-31","Stable/Final","Completed","2023-12-16",null,null,null,"2024-03-29",null,null,null,"Stable/Final","Completed","2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-04-02",null,null,null,"Stable/Final","Completed","https://openkkk.nav.gov.hu/Megosztott dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FANPNTS&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D",null,"The developments are in progress.",1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","IE-Éire/Ireland","None","2019-10-04","Stable/Final","Completed","2020-04-30",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2021-10-05",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/","Will be updated to Revised Annex B in Q1 2026",null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","IT-Italia","None","2022-06-01","Stable/Final","Completed","2022-09-05",null,null,null,"2022-12-12",null,null,null,"Stable/Final","Completed","2022-12-13",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/dogane/operatore/ecustoms-aida/progetti-aida",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","LT-Lietuva","Granted","2023-05-04","Stable/Final","Completed","2023-06-04",null,null,null,"2023-11-17",null,null,null,"Stable/Final","Completed","2023-10-31",null,null,null,"Stable/Final","Completed","2023-10-31",null,null,null,"2023-10-31",null,null,null,"Stable/Final","Completed","2023-11-19",null,null,null,"Stable/Final","Completed","https://lrmuitine.lt/web/guest/591",null,null,14,"2025-01-31","Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_TS_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","LU-Luxembourg","Granted","2021-12-14","stable/final","Completed","2022-10-01",null,null,null,"2023-07-01",null,null,null,"Stable/Final","Completed","2023-01-10",null,null,null,"stable/final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-01-10",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS.html",null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","LV-Latvija","None","2017-06-05","stable/final","Completed","2017-08-01",null,null,null,"2017-09-22",null,null,null,"stable/final","Completed","2017-09-24",null,null,null,"stable/final","Completed","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2017-09-25",null,null,null,"stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","As from 24.09.2017 National Temporary Storage System has been updated according to UCC data elements. Additional functionality for movements between TS places (if located in Latvia) has been added on 5.03.2018. The undated version of national TS system according to the latest changes of EUCDM is in production since 15.02.2022. ",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","MT-Malta","Granted","2024-02-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/",null,null,3,"2025-02-10"]
["NL-Nederland:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","NL-Nederland","Granted","2022-09-01","Stable/Final","Completed","2023-11-06",null,null,null,"2024-02-29",null,null,null,"Stable/Final","Completed","2023-12-01",null,null,null,"Stable/Final","Completed","2023-12-01",null,null,null,"2024-02-29",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","https://www.nhdouane.nl/",null,null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","PL-Polska","Granted","2022-07-29","Stable/Final","Completed","2023-09-30",null,null,null,"2025-04-30",null,null,null,"Stable/Final","In progress","2025-04-20",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-05-01",null,null,null,"Stable/Final","Not started",null,null,"Poland was granted a derogation decision.TS functionalities are being developed within national import system and according to its schedule.",0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","PT-Portugal","Granted/Requested","2022-07-31","stable/final","Completed","2022-12-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-04-04",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-04-07",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024","Project 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nDevelopment and testing is ongoing.",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","RO-România ","Granted","2025-03-31","Indicative","In progress","2025-03-01",null,null,null,"2025-06-30",null,null,null,"Indicative","In progress","2025-06-30",null,null,null,"Indicative","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Stable/Final","In progress","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn","We are reporting a delay in depolyment of TSD because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 12/31/2023. Also, this system is depending by ICS 2 ","the updated deadlines took into account the derogation decisions",3,"2025-02-10","Customs procedures department","vama@customs.ro",40213155858]
["SE-Sverige:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","SE-Sverige","Granted/Requested","2024-04-01","Stable/Final","Completed","2024-07-01",null,null,null,"2024-12-31",null,null,null,"Indicative","Not started","2024-10-08",null,null,null,"Stable/Final","Completed","2024-10-08",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Completed","2024-12-31",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html",null,null,24,"2025-01-27","Control Department","projekt.ava.dtl@tullverket.se",46771520520]
["SI-Slovenija:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","SI-Slovenija","Granted","2023-04-28","Stable/Final","Completed","2023-09-01",null,null,null,"2024-02-28",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","2023-11-30",null,null,null,"2024-02-28",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/","","completed within the deadlines set by the derogation regulation",18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Temporary Storage (TS) - Aircraft","UCC Temporary Storage (TS) - Aircraft","SK-Slovensko","Granted/Requested","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","N/A",null,null,null,"indicative","Not applicable",null,null,null,null,null,null,null,null,null,null,"N/A",null,null,null,"indicative","Not applicable",null,"TS business is done with other workarounds in multiple systems and evidences. No TP system in line with annex B of UCC DA is in place at this moment. NA-SK is planning to develope TS system sometime in 2026-2027","Deadline defined in COM Implementing Decision 2023/236 not reached. Second request for derogation sent on 22nd of November 2023.",1,"2025-01-27","Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]
["AT-Österreich:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","AT-Österreich","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","N/A",null,null,null,"Stable/Final","Not applicable",null,"Not applicabale because only air traffic in Austria",null,15,"2025-02-12","Federal ministry of finance, division I/4","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51435"]
["BE-Belgique/België:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","BE-Belgique/België","Granted","2021-10-12","Stable/Final","Completed","2023-08-01",null,null,null,"2025-09-30",null,null,null,"Stable/Final","In progress","2023-11-29",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2025-12-31",null,null,null,"Indicative","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","BG-България","None","2023-08-04","Stable/Final","Completed","2023-09-04",null,null,null,"2023-10-16",null,null,null,"Stable/Final","Completed","2023-11-10",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-01-15",null,null,null,"Stable/Final","Completed",null,null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","CY-Κύπρος","Granted","2023-05-22","Stable/Final","Completed","2023-10-01",null,null,null,"2025-03-10",null,null,null,"Stable/Final","In progress","2025-03-31",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-03-31",null,null,null,"Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","CZ-Česká republika","Granted","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2023-12-05",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-12-05",null,null,null,"Stable/Final ","Completed",null,null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Please refer to \"Air transport\".",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","DK-Danmark","Granted","2024-09-01","Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-06-30",null,null,null,"Indicative","Not started","2024-12-01",null,null,null,"2025-10-01",null,null,null,"Indicative","In progress","2025-10-01",null,null,null,"Indicative","Not started",null,null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","EE-Eesti","Granted","2020-12-31","Stable/Final","Completed","2023-11-01",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2023-10-01",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2025-09-01",null,null,null,"Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,"A derogation request was accordingly submitted by EE on 06.07.2022.",20,"2025-02-10","Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","ES-España","Granted","2022-06-30","Stable/Final","Completed","2023-10-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2024-03-01",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2026-01-01",null,null,null,"Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html","Final date for Migration and the date for Operations depend on the deployment date of EMSWe ","Aligned with the granted derogation date. Although the EO are encouraged to continue filing in the national single maritime window until the EMSWe replaces it.",3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","FI-Suomi/Finland","None","2022-06-30","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-06-30",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"2024-06-30",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","FR-France","Granted","2023-03-31","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2025-04-01",null,null,null,"Stable/Final","In progress","2025-04-01",null,null,null,"Indicative","In progress",null,null,"Updated planning",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","GR-Ελλάδα","Granted","2024-12-31","Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Indicative","Not started","2025-06-30",null,null,null,"2025-06-30",null,null,null,"Indicative","Not started","2025-06-30",null,null,null,"Indicative","Not started",null,null,null,7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","HR-Hrvatska","Granted","2022-03-31","Stable/Final","Completed","2023-01-02",null,null,null,"2023-04-16",null,null,null,"Stable/Final","Completed","2023-04-17",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-04-17",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/",null,null,9,"2025-01-31","Sector for customs system","PNTS@carina.hr",38516102333]
["HU-Magyarország:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","HU-Magyarország","Granted","2023-07-03","Stable/Final","Completed","2023-12-16",null,null,null,"2024-03-29",null,null,null,"Stable/Final","Completed","2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","IE-Éire/Ireland","None","2019-10-04","Stable/Final","Completed","2020-04-30",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2021-10-05",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/",null,null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","IT-Italia","None","2024-03-27","Stable/Final","Completed","2024-05-03",null,null,null,"2024-05-31",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","LT-Lietuva","Granted","2023-05-04","Stable/Final","Completed","2023-06-04",null,null,null,"2023-11-17",null,null,null,"Stable/Final","Completed","2023-10-31",null,null,null,"Stable/Final","Completed","2023-10-31",null,null,null,"2023-10-31",null,null,null,"Stable/Final","Completed","2023-11-19",null,null,null,"Stable/Final","Completed",null,null,null,14,"2025-01-31","Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_TS_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","LU-Luxembourg","Granted","2021-12-14","stable/final","Completed","2022-10-01",null,null,null,"2023-07-01",null,null,null,"Stable/Final","Completed","2023-01-10",null,null,null,"stable/final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-01-10",null,null,null,"Stable/Final","Completed",null,null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","LV-Latvija","None","2017-06-05","Stable/Final","Completed","2017-08-01",null,null,null,"2017-09-22",null,null,null,"Stable/Final","Completed","2017-09-24",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2017-09-25",null,null,null,"Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","As from 24.09.2017 National Temporary Storage System has been updated according to UCC data elements. Additional functionality for movements between TS places (if located in Latvia) has been added on 5.03.2018. The undated version of national TS system according to the latest changes of EUCDM is in production since 15.02.2022. ",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","MT-Malta","Granted","2024-06-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started",null,null,null,3,"2025-02-10"]
["NL-Nederland:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","NL-Nederland","Granted","2023-09-01","Stable/Final","Completed","2024-01-01",null,null,null,"29/02/2025",null,null,null,"Stable/Final","In progress","2024-05-27",null,null,null,"Stable/Final","Completed","2024-08-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-04-01",null,null,null,"Indicative","Not started",null,"NL is considering to combine the migration for traders for TS maritime with ICS2 R3, following a request from Trade",null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","PL-Polska","Granted","2022-07-29","Stable/Final","Completed","2023-09-30",null,null,null,"2025-04-30",null,null,null,"Stable/Final","In progress","2025-04-20",null,null,null,"Stable/Final","Not started","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","2025-05-01",null,null,null,"Stable/Final","Not started",null,null,"Poland was granted a derogation decision.TS functionalities are being developed within national import system and according to its schedule.",0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","PT-Portugal","Granted/Requested","2022-07-31","Stable/Final","Completed","2022-12-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-04-04",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-04-07",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/SiMTeM/Paginas/default.aspx","Derrogation request to second semester 2024","Project 1,2 and 3 are developed in same system;\nTest environment available to EOs;\nEOs started testing;\nOngoing the activities and tests with ports Authorities;\nDevelopment and testing is ongoing.",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","RO-România ","Granted","2025-03-31","Indicative","In progress","2025-03-01",null,null,null,"2025-06-30",null,null,null,"Indicative","In progress","2025-06-30",null,null,null,"Indicative","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Stable/Final","In progress","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn","We are reporting a delay in depolyment of TSD because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 12/31/2023. Also, this system is depending by ICS 2 ","the updated deadlines took into account the derogation decisions",3,"2025-02-10","Customs procedures department","vama@customs.ro",40213155858]
["SE-Sverige:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","SE-Sverige","Granted/Requested","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-08-15",null,null,null,"Indicative","Not started","2025-08-15",null,null,null,"2025-08-15",null,null,null,"Indicative","Not started","2025-08-15",null,null,null,"Indicative","Not started","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html",null,"Concerning the maritime traffic we have asked for a derogation until 15 August 2025 because of the dependencies to EMSW. Since we aim to use MNSW as the external domain there is no need for technical specification nor conformance testing with Trade from our side. We are for the moment analysing the consequences for the customs formalities since the deployment of MNSW In Sweden will be delayed until Q 1 2027.  ",24,"2025-01-27","Control Department","projekt.ava.dtl@tullverket.se",46771520520]
["SI-Slovenija:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","SI-Slovenija","Granted","2023-04-28","Stable/Final","Completed","2023-09-01",null,null,null,"2024-02-28",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","2023-11-30",null,null,null,"2024-02-28",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/","","completed within the deadlines set by the derogation regulation",18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Temporary Storage (TS) - Maritime","UCC Temporary Storage (TS) - Maritime","SK-Slovensko","Granted/Requested","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","N/A",null,null,null,"Indicative","Not applicable",null,null,null,null,null,null,null,null,null,null,"N/A",null,null,null,"Indicative","Not applicable",null,null,null,1,"2025-01-27","Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]
["AT-Österreich:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","AT-Österreich","Granted","2024-10-01","Stable/Final","Completed","2025-02-28",null,null,null,"2025-09-01",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-09-15",null,null,null,"Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/4","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51435"]
["BE-Belgique/België:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","BE-Belgique/België","Granted","N/A","","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable",null,null,null,3,"2025-01-30"]
["BG-България:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","BG-България","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","CY-Κύπρος","Granted","N/A","","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable",null,null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","CZ-Česká republika","Granted","2023-09-01","Stable/Final","Completed","2023-11-01",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-05",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-12-05",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Please refer to \"Air transport\".",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","DK-Danmark","Granted","2024-09-01","Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-06-30",null,null,null,"Indicative","Not started","2024-12-01",null,null,null,"2025-10-01",null,null,null,"Indicative","In progress","2025-10-01",null,null,null,"Indicative","Not started",null,null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","EE-Eesti","Granted","2020-12-31","Stable/Final","Completed","2024-06-03",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2025-09-01",null,null,null,"Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,"A derogation request was accordingly submitted by EE on 06.07.2022.",20,"2025-02-10","Customs Manegement Department","AN-PN-TS-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","ES-España","Granted","2022-06-30","Stable/Final","Completed","2023-10-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2024-03-01",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"2025-12-31",null,null,null,"Indicative","In progress","2026-01-01",null,null,null,"Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","FI-Suomi/Finland","None","2022-06-30","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-06-30",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"2024-06-30",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","FR-France","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","GR-Ελλάδα","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","HR-Hrvatska","Granted","2022-03-31","Stable/Final","Completed","2023-01-02",null,null,null,"2023-04-16",null,null,null,"Stable/Final","Completed","2023-04-17",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-04-17",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/",null,null,9,"2025-01-31","Sector for customs system","PNTS@carina.hr",38516102333]
["HU-Magyarország:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","HU-Magyarország","Granted","2023-07-03","Stable/Final","Completed","2023-12-16",null,null,null,"2024-03-29",null,null,null,"Stable/Final","Completed","2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-04-02",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","IE-Éire/Ireland","None","2019-10-04","Stable/Final","Completed","2020-04-30",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2021-10-05",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/",null,null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","IT-Italia","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","LT-Lietuva","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,14,"2025-01-31","Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_TS_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","LU-Luxembourg","Granted",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","LV-Latvija","None","2017-06-05","Stable/Final","Completed","2017-08-01",null,null,null,"2017-09-22",null,null,null,"Stable/Final","Completed","2017-09-24",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2017-09-25",null,null,null,"Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","As from 24.09.2017 National Temporary Storage System has been updated according to UCC data elements. Additional functionality for movements between TS places (if located in Latvia) has been added on 5.03.2018. The undated version of national TS system according to the latest changes of EUCDM is in production since 15.02.2022. ",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","MT-Malta","Granted","2024-06-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started",null,null,null,3,"2025-02-10"]
["NL-Nederland:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","NL-Nederland","Granted","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable",null,null,null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","PL-Polska","Granted","2022-07-29","Stable/Final","Completed","2023-09-30",null,null,null,"2025-04-30",null,null,null,"Stable/Final","In progress","2025-04-20",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-05-01",null,null,null,"Stable/Final","Not started",null,null,"Poland was granted a derogation decision.TS functionalities are being developed within national import system and according to its schedule.",0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","PT-Portugal","Granted/Requested",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","RO-România ","Granted","2025-03-31","Indicative","In progress","2025-03-01",null,null,null,"2025-06-30",null,null,null,"Indicative","In progress","2025-06-30",null,null,null,"Indicative","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Stable/Final","In progress","https://www.customs.ro/e-customs/sistemul-national-de-import/sistemul-informatic-tsd-pn","We are reporting a delay in depolyment of TSD because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 12/31/2023. Also, this system is depending by ICS 2 ","the updated deadlines took into account the derogation decisions",3,"2025-02-10","Customs procedures department","vama@customs.ro",40213155858]
["SE-Sverige:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","SE-Sverige","Granted/Requested",null,null,null,null,null,null,null,null,null,null,null,null,null,"N/A",null,null,null,null,"Not applicable","N/A",null,null,null,null,null,null,null,null,"Not applicable","N/A",null,null,null,null,"Not applicable","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/presentationnotificationforgoodsandtemporarystoragedeclarations.4.21f3dd0d183a9e9ca643952.html","Customs declarations of goods delivered by road will be considered as temporary storage declarations. Transit declarations in NCTS will be considered as temporary storage declarations, which means that a separate temporary storage declaration will not be required for goods in transit nor in the road traffic.",null,24,"2025-01-27","Control Department","projekt.ava.dtl@tullverket.se",46771520520]
["SI-Slovenija:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","SI-Slovenija","Granted","2023-04-28","Stable/Final","Completed","2023-09-01",null,null,null,"2024-02-28",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","2023-11-30",null,null,null,"2024-02-28",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/",null,null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Temporary Storage (TS) - Road and rail transport","UCC Temporary Storage (TS) - Road and rail transport","SK-Slovensko","Granted/Requested","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","N/A",null,null,null,"Indicative","Not applicable",null,null,null,null,null,null,null,null,null,null,"N/A",null,null,null,"Indicative","Not applicable",null,null,null,1,"2025-01-27","Customs division (MB)","cis@financnasprava.sk","00421 2 48273216"]
["AT-Österreich:UCC National Import Systems upgrade","UCC National Import Systems upgrade","AT-Österreich","Granted","2024-10-01","Stable/Final","Completed","2025-02-28",null,null,null,"2025-09-01",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-09-15",null,null,null,"Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/5","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51436"]
["BE-Belgique/België:UCC National Import Systems upgrade","UCC National Import Systems upgrade","BE-Belgique/België","Granted","2021-11-01","Stable/Final","Completed","2023-07-01",null,null,null,"2024-06-05",null,null,null,"Stable/Final","In progress","2024-08-28",null,null,null,"Indicative","In progress","2024-08-28",null,null,null,"2024-12-13",null,null,null,"Indicative","Not started","2024-12-13",null,null,null,"Indicative","Not started","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC National Import Systems upgrade","UCC National Import Systems upgrade","BG-България","None","2023-08-04","Stable/Final","Completed","2023-09-04",null,null,null,"2023-10-16",null,null,null,"Stable/Final","Completed","2023-11-10",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-01-15",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/","In relation to the update of the new Annex B the new import national system became operational on 15.01.2024.",null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC National Import Systems upgrade","UCC National Import Systems upgrade","CY-Κύπρος","Granted","2023-05-22","Stable/Final","Completed","2023-10-01",null,null,null,"2025-03-10",null,null,null,"Stable/Final","In progress","2025-03-31",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-03-31",null,null,null,"Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,"Derogation was granted.",8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC National Import Systems upgrade","UCC National Import Systems upgrade","CZ-Česká republika","Granted","2024-06-30","Stable/Final","Completed","2025-07-01",null,null,null,"2025-12-14",null,null,null,"Indicative","Not started","2025-12-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-12-15",null,null,null,"Indicative","Not started",null,null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC National Import Systems upgrade","UCC National Import Systems upgrade","DE-Deutschland","None","2020-10-09","Stable/Final","Completed","2021-05-01",null,null,null,"2022-10-14",null,null,null,"Stable/Final","Completed","2021-03-06",null,null,null,"Stable/Final","Completed","2021-05-01",null,null,null,"2022-10-14",null,null,null,"Stable/Final","Completed","2022-10-31",null,null,null,"Stable/Final","Completed","https://www.zoll.de/","This project is implemented in the major release of the national IT-ATLAS (Release 9.1) to ensure that all data requirements from Annex B are covered, especially to provide the information required by Surveillance 3. Please note, that the datamodel is not in line with EU-CDM (FMS) as implemented in CCI. Therefore the national import system will be replaced by CCI being the basis for the new and modernized import application.",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC National Import Systems upgrade","UCC National Import Systems upgrade","DK-Danmark","Granted","2024-09-01","Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-06-30",null,null,null,"Indicative","Not started","2024-12-01",null,null,null,"2025-10-01",null,null,null,"Indicative","In progress","2025-10-01",null,null,null,"Indicative","Not started","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC National Import Systems upgrade","UCC National Import Systems upgrade","EE-Eesti","None","2020-09-30","Stable/Final","Completed","2020-12-01",null,null,null,"2021-06-30",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"Stable/Final","Completed","2021-06-30",null,null,null,"2021-07-01",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,20,"2025-02-10","Customs Manegement Department","Impulss-EE@emta.ee","    00 372 8800 814"]
["ES-España:UCC National Import Systems upgrade","UCC National Import Systems upgrade","ES-España","Granted","2022-03-14","Stable/Final","Completed","2023-05-16",null,null,null,"2025-10-13",null,null,null,"Stable/Final","In progress","2023-09-05",null,null,null,"Stable/Final","Completed","2023-09-05",null,null,null,"2025-10-13",null,null,null,"Indicative","In progress","2025-10-14",null,null,null,"Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,3,"2025-02-06","Helpdesk Gestión Aduanera","H1.info@correo.aeat.es"]
["FI-Suomi/Finland:UCC National Import Systems upgrade","UCC National Import Systems upgrade","FI-Suomi/Finland","None","2019-06-30","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2019-12-31",null,null,null,"Stable/Final","Completed","2019-12-31",null,null,null,"2022-12-31",null,null,null,"Stable/Final","Completed","2022-12-31",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Import2_1/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC National Import Systems upgrade","UCC National Import Systems upgrade","FR-France","Granted","2022-03-31","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-11-30",null,null,null,"Stable/Final","Completed","2024-11-30",null,null,null,"2025-05-31",null,null,null,"Stable/Final","In progress","2025-05-31",null,null,null,"Stable/Final","In progress","https://www.douane.gouv.fr/services-aide/edi","The technical specifications are published since February, 2022 and are regularly  with new information.\nThe project Surveillance 3 follow the same calendar deployment with a deployement at 07/11/2024. The conformance for Surveillance is planned during Q3 and Q4 2024",null,2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC National Import Systems upgrade","UCC National Import Systems upgrade","GR-Ελλάδα","Granted","2024-12-31","Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Indicative","Not started","2025-06-30",null,null,null,"2025-06-30",null,null,null,"Indicative","Not started","2025-06-30",null,null,null,"Indicative","Not started","https://www.aade.gr/customs","OUR CURRENT NATIONAL IMPORT SYSTEM WILL BE UPGRADED IN ORIDER TO SEND SURVEILLANCE DATA IN UCC FORMAT. IT WILL BE PUT IN PRODUCTION ON Q2 2024","derogation request",7,"2024-06-28",null,"IMPORT_NPM@AADE.GR"]
["HR-Hrvatska:UCC National Import Systems upgrade","UCC National Import Systems upgrade","HR-Hrvatska","None","2021-12-31","Stable/Final","Completed","2022-09-01",null,null,null,"2022-12-31",null,null,null,"Stable/Final","Completed","2023-01-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-01-01",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/",null,null,9,"2025-01-31","Sector for customs system","hrais3@carina.hr",38516102333]
["HU-Magyarország:UCC National Import Systems upgrade","UCC National Import Systems upgrade","HU-Magyarország","Granted","2022-07-31","Stable/Final","Completed","2023-07-01",null,null,null,"2023-09-17",null,null,null,"Stable/Final","Completed","2023-10-12",null,null,null,"Stable/Final","Completed","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","2023-11-01",null,null,null,"Stable/Final","Completed","https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D","In order to have a smooth transition we envisage to have a period (one week), during which both import systems (i.e. our current import system based on the UCC-TDA and the new import system based on Annex B UCC-DA/IA) would run in production in parallel (the new National Import System would be used in this period only by a few designated/volunteering economic operators).","The developments are in progress.",1,"2025-01-31","NTCA IT Institute","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC National Import Systems upgrade","UCC National Import Systems upgrade","IE-Éire/Ireland","None","2023-06-23","Stable/Final","Completed","2025-06-03",null,null,null,"2026-01-19",null,null,null,"Stable/Final","Not started","2026-01-20",null,null,null,"Stable/Final","Not started","2026-01-20",null,null,null,"2026-04-20",null,null,null,"Stable/Final","Not started","2026-04-21",null,null,null,"Stable/Final","Not started","https://www.revenue.ie/","Upgrade of our UCC compliant system to align with Revised Annex B in Q1 2026",null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC National Import Systems upgrade","UCC National Import Systems upgrade","IT-Italia","None","2019-12-02","Stable/Final","Completed","2020-06-30",null,null,null,"2021-06-30",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"2022-06-08",null,null,null,"Stable/Final","Completed","2022-11-30",null,null,null,"Stable/Final","Completed","https://www.adm.gov.it/portale/dogane/operatore/ecustoms-aida/progetti-aida",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC National Import Systems upgrade","UCC National Import Systems upgrade","LT-Lietuva","Granted","2023-08-15","Stable/Final","Completed","2023-08-15",null,null,null,"2024-02-09",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2024-03-11",null,null,null,"Stable/Final","Completed",null,null,null,14,"2025-01-31","Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_IMP_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC National Import Systems upgrade","UCC National Import Systems upgrade","LU-Luxembourg","Granted","2022-01-03","Stable/Final","Completed","2022-10-01",null,null,null,"2023-04-29",null,null,null,"Stable/Final","Completed","2023-05-02",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-05-02",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/National_Import_System.html",null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC National Import Systems upgrade","UCC National Import Systems upgrade","LV-Latvija","None","N/A","stable/final","Not applicable","2018-05-01",null,null,null,"2018-06-01",null,null,null,"stable/final","Completed","2018-06-03",null,null,null,"stable/final","Completed","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2018-06-04",null,null,null,"stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","As from 3.06.2018 National import system has been aligned with UCC DI/IA Annex B and EUCDM V2.0. New AIS aligned with the latest version of UCC and EUCDM has been implemented on 13.06.2023 and H6 has been transferred to the new AIS by the 8.08.2023. ",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC National Import Systems upgrade","UCC National Import Systems upgrade","MT-Malta","Granted","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/",null,null,3,"2025-02-10"]
["NL-Nederland:UCC National Import Systems upgrade","UCC National Import Systems upgrade","NL-Nederland","Granted","2021-06-22","Stable/Final","Completed","2022-02-01",null,null,null,"2022-12-31",null,null,null,"Stable/Final","Completed","2022-04-01",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","https://www.nhdouane.nl/","The transition period has formally ended, but not all traders are fully migrated yet. ",null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC National Import Systems upgrade","UCC National Import Systems upgrade","PL-Polska","Granted","2022-07-29","Stable/Final","Completed","2023-09-30",null,null,null,"2025-04-30",null,null,null,"Stable/Final","In progress","2025-04-20",null,null,null,"Stable/Final","Not started","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","2025-05-01",null,null,null,"Stable/Final","Not started",null,null,null,0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC National Import Systems upgrade","UCC National Import Systems upgrade","PT-Portugal","Granted/Requested","2022-07-01","Stable/Final","Completed","2022-12-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-04-04",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-04-07",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/STADA_Importacao_CAU/Pages/default.aspx","Derrogation request to second semester 2024"," Projects 4, 6, 8 and 9 are developed in same system;\nTest environment available to EOs;\nOngoing the activities and tests with EOs who have started testing;\nDevelopment and testing is ongoing for Webforms and Webservices.",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC National Import Systems upgrade","UCC National Import Systems upgrade","RO-România ","Granted","2025-03-31","Indicative","In progress","2024-12-18",null,null,null,"2025-06-30",null,null,null,"Indicative","In progress","2025-06-30",null,null,null,"Indicative","In progress","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Indicative","Not started","https://www.customs.ro/","We are reporting a delay in deployment of NIS because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 31/12/2023 ","the updated deadlines took into account the derogation decisions",3,"2025-02-10","Customs procedures department","vama@customs.ro",40213155858]
["SE-Sverige:UCC National Import Systems upgrade","UCC National Import Systems upgrade","SE-Sverige","Granted","2021-09-15","Stable/Final","Completed","2021-12-01",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2022-03-15",null,null,null,"Stable/Final","Completed","2022-03-15",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/importinggoods/customsdeclarationsforimports.4.21f3dd0d183a9e9ca643689.html","Concerning the declaration for Customs warehousing procedure we will perform an update from the \"current\" Annex B to the \"new\" Annex B.",null,24,"2025-01-27","Control Department","projekt.import@tullverket.se",46771520520]
["SI-Slovenija:UCC National Import Systems upgrade","UCC National Import Systems upgrade","SI-Slovenija","None","2019-07-01","Stable/Final","Completed","2021-04-01",null,null,null,"2021-10-01",null,null,null,"Stable/Final","Completed","2022-01-01",null,null,null,"Stable/Final","Completed","2022-01-01",null,null,null,"2022-01-01",null,null,null,"Stable/Final","Completed","2022-01-01",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/",null,null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC National Import Systems upgrade","UCC National Import Systems upgrade","SK-Slovensko","Requested","2025-01-31","Indicative","Not started","2025-05-01",null,null,null,"2025-09-30",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"2025-09-30",null,null,null,"Indicative","Not started","2025-10-01",null,null,null,"Indicative","Not started",null,null,"Request for derogation sent on 2nd of October 2023 ",1,"2025-01-27","Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]
["AT-Österreich:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","AT-Österreich","None","2020-12-31","Stable/Final","Completed","2024-06-10",null,null,null,"2024-12-16",null,null,null,"Stable/Final","Completed","2025-01-26",null,null,null,"Stable/Final","Completed","2025-01-26",null,null,null,"2025-05-31",null,null,null,"Stable/Final",null,"2025-06-01",null,null,null,"Indicative",null,"https://www.bmf.gv.at/themen/zoll/ACCS/aes.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/6","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51437"]
["BE-Belgique/België:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","BE-Belgique/België","None","2021-09-01","Stable/Final","Completed","2023-06-01",null,null,null,"2023-09-01",null,null,null,"Stable/Final","Completed","2024-06-19",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","BG-България","None","2022-08-31","Stable/Final","Completed","2023-07-24",null,null,null,"2023-08-11",null,null,null,"Stable/Final","Completed","2023-08-28",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-08-29",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/",null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","CY-Κύπρος","None","2023-08-01","Stable/Final","Completed","2023-09-18",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-12-18",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-12-18",null,null,null,"Stable/Final","Completed","https://www.mof.gov.cy/mof/customs/customs.nsf/ced12_gr/ced12_gr?OpenDocument",null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","CZ-Česká republika","None","2021-10-21","Stable/Final","Completed","2023-01-02",null,null,null,"2023-09-30",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","https://www.celnisprava.cz/cz/clo/e-customs/ncts/Stranky/dokumentace-pro-vyrobce-SW-UCC-NCTS.aspx","In CZ \"big bang\". All economic operators started at the same date. ",null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","DE-Deutschland","None","2020-10-09","Stable/Final","Completed","2021-04-19",null,null,null,"2023-10-29",null,null,null,"Stable/Final","Completed","2021-03-06",null,null,null,"Stable/Final","Completed","2021-04-19",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-12-01",null,null,null,"Stable/Final","Completed","https://www.zoll.de/","This component is implemented in line with the project \"UCC AES (Component 1) Transeuropean AES\"",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","DK-Danmark","None","2022-08-01","Stable/Final","Completed","2023-03-01",null,null,null,"2023-07-14",null,null,null,"Stable/Final","Completed","2023-07-29",null,null,null,"Stable/Final","Completed","2023-07-29",null,null,null,"2024-05-31",null,null,null,"Stable/Final","Completed","2024-05-31",null,null,null,"Stable/Final","Completed","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","EE-Eesti","None","2022-03-31","Stable/Final","Completed","2023-03-01",null,null,null,"2023-09-01",null,null,null,"Stable/Final","Completed","2023-09-30",null,null,null,"Stable/Final","Completed","2023-09-30",null,null,null,"2023-09-30",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,20,"2025-02-10","Customs Manegement Department","AES-NPM-EE@emta.ee","    00 372 8800 814"]
["ES-España:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","ES-España","None","2021-04-15","Stable/Final","Completed","2021-11-10",null,null,null,"2023-05-08",null,null,null,"Stable/Final","Completed","2022-10-18",null,null,null,"Stable/Final","Completed","2022-10-18",null,null,null,"2023-05-08",null,null,null,"Stable/Final","Completed","2023-05-09",null,null,null,"Stable/Final","Completed","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","FI-Suomi/Finland","Requested","2023-06-30","Stable/Final","Completed","2023-06-30",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Completed","2024-11-05",null,null,null,"Stable/Final","In progress","2024-10-05",null,null,null,"2024-11-05",null,null,null,"Stable/Final","Completed","2024-11-05",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Export/en/index.html","The derogation paper has been sent for end date Q2/2024. Unfortunately we have to postpone the date until Q4/2024.  We have devided implementation into two phases. Phase 1  contains normal export, sp, simplifications, centralized clearance and EMCS integration.  Phase 2 contains exit functionalities and integration to EMSWe.  Phase 2 will be deployed Q2/2025. Phase 1 will be found in line for step 1 and phase 2 in line for step 3. Thus the line for step 2 will be empty.",null,17,"2025-01-27"]
["FR-France:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","FR-France","None","2025-04-30","Indicative","In progress","2025-03-31",null,null,null,"2025-09-30",null,null,null,"Indicative","Not started","2025-10-30",null,null,null,"Indicative","Not started","2025-10-30",null,null,null,"2025-12-31",null,null,null,"Indicative","Not started","2025-12-31",null,null,null,"Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report",null,2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","GR-Ελλάδα","None","2024-09-30","Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-12-31",null,null,null,"Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-12-16",null,null,null,"Stable/Final","Not started","https://www.aade.gr/customs",null,null,7,"2024-06-28",null,"AES_NPM@AADE.GR"]
["HR-Hrvatska:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","HR-Hrvatska","None","2021-12-31","Stable/Final","Completed","2022-10-01",null,null,null,"2022-12-31",null,null,null,"Stable/Final","Completed","2023-01-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-01-01",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/","Depending on the development of the national import customs clearance system and the budget",null,9,"2025-01-31","Sector for customs system","AES@carina.hr",38516102333]
["HU-Magyarország:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","HU-Magyarország","None","2023-04-03","Stable/Final","Completed","2024-05-02",null,null,null,"2025-02-11",null,null,null,"Indicative","In progress","2025-02-12",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-02-12",null,null,null,"Indicative","Not started","https://openkkk.nav.gov.hu/Megosztott dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FE%2DV%C3%81M%20specifik%C3%A1ci%C3%B3k%2FAES&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D","The developments will be implemented within the framework of AES",null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","IE-Éire/Ireland","None","2022-01-28","Stable/Final","Completed","2022-07-31",null,null,null,"2023-03-30",null,null,null,"Stable/Final","Completed","2023-03-21",null,null,null,"Stable/Final","Completed","2023-03-21",null,null,null,"2023-05-21",null,null,null,"Stable/Final","Completed","2023-05-21",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/",null,null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","IT-Italia","None","2021-02-15","Stable/Final","Completed","2022-02-01",null,null,null,"2023-05-07",null,null,null,"Stable/Final","Completed","2023-06-08",null,null,null,"Stable/Final","Completed","2023-06-08",null,null,null,"2024-12-01",null,null,null,"Stable/Final","Completed","2024-12-02",null,null,null,"Stable/Final","Completed","https://www.adm.gov.it/portale/dogane/operatore/ecustoms-aida/progetti-aida",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","LT-Lietuva","None","2023-05-04","Stable/Final","Completed","2023-06-04",null,null,null,"2023-12-01",null,null,null,"Stable/Final","Completed","2023-12-03",null,null,null,"Stable/Final","Completed","2023-12-03",null,null,null,"2023-12-03",null,null,null,"Stable/Final","Completed","2023-12-03",null,null,null,"Stable/Final","Completed","https://lrmuitine.lt/web/guest/591",null,null,14,"2025-01-31","Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_SP_C1_EXP_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","LU-Luxembourg","None","2023-07-01","Stable/Final","Completed","2024-02-01",null,null,null,"2024-09-30",null,null,null,"Stable/Final","Completed","2024-07-08",null,null,null,"Stable/Final","Completed","2024-07-08",null,null,null,"2024-12-01",null,null,null,"Stable/Final","Completed","2024-12-02",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS.html",null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","LV-Latvija","None","N/A","stable/final","Not applicable","2023-07-10",null,null,null,"2023-09-30",null,null,null,"stable/final","Completed","2023-10-10",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2023-10-10",null,null,null,"Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Along with AES",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","MT-Malta","None","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-06-02",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/","Due to the small amount of movements that Maltese Economic Operators (EOs) have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a Graphic User Interface (GUI) where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.",null,3,"2025-02-10"]
["NL-Nederland:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","NL-Nederland","None","2021-06-22","Stable/Final","Completed","2022-02-01",null,null,null,"2022-12-31",null,null,null,"Stable/Final","Completed","2022-04-01",null,null,null,"Stable/Final","Completed","2023-05-08",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-11-30",null,null,null,"Stable/Final","Completed","https://www.nhdouane.nl/","The transition period has formally ended, but not all traders are fully migrated yet.",null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","PL-Polska","None","2020-10-23","Stable/Final","Completed","2020-11-23",null,null,null,"2021-05-04",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2022-03-28",null,null,null,"Stable/Final","Completed","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje/","The National (PL) UCC Special Procedures Project as a whole consists of some parts: \n(1) activities carried out within the National Project of UCC Automated Export System (AES) and \n(2) activities carried out within the National Project of UCC Automated Import System (AIS) and also \n(3) activities carried out within the National Project of (a new) System “RPS” concerning management & settlement of the Special Procedures.  \n\nCOMPONENT 1_(Part AES and RPS)\nHere we indicate that part of relevant functionalities regarding export issues connected with UCC Special Procedures is being implemented during the works concerning the Project of System AES – ad(1) and also the Project of System “RPS” – ad(3).\n\nExplanation:\nThe given dates of stages concern the contracts which were completed in 2022 and the selected key functionalities of UCC SP were entered into IT Components 1+2. \nSupplementation of current Components 1+2 with additional required UCC SP functions are being developed in AIS, AES and RPS systems and will be aligned with the new data matrix referred to in Annex B of the UCC-DA/UCC-IA. \nAfter necessary tests these functionalities will become operational in planned dates: 7.2024 for IMP; 12.2024 for EXP.",null,0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.projekt.aes.350000@mf.gov.pl \nsp_pl_project@mf.gov.pl ","48 (22) 694 50 05"]
["PT-Portugal:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","PT-Portugal","Requested","2023-02-22","Stable/Final","Completed","2023-04-01",null,null,null,"2025-05-01",null,null,null,"Indicative","In progress","2025-05-03",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-05-06",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Sistema_exportacao_e_saida/Sistema_Automatico_Exportacao/Paginas/default.aspx","Integrated in AES component 1\nDerrogation request to second semester 2024",null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","RO-România ","None","2024-03-16","Stable/Final","Completed","2023-05-15",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2024-03-16",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"www.revenue.ie","2024-03-16",null,null,null,"Stable/Final","Completed","https://www.customs.ro/e-customs/aes",null,null,3,"2025-02-10","Customs procedures department","vama@customs.ro",40213155858]
["SE-Sverige:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","SE-Sverige","Requested","2022-12-15","Stable/Final","Completed","2024-01-24",null,null,null,"2024-12-02",null,null,null,"Stable/Final","Completed","2024-10-01",null,null,null,"Stable/Final","Completed","2024-10-01",null,null,null,"2024-12-02",null,null,null,"Stable/Final","Completed","2024-12-02",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/exportinggoods.4.422c8052175b1d82769598d.html",null,null,24,"2025-01-27","Control Department","projekt.export@tullverket.se",46771520520]
["SI-Slovenija:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","SI-Slovenija","None","2020-12-18","Stable/Final","Completed","2022-05-03",null,null,null,"2023-05-23",null,null,null,"Stable/Final","Completed","2023-05-24",null,null,null,"Stable/Final","Completed","2023-05-24",null,null,null,"2023-05-24",null,null,null,"Stable/Final","Completed","2023-05-24",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/",null,null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Special Procedures (Component 1) \"National SP EXP\"","UCC Special Procedures (Component 1) \"National SP EXP\"","SK-Slovensko","Requested","2023-02-03","stable/final","Completed","2023-10-25",null,null,null,"2024-10-31",null,null,null,"Stable/Final","Completed","2024-11-01",null,null,null,"Stable/Final","Completed","2024-11-01",null,null,null,"2024-11-01",null,null,null,"Stable/Final","Completed","2024-11-01",null,null,null,"Stable/Final","Completed",null,"SP (Component 1) is developed as a part of AES. ","Request for derogation sent on 2nd of October 2023 ",1,"2025-01-27","Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]
["AT-Österreich:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","AT-Österreich","Granted","2024-10-01","Stable/Final","Completed","2025-02-28",null,null,null,"2025-09-01",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-04-01",null,null,null,"Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/7","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51438"]
["BE-Belgique/België:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","BE-Belgique/België","None","2021-11-01","Stable/Final","Completed","2023-07-01",null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","2024-08-28",null,null,null,"Indicative","In progress",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","BG-България","Granted","2023-08-04","Stable/Final","Completed","2023-09-04",null,null,null,"2023-10-16",null,null,null,"Stable/Final","Completed","2023-11-10",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-01-15",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/",null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","CY-Κύπρος","Granted","2023-05-22","Stable/Final","Completed","2023-10-01",null,null,null,"2025-03-10",null,null,null,"Stable/Final","In progress","2025-03-31",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-03-31",null,null,null,"Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","CZ-Česká republika","Granted","2024-06-30","Stable/Final","Completed","2025-07-01",null,null,null,"2025-12-14",null,null,null,"Indicative","Not started","2025-12-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-12-15",null,null,null,"Indicative","Not started",null,null,"GAN, data mapping",1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","DE-Deutschland","None","2020-10-09","Stable/Final","Completed","2021-05-01",null,null,null,"2022-10-14",null,null,null,"Stable/Final","Completed","2021-03-06",null,null,null,"Stable/Final","Completed","2021-05-01",null,null,null,"2022-10-14",null,null,null,"Stable/Final","Completed","2022-10-31",null,null,null,"Stable/Final","Completed","https://www.zoll.de/","This component is implemented in the major release of the national IT-System ATLAS (Release 9.1) being part of the \"National Import Systems upgrade\".",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","DK-Danmark","Granted","2024-09-01","Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-06-30",null,null,null,"Indicative","Not started","2024-12-01",null,null,null,"2025-10-01",null,null,null,"Indicative","In progress","2025-10-01",null,null,null,"Indicative","Not started","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","EE-Eesti","None","2020-09-30","Stable/Final","Completed","2020-12-01",null,null,null,"2021-06-30",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"Stable/Final","Completed","2021-06-30",null,null,null,"2021-07-01",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,20,"2025-02-10","Customs Manegement Department","Impulss-EE@emta.ee","    00 372 8800 814"]
["ES-España:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","ES-España","Granted","2022-03-14","Stable/Final","Completed","2023-05-16",null,null,null,"2025-10-13",null,null,null,"Stable/Final","In progress","2023-09-05",null,null,null,"Stable/Final","Completed","2023-09-05",null,null,null,"2025-10-13",null,null,null,"Indicative","In progress","2025-10-14",null,null,null,"Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,3,"2025-02-06","Helpdesk Gestión Aduanera","H1.info@correo.aeat.es"]
["FI-Suomi/Finland:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","FI-Suomi/Finland","None","2019-06-30","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2022-12-31",null,null,null,"Stable/Final","Completed","2022-12-31",null,null,null,"2022-12-31",null,null,null,"Stable/Final","Completed","2022-12-31",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Import2_1/en/index.html",null,null,17,"2025-01-27"]
["FR-France:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","FR-France","Granted","2022-03-31","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-11-30",null,null,null,"Stable/Final","Completed","2024-11-30",null,null,null,"2025-05-31",null,null,null,"Stable/Final","In progress","2025-05-31",null,null,null,"Stable/Final","In progress","https://www.douane.gouv.fr/services-aide/edi","The technical specifications are published since February, 2022 and are regularly  with new information.\nProgress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report",null,2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","GR-Ελλάδα","Granted","2025-06-30","Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Indicative","Not started","2025-06-30",null,null,null,"2025-06-30",null,null,null,"Indicative","Not started","2025-06-30",null,null,null,"Indicative","Not started","https://www.aade.gr/customs",null,null,7,"2024-06-28",null,"IMPORT_NPM@AADE.GR"]
["HR-Hrvatska:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","HR-Hrvatska","None","2021-12-31","Stable/Final","Completed","2022-09-01",null,null,null,"2022-12-31",null,null,null,"Stable/Final","Completed","2023-01-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-01-01",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/",null,null,9,"2025-01-31","Sector for customs system","hrais3@carina.hr",38516102333]
["HU-Magyarország:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","HU-Magyarország","Granted","2022-07-31","Stable/Final","Completed","2023-07-01",null,null,null,"2023-09-17",null,null,null,"Stable/Final","Completed","2023-10-12",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-11-01",null,null,null,"Stable/Final","Completed","https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D","The developments will be implemented within the framework of NIS","The developments are in progress.",1,"2025-01-31","NTCA IT Institute","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","IE-Éire/Ireland","None","2019-10-04","Stable/Final","Completed","2020-04-30",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2021-10-05",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/","Will be updated to Revised Annex B in Q1 2026",null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","IT-Italia","None","2019-12-02","Stable/Final","Completed","2020-06-30",null,null,null,"2021-06-30",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"2022-06-08",null,null,null,"Stable/Final","Completed","2022-11-30",null,null,null,"Stable/Final","Completed","https://www.adm.gov.it/portale/dogane/operatore/ecustoms-aida/progetti-aida",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","LT-Lietuva","Granted","2023-08-15","Stable/Final","Completed","2023-08-15",null,null,null,"2024-02-09",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2024-03-11",null,null,null,"Stable/Final","Completed",null,null,null,14,"2025-01-31","Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_SP_C2_IMP_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","LU-Luxembourg","Granted","2022-01-03","Stable/Final","Completed","2022-10-01",null,null,null,"2023-04-29",null,null,null,"Stable/Final","Completed","2023-05-02",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-05-02",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS.html","The go-live of our national import system will  include Special procedures for Import.\n\nNo migration of data - big bang including big bang for traders.",null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","LV-Latvija","None","2017-10-30","stable/final","Completed","2018-05-01",null,null,null,"2018-06-01",null,null,null,"stable/final","https://www.revenue.ie/","2018-06-03",null,null,null,"stable/final","Completed","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2018-06-04",null,null,null,"stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","As from 3.06.2018 National import system has been aligned with UCC DI/IA Annex B and EUCDM V2.0. New national AIS aligned with the latest version of UCC and EUCDM has been implemented on 13.06.2023. ",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","MT-Malta","Granted","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-03-17",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-03-17",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/",null,null,3,"2025-02-10"]
["NL-Nederland:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","NL-Nederland","Granted","2021-06-22","Stable/Final","Completed","2022-02-01",null,null,null,"2022-12-31",null,null,null,"Stable/Final","Completed","2022-04-01",null,null,null,"Stable/Final","Completed","2022-10-01",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","https://www.nhdouane.nl/","The transition period has formally ended, but not all traders are fully migrated yet.",null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","PL-Polska","None","2020-11-16","Stable/Final","Completed","2020-11-23",null,null,null,"2021-05-04",null,null,null,"Stable/Final","Completed","2021-07-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2022-03-28",null,null,null,"Stable/Final","Completed","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje/","\"The National (PL) UCC Special Procedures Project as a whole consists of some parts: \n(1) activities carried out within the National Project of UCC Automated Export System (AES) and \n(2) activities carried out within the National Project of UCC Automated Import System (AIS) and also \n(3) activities carried out within the National Project of (a new) System “RPS” concerning management & settlement of the Special Procedures.  \n\nCOMPONENT 2_(Part AIS and RPS)\nHere we indicate that part of relevant functionalities regarding import issues connected with UCC Special Procedures is being implemented during the works concerning  the Project of System (AIS) – ad(2) and also the Project of System “RPS” – ad(3).\n\nExplanation:\n\nThe given dates of stages concern the contracts which were completed in 2022 and the selected key functionalities of UCC SP were entered into IT Components 1+2. \nSupplementation of current Components 1+2 with additional required UCC SP functions are being developed in AIS, AES and RPS systems and will be aligned with the new data matrix referred to in Annex B of the UCC-DA/UCC-IA. \nAfter necessary tests these functionalities will become operational in planned dates: 7.2024 for IMP; 12.2024 for EXP.\"",null,0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.projekt.ais.350000@mf.gov.pl \nsp_pl_project@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","PT-Portugal","Granted/Requested","2022-07-01","Stable/Final","Completed","2022-12-01",null,null,null,"2025-04-01",null,null,null,"Indicative","In progress","2025-04-04",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-04-07",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/STADA_Importacao_CAU/Pages/default.aspx","Integrated in NIS\nDerrogation request to second semester 2024","Projects 4, 6, 8 and 9 are developed in same system;\nTest environment available to EOs;\nOngoing the activities and tests with EOs who have started testing;\nDevelopment is ongoing for Webforms and Webservices.",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","RO-România ","Granted","2025-03-31","Indicative","In progress","2024-12-18",null,null,null,"2025-06-30",null,null,null,"Indicative","In progress","2025-06-30",null,null,null,"Indicative","In progress","N/A ",null,null,null,"N/A ",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Indicative","Not started","https://www.customs.ro/","We are reporting a delay in deployment of SP IMP because the development of this system is part of a large project in which several systems and applications that interact with each other are being developed/updated and some of them could not be completed by the deadline of 31/12/2023 ","the updated deadlines took into account the derogation decisions",3,"2025-02-10","Customs procedures department","vama@customs.ro",40213155858]
["SE-Sverige:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","SE-Sverige","Granted","2022-06-01","Stable/Final","Completed","2022-11-01",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-02-23",null,null,null,"Stable/Final","Completed","2023-02-23",null,null,null,"2023-12-31",null,null,null,"Stable/Final","Completed","2023-12-31",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/importinggoods.4.422c8052175b1d82769590f.html",null,null,24,"2025-01-27","Control Department","projekt.import@tullverket.se",46771520520]
["SI-Slovenija:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","SI-Slovenija","None","2019-07-01","Stable/Final","Completed","2021-04-01",null,null,null,"2021-10-01",null,null,null,"Stable/Final","Completed","2022-01-01",null,null,null,"Stable/Final","Completed","2022-01-01",null,null,null,"2022-01-01",null,null,null,"Stable/Final","Completed","2022-01-01",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/",null,null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Special Procedures (Component 2) \"National SP IMP\"","UCC Special Procedures (Component 2) \"National SP IMP\"","SK-Slovensko","Requested","2016-01-27","stable/final","Completed","2016-03-15",null,null,null,"2016-06-10",null,null,null,"stable/final","Completed","2016-06-11",null,null,null,"stable/final","Completed","2016-06-10",null,null,null,"2016-06-10",null,null,null,"stable/final","Completed","2016-06-11",null,null,null,"stable/final","Completed",null,"SP (Component 2) was developed as a part of National Import System.Our NIS and thus SP IMP are based on Annex D DA. Our understanding was that full alignment with Annex B DA is considered as fullfilment of the project requirements. However according to our communication with EC, the implementation of Annex D in our NIS is considered as fulfilment for NIS and therefore we can confirm, that SP IMP as a part of NIS, even if not be in line with Annex B DA, is already deployed.",null,1,"2025-01-27","Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]
["AT-Österreich:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","AT-Österreich","None","N/A","Stable/Final","Not applicable","2024-02-08",null,null,null,"2024-03-07",null,null,null,"Stable/Final","Completed","2025-09-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-09-15",null,null,null,"Indicative","Not started",null,null,null,15,"2025-02-12","Federal ministry of finance, division I/8","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51439"]
["BE-Belgique/België:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","BE-Belgique/België","None","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","N/A",null,null,null,"Indicative","Not applicable",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","BG-България","None",null,null,null,"2024-11-09",null,null,null,"2024-11-21",null,null,null,"Stable/Final","Completed","2025-04-14",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-04-14",null,null,null,"Indicative","Not started","https://ep.customs.bg/eportal/","National GUM system (in production as of 07.01.2019) is going to be upgraded in order to implement UCC GUM2 project.\n CT completed with GUM1 component. No CT envisaged with the economic operators.",null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","CY-Κύπρος","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-02",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-02",null,null,null,"Indicative","Not started",null,null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","CZ-Česká republika","None","2024-10-01","Stable/Final","Completed","2024-12-01",null,null,null,"2025-01-01",null,null,null,"Stable/Final","Completed","2025-01-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2025-01-01",null,null,null,"Stable/Final","Completed","https://forms.celnisprava.cz/aforms.php?action=fill&id_form=145","GUM2 will be connected to GUM1 in June 2025",null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-11-15",null,null,null,"Indicative","In progress",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://www.zoll.de/","This project will be implemented as part of the major release of the national IT-System ATLAS (Release 10.2), which will be oprational in parallel to CCI.",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","DK-Danmark","None","2025-04-01","Indicative","Not started","2025-08-01",null,null,null,"2025-09-07",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Not provided",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Indicative","Not started","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","EE-Eesti","None","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-06-09",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-06-02",null,null,null,"Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,20,"2025-02-10","Revenue Department","GUM-NPM-EE@emta.ee","    00 372 8800 814"]
["ES-España:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","ES-España","None","2016-06-30","Stable/Final","Completed","2016-07-01",null,null,null,"2016-08-31",null,null,null,"Stable/Final","Completed","2016-09-01",null,null,null,"Stable/Final","Completed","2016-09-01",null,null,null,"2019-05-01",null,null,null,"Stable/Final","Completed","2019-05-01",null,null,null,"Stable/Final","Completed",null,null,null,3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","FI-Suomi/Finland","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-05-24",null,null,null,"Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-05-24",null,null,null,"Stable/Final","In progress",null,"National GUM goes into production in several phases, NCTS part was deployed on Q4/2024. The final phase (integration to CRS + Import) will be in production Q2/2025",null,17,"2025-01-27"]
["FR-France:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","FR-France","None","2025-06-01","Indicative","In progress","NA",null,null,null,"NA",null,null,null,null,"Not applicable","2025-12-31",null,null,null,"Indicative","Not started","2025-12-31",null,null,null,"2026-03-30",null,null,null,"Indicative","Not started","2026-03-30",null,null,null,"Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report",null,2,"2025-02-04","Office FIN 3 DGDDI","dg-fin3@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","GR-Ελλάδα","None","2025-06-30","Indicative","Not started","2025-12-31",null,null,null,"Indicative",null,null,null,"Indicative","Not started","2026-03-31",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2026-03-31",null,null,null,"Indicative","Not started","https://www.aade.gr/customs","NATIONAL GAURANTEE MANAGEMENT SYSTEM ALREADY IN PRODUCTION - IT WILL BE UPGRADED IN ORDER TO SUPPORT SOME NEW FUNCTIONALITIES",null,7,"2024-06-28","Not appointed yet"]
["HR-Hrvatska:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","HR-Hrvatska","None","03/31/2025","Indicative","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-02",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","https://carina.gov.hr/","Depending on the internal  resources, budget and priorities of development of other systems which have to be iplemented in the next period",null,9,"2025-01-31","Sector for customs system","hrais3@carina.hr",38516102333]
["HU-Magyarország:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","HU-Magyarország","None","2025-03-01","Indicative","Not started","2025-04-01",null,null,null,"2025-05-15",null,null,null,"Indicative","Not started","2025-06-01",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-06-01",null,null,null,"Indicative","Not started","https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D",null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","IE-Éire/Ireland","None","2019-10-04","Stable/Final","Completed","2020-04-30",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"Stable/Final","Completed","2020-11-23",null,null,null,"2021-10-04",null,null,null,"Stable/Final","Completed","2021-10-05",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/","Review undertaken - no requriement for IE to build additional system. ",null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","IT-Italia","None","2024-11-29","Indicative","In progress","2025-04-01",null,null,null,"2025-05-16",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/dogane/operatore/ecustoms-aida/progetti-aida",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","LT-Lietuva","None","2021-11-01","Stable/Final","Completed","2022-03-01",null,null,null,"2022-08-31",null,null,null,"Stable/Final","Completed","2022-11-16",null,null,null,"Stable/Final","Completed","2022-10-17",null,null,null,"2023-03-19",null,null,null,"Stable/Final","Completed","2023-03-20",null,null,null,"Stable/Final","Completed","https://lrmuitine.lt/web/guest/988",null,null,14,"2025-01-31","Tax Administration Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_GUM_C2_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","LU-Luxembourg","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-01",null,null,null,"indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-01",null,null,null,"indicative","Not started",null,"The dates for GUM phase 2 are purely Indicative till now",null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","LV-Latvija","None","N/A","stable/final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2018-06-03",null,null,null,"stable/final","Completed","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2018-06-04",null,null,null,"stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","National guarantee system has been updated along with national import system. Implementation of the interface between national GUM and central GUM component is under analysis. ",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","MT-Malta","None","TBD","Indicative","Not started","TBD",null,null,null,"TBD",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/","Due to the small amount of movements that Maltese EOs have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a GUI where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.",null,3,"2025-02-10"]
["NL-Nederland:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","NL-Nederland","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-01",null,null,null,"Indicative","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-01",null,null,null,"Indicative","Not started","https://www.nhdouane.nl/","GUM2 is the implementation of the national guarantee management system. No conformance tests with EO's or TAXUD needed, therefor the migration (transitional period) for EO's and external communication is not applicable. ",null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","PL-Polska","None","2021-12-31","Stable/Final","Completed","2024-12-01",null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-02",null,null,null,"Indicative","Not started","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje/",null,null,0,"2025-02-05","Ministry of Finance Customs Department","osoz2.admin.ias.350000@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","PT-Portugal","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-04-04",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-04-07",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Pages/default.aspx","There is no Technical Specifications to the external interface.",null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","RO-România ","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Indicative","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Indicative","Not started","https://www.customs.ro/","There is no Tehnical Specification to external communication. Updated together with national import system. ",null,3,"2025-02-10","Guarantee Office","vama@customs.ro",40213155858]
["SE-Sverige:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","SE-Sverige","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2021-04-17",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2021-04-17",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/internationalbusiness/guarantee.4.3e6caad21870dc6781c37fb.html","Dates for technical spec and CT are not applcable since there will be no external domain for the Economic Operator (EO) to the system. There will be a webservice for the EO to check the reference amount. ",null,24,"2025-01-27","Revenue Department","projekt.import@tullverket.se",46771520520]
["SI-Slovenija:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","SI-Slovenija","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-01",null,null,null,"Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-01",null,null,null,"Stable/Final","Not started",null,"Conformance Testing in relation to the connection between GUM 2 and GUM 1 is planned from 01/01/2025 to 20/05/2025. The Conformance Testing on GUM 2 with the traders is not foreseen. ",null,18,"2025-02-05","UP-OZP","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Guarantee Management (Component 2) \"National GUM\"","UCC Guarantee Management (Component 2) \"National GUM\"","SK-Slovensko","None","2025-06-01","indicative","In progress","2025-06-01",null,null,null,"2025-12-01",null,null,null,"indicative","Not started","2026-01-01",null,null,null,"indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2026-01-01",null,null,null,"indicative","Not started",null,null,null,1,"2025-01-27","Customs division (LH)","cis@financnasprava.sk","00421 2 48273232"]
["AT-Österreich:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","AT-Österreich","None","2024-10-01","Stable/Final","In progress","2025-02-28",null,null,null,"2025-11-07",null,null,null,"Indicative","Not started","2025-11-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-11-14",null,null,null,"Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/9","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51440"]
["BE-Belgique/België:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","BE-Belgique/België","None","N/A","","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","N/A",null,null,null,"","Not applicable","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0","Beligum will skip phase 1 and move to phase 2 directly",null,3,"2025-01-30"]
["BG-България:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","BG-България","None","2023-06-26","Stable/Final","Completed","2023-09-04",null,null,null,"2023-10-16",null,null,null,"Stable/Final","Completed","2023-11-10",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-01-15",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/",null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","CY-Κύπρος","None","2023-05-22","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","2025-06-02",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-02",null,null,null,"Stable/Final","Not started","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","CZ-Česká republika","None","2024-06-30","Stable/Final","Completed","2025-07-01",null,null,null,"2025-12-14",null,null,null,"Indicative","Not started","2025-12-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-12-15",null,null,null,"Indicative","Not started","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","DE-Deutschland","None","2024-11-22","Indicative","In progress","2025-09-01",null,null,null,"2026-10-30",null,null,null,"Indicative","In progress","2025-11-15",null,null,null,"Indicative","In progress","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-11-15",null,null,null,"Indicative","In progress","https://www.zoll.de/","This project will be implemented as part of the major release of the national IT-System ATLAS (Release 10.2) as a new trans-European system.\nNote om CT: the duration of this phase depends on the number of EO who will participate and will be extended when needed.\nNote on migration: Migration from phase 1 to phase 2 is not required.\nA first version of the technical specifications are published and will be updated and complemented following the iterative approach of the development.  ",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","DK-Danmark","None","2025-04-01","Indicative","Not started","2025-08-01",null,null,null,"2025-09-07",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Not provided",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Indicative","Not started","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","EE-Eesti","None","2024-04-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-06-09",null,null,null,"Stable/Final","Completed","2024-06-08",null,null,null,"2024-06-09",null,null,null,"Stable/Final","Completed","2024-06-09",null,null,null,"Stable/Final","Completed","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,20,"2025-02-10","Customs Manegement Department","CCI-NPM-EE@emta.ee","    00 372 8800 814"]
["ES-España:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","ES-España","None","2022-03-14","Stable/Final","Completed","2022-07-04",null,null,null,"tbc",null,null,null,"Stable/Final","Completed","2022-09-30",null,null,null,"Stable/Final","Completed","2022-10-03",null,null,null,"2022-10-03",null,null,null,"Stable/Final","Completed","2022-10-03",null,null,null,"Stable/Final","Completed","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,3,"2025-02-06","Helpdesk Gestión Aduanera","H1.info@correo.aeat.es"]
["FI-Suomi/Finland:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","FI-Suomi/Finland","Requested","2024-12-31","Stable/Final","Completed","2025-06-30",null,null,null,null,null,null,null,"Stable/Final","In progress","2025-05-24",null,null,null,"Stable/Final","In progress","2025-05-25",null,null,null,"N/A",null,null,null,"Stable/Final","Not started","2025-05-24",null,null,null,"Stable/Final","Not started",null,"Traders will start to use CCI according to their own needs, hence no end data for migration. Derogation request has been sent.",null,17,"2025-01-27"]
["FR-France:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","FR-France","None","2025-06-30","Indicative","In progress","2026-04-01",null,null,null,"2026-06-30",null,null,null,"Indicative","Not started","2026-06-30",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2026-06-30",null,null,null,"Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report",null,2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","GR-Ελλάδα","None","2024-12-31","Indicative","Not started","2025-03-31",null,null,null,"2025-06-30",null,null,null,"Indicative","Not started","2025-06-30",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Indicative","Not started","https://www.aade.gr/customs","IMPLEMENT PHASE 1 AND 2 ON THE SAME TIME","derogation request",7,"2024-06-28",null,"IMPORT_NPM@AADE.GR"]
["HR-Hrvatska:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","HR-Hrvatska","None","2023-10-31","Stable/Final","Completed","2023-12-01",null,null,null,"2024-09-29",null,null,null,"Stable/Final","Completed","2024-09-30",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-09-30",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/",null,null,9,"2025-01-31","Sector for customs system","hrais3@carina.hr",38516102333]
["HU-Magyarország:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","HU-Magyarország","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D",null,"The replanning of the developments are in progress. Probably NA_HU will request derogation.",1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","IE-Éire/Ireland","None","2023-06-23","Stable/Final","Completed","2025-06-03",null,null,null,"2026-01-19",null,null,null,"Stable/Final","Not started","2026-01-20",null,null,null,"Stable/Final","Not started","2026-01-20",null,null,null,"2026-04-20",null,null,null,"Stable/Final","Not started","2026-04-21",null,null,null,"Stable/Final","Not started","https://www.revenue.ie/","Revised trader specifications issued in June 2024",null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","IT-Italia","None","2023-01-31","Stable/Final","Completed","2024-07-01",null,null,null,"2024-09-13",null,null,null,"Stable/Final","Completed","2024-11-04",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/dogane/operatore/ecustoms-aida/progetti-aida",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","LT-Lietuva","Requested","2023-10-31","Stable/Final","Completed","2024-03-18",null,null,null,"2024-05-28",null,null,null,"Stable/Final","Completed","2024-07-01",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"2024-06-30",null,null,null,"Stable/Final","Completed","2024-07-01",null,null,null,"Stable/Final","Completed","https://lrmuitine.lt/web/guest/591",null,null,14,"2025-01-31","Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_CC_IMP_P1-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","LU-Luxembourg","None","2023-10-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-06-30",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-06-30",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/National_Import_System.html","NA-LU will already implement the P2 messages with the go-live of CCI P1\nNo economic operator available for conformance testing.",null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","LV-Latvija","None","N/A","stable/final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-07-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2024-07-01",null,null,null,"Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","CCI is a part of the new national import system (AIS). GUI is provided, API will be added on later stages if needed (no business case so far).",null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","MT-Malta","None","N/A","Indicative","Not applicable","2024-11-18",null,null,null,"2025-03-14",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/",null,null,3,"2025-02-10"]
["NL-Nederland:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","NL-Nederland","None","2025-02-01","Indicative","Not started","2025-02-01",null,null,null,"2025-05-01",null,null,null,"Indicative","Not started","2025-05-01",null,null,null,"Indicative","Not started","2025-05-01",null,null,null,"2025-11-01",null,null,null,"indicative","Not started","2025-11-01",null,null,null,"Indicative","Not started","https://www.nhdouane.nl/","Impact and planning are at the moment being analysed. An update will be send as soon as the planning is more clear.",null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","PL-Polska","None","2022-07-30","Stable/Final","Completed","2023-06-01",null,null,null,"2024-05-30",null,null,null,"Stable/Final","Completed","2024-07-01",null,null,null,"Stable/Final","Completed","2024-06-30",null,null,null,"2024-07-01",null,null,null,"Stable/Final","Completed","2024-07-01",null,null,null,"Stable/Final","Completed","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje/",null,null,0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","PT-Portugal","Requested","2022-07-01","Stable/Final","Completed","2025-03-01",null,null,null,"2025-06-27",null,null,null,"Indicative","In progress","2025-06-28",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-07-01",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/STADA_Importacao_CAU/Pages/default.aspx","Derrogation request to second semester 2024",null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","RO-România ","None","2024-05-30","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-07-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-07-01",null,null,null,"Stable/Final","Completed","https://www.customs.ro/",null,null,3,"2025-02-10","Customs procedures department","cci.aut@customs.ro",40213155858]
["SE-Sverige:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","SE-Sverige","Requested","2024-12-02","Stable/Final","In progress","2025-03-01",null,null,null,"N/A",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-02",null,null,null,"Indicative","Not started","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/importinggoods/customsdeclarationsforimports/centralisedcustomsclearanceimport.4.26dbb8018fc32e89b7302ef.html","No need for migration since we have no authorisations today.",null,24,"2025-01-27","Control Department","projekt.import@tullverket.se",46771520520]
["SI-Slovenija:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","SI-Slovenija","None","2021-03-01","Stable/Final","Completed","2024-09-01",null,null,null,"2025-03-31",null,null,null,"Indicative","In progress","2025-05-26",null,null,null,"Indicative","Not started","2025-05-30",null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started","https://www.fu.gov.si/carina/poslovanje_z_nami/centralizirano_carinjenje/",null,null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Centralised Clearance for Import (Phase 1)","UCC Centralised Clearance for Import (Phase 1)","SK-Slovensko","Requested","2025-02-15","Indicative","In progress","2025-10-15",null,null,null,"2025-12-31",null,null,null,"Indicative","Not started","2026-01-01",null,null,null,"Indicative","Not started","2026-01-01",null,null,null,"2026-01-01",null,null,null,"Indicative","Not started","2026-01-01",null,null,null,"Indicative","Not started",null,null,"Request for derogation sent on 2nd of October 2023 ",1,"2025-01-27","Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]
["AT-Österreich:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","AT-Österreich","None","2024-10-01","Stable/Final","In progress","2025-02-28",null,null,null,"2025-11-07",null,null,null,"Indicative","Not started","2025-11-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-11-14",null,null,null,"Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ais.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/10","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51441"]
["BE-Belgique/België:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","BE-Belgique/België","None","N/A","Indicative","Not applicable","2025-04-01",null,null,null,"2025-04-01",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","BG-България","None","2024-12-13","Stable/Final","Completed","2025-02-03",null,null,null,"2025-02-28",null,null,null,"Indicative","Not started","2025-04-21",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-04-21",null,null,null,"Indicative","Not started","https://ep.customs.bg/eportal/",null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","CY-Κύπρος","None","2024-11-30","Indicative","Completed","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","2025-06-02",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-02",null,null,null,"Stable/Final","Not started","https://www.mof.gov.cy/mof/customs/customs.nsf/ced12_gr/ced12_gr?OpenDocument",null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","CZ-Česká republika","None","2024-06-30","Stable/Final","Completed","2025-07-01",null,null,null,"2025-12-14",null,null,null,"Indicative","Not started","2025-12-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-12-15",null,null,null,"Indicative","Not started","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx",null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","DE-Deutschland","None","2024-11-22","Indicative","In progress","2025-09-01",null,null,null,"2026-10-30",null,null,null,"Indicative","In progress","2025-11-15",null,null,null,"Indicative","In progress","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-11-15",null,null,null,"Indicative","In progress","https://www.zoll.de/","Please refer to CCI-Phase 1.",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","DK-Danmark","None","2025-04-01","Indicative","Not started","2025-08-01",null,null,null,"2025-09-07",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Not provided",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Indicative","Not started","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","EE-Eesti","None","2025-03-31","Stable/Final","In progress","2025-05-05",null,null,null,"2025-05-23",null,null,null,"Stable/Final","Not started","2025-06-02",null,null,null,"Stable/Final","Not started","2025-06-01",null,null,null,"2025-06-02",null,null,null,"Stable/Final","Not started","2025-06-02",null,null,null,"Stable/Final","Not started","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,20,"2025-02-10","Customs Manegement Department","CCI-NPM-EE@emta.ee","    00 372 8800 814"]
["ES-España:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","ES-España","None","2024-06-02","Stable/Final","Completed","2025-03-03",null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,3,"2025-02-06","Helpdesk Gestión Aduanera","H1.info@correo.aeat.es"]
["FI-Suomi/Finland:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","FI-Suomi/Finland","Requested","2024-12-31","Stable/Final","Completed","2025-06-30",null,null,null,null,null,null,null,"Stable/Final","In progress","2025-05-24",null,null,null,"Stable/Final","In progress","2025-05-24",null,null,null,"N/A",null,null,null,"Stable/Final","Not started","2025-05-24",null,null,null,"Stable/Final","Not started",null,"Traders will start to use CCI according to their own needs, hence no end data for migration. Derogation request has been sent.",null,17,"2025-01-27"]
["FR-France:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","FR-France","None","2025-09-30","Indicative","Not started","2026-10-01",null,null,null,"2026-12-31",null,null,null,"Indicative","Not started","2026-12-31",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2026-12-31",null,null,null,"Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report",null,2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-rec@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","GR-Ελλάδα","None","2024-12-31","Indicative","Not started","2025-03-31",null,null,null,"2025-06-30",null,null,null,"Indicative","Not started","2025-06-30",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-30",null,null,null,"Indicative","Not started","https://www.aade.gr/customs","IMPLEMENT PHASE 1 AND 2 ON THE SAME TIME",null,7,"2024-06-28",null,"IMPORT_NPM@AADE.GR"]
["HR-Hrvatska:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","HR-Hrvatska","None","2024-09-30","Stable/Final","Completed","2025-01-22",null,null,null,"2025-02-22",null,null,null,"Stable/Final","In progress","2025-06-02",null,null,null,"Stable/Final","Not started",null,null,null,null,null,null,null,null,null,null,"2025-06-02",null,null,null,"Stable/Final","Not started","https://carina.gov.hr/",null,null,9,"2025-01-31","Sector for customs system","hrais3@carina.hr",38516102333]
["HU-Magyarország:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","HU-Magyarország","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D",null,"The replanning of the developments are in progress. Probably NA_HU will request derogation.",1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","IE-Éire/Ireland","None","2023-06-23","Stable/Final","Completed","2025-06-03",null,null,null,"2026-01-19",null,null,null,"Stable/Final","Not started","2026-01-20",null,null,null,"Stable/Final","Not started","2026-01-20",null,null,null,"2026-04-20",null,null,null,"Stable/Final","Not started","2026-04-21",null,null,null,"Stable/Final","Not started","https://www.revenue.ie/","Revised trader specifications issued in June 2024",null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","IT-Italia","None","TBD","Indicative","Not started","TBD",null,null,null,"TBD",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/dogane/operatore/ecustoms-aida/progetti-aida",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","LT-Lietuva","None","31/07/2025","indicative","Not started","2025-07-01",null,null,null,"2025-11-21",null,null,null,"indicative","Not started","2025-11-25",null,null,null,"indicative","Not started","2025-11-25",null,null,null,"2025-11-25",null,null,null,"indicative","Not started","2025-11-25",null,null,null,"indicative","Not started",null,"The new procurement procedure has been started. The delay will not affect the exchange of information between LT and other Member States nor the exchange and storage of information in other Member States, because LT has not issued any authorisation for CCI and isn’t involved in the use of any CCI authorisation as participating Member State.","There will be a big bang for all economic operators. Posible risk - lack of financial resources.",14,"2025-01-31","Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_CC_IMP_P2-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","LU-Luxembourg","None","2025-01-23","Stable/Final","Completed","TBD",null,null,null,"TBD",null,null,null,null,"Not started","2025-06-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-01",null,null,null,"indicative","Not started",null,"No economic operator yet available for conformance testing.",null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","LV-Latvija","None","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-06-02",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2025-06-02",null,null,null,"indicative","Not started","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas",null,null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","MT-Malta","None","N/A","Indicative","Not applicable","2024-11-27",null,null,null,"2025-05-20",null,null,null,"Indicative","Not started","2025-09-29",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-09-29",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/",null,null,3,"2025-02-10"]
["NL-Nederland:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","NL-Nederland","None","2025-02-01","Indicative","Not started","2025-02-01",null,null,null,"2025-05-01",null,null,null,"Indicative","Not started","2025-05-01",null,null,null,"Indicative","Not started","2025-05-01",null,null,null,"2025-11-01",null,null,null,"indicative","Not started","2025-11-01",null,null,null,"Indicative","Not started","https://www.nhdouane.nl/","Impact and planning are at the moment being analysed. An update will be send as soon as the planning is more clear.",null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","PL-Polska","None","2025-03-01","indicative","Not started","2025-09-01",null,null,null,"2026-01-31",null,null,null,"indicative","Not started","2026-06-01",null,null,null,"indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2026-06-01",null,null,null,"indicative","Not started",null,"UCC CCI Phase 2 -  will be developed uder new contract (tendering in preparation phase)",null,0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.adm.merytoryczna@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","PT-Portugal","None","2025-02-01","Indicative","In progress","2025-09-01",null,null,null,"2025-12-20",null,null,null,"Indicative","In progress","2025-12-21",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-12-23",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/STADA_Importacao_CAU/Pages/default.aspx",null,null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","RO-România ","None","2024-09-30","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-02",null,null,null,"Indicative","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-06-02",null,null,null,"Indicative","In progress","https://www.customs.ro/",null,null,3,"2025-02-10","Customs procedures department","cci.aut@customs.ro",40213155858]
["SE-Sverige:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","SE-Sverige","None","2026-03-01","Indicative","In progress","2026-06-01",null,null,null,"N/A",null,null,null,"Indicative","Not started","2026-09-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"","Not applicable","2026-09-01",null,null,null,"Indicative","Not started","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/importinggoods/customsdeclarationsforimports/centralisedcustomsclearanceimport.4.26dbb8018fc32e89b7302ef.html","No need for migration since we have no authorisations today.",null,24,"2025-01-27","Control Department","projekt.import@tullverket.se",46771520520]
["SI-Slovenija:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","SI-Slovenija","None","2023-10-01","Stable/Final","Completed","2025-02-01",null,null,null,"2025-05-20",null,null,null,"Indicative","Not started","2025-05-26",null,null,null,"Indicative","Not started","2025-05-30",null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","2025-06-02",null,null,null,"Indicative","Not started","https://www.fu.gov.si/carina/poslovanje_z_nami/centralizirano_carinjenje/",null,null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Centralised Clearance for Import (Phase 2)","UCC Centralised Clearance for Import (Phase 2)","SK-Slovensko","Requested","2025-02-15","Indicative","In progress","2025-10-15",null,null,null,"2025-12-31",null,null,null,"Indicative","Not started","2026-01-01",null,null,null,"Indicative","Not started","2026-01-01",null,null,null,"2026-01-01",null,null,null,"Indicative","Not started","2026-01-01",null,null,null,"Indicative","Not started",null,null,null,1,"2025-01-27","Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]
["AT-Österreich:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","AT-Österreich","None","2023-12-01","Stable/Final","Completed","2024-07-01",null,null,null,"2024-09-19",null,null,null,"Stable/Final","Completed","2024-12-02",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-12-01",null,null,null,"Stable/Final","Completed","https://www.bmf.gv.at/themen/zoll/ACCS/ncts5.html","  ","  ",15,"2025-02-12","Federal ministry of finance, division I/11","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51442"]
["BE-Belgique/België:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","BE-Belgique/België","None","2021-09-01","Stable/Final","Completed",null,null,null,null,null,null,null,null,"Indicative","In progress",null,"21/01/2025","31/12/2025",null,"Indicative","In progress","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-05-21",null,null,null,"Stable/Final","Completed","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0","  ","  ",3,"2025-01-30"]
["BG-България:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","BG-България","None","2022-08-31","Stable/Final","Completed","2023-07-24",null,null,null,"2023-08-11",null,null,null,"Stable/Final","Completed","2023-08-28",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-08-28",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/","  ","  ",10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","MASP_BG@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","CY-Κύπρος","None","N/A",null,"Not applicable","N/A","2024-03-18","2024-11-01",null,"N/A","2024-04-19","2024-11-29",null,"Stable/Final","Completed","N/A","2024-04-24","2025-01-20",null,"Stable/Final","Completed","N/A","N/A","N/A",null,"N/A","N/A","N/A",null,null,"Not applicable","N/A","2024-04-24","2025-01-20",null,"Stable/Final","Completed",null,"  ","  ",8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","CZ-Česká republika","None","2021-10-21","Stable/Final","Completed","2022-03-01",null,null,null,"2023-09-30",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","https://www.celnisprava.cz/cz/clo/e-customs/ncts/Stranky/dokumentace-pro-vyrobce-SW-UCC-NCTS.aspx","In CZ will be \"big bang\". All economic operators will start at the same date.   ","  ",1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","DE-Deutschland","None","2020-10-09","Stable/Final","Completed","2021-04-19",null,null,null,"2023-10-29",null,null,null,"Stable/Final","Completed","2021-03-06",null,null,null,"Stable/Final","Completed","2021-04-19",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-10-29",null,null,null,"Stable/Final","Completed","https://www.zoll.de/","This component is implemented in the major release of the national IT-System ATLAS (Release 9.1)  The functionality \"Interface with AES\" is already covered by the national IT-systems ATLAS (Release 9.1) and AES Release 3.0 and the primary requirements are activated on 21.01.2025.","  ",7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","DK-Danmark","None","2022-08-01","Stable/Final","Completed","2023-03-01",null,null,null,"2023-05-22",null,null,null,"Stable/Final","Completed","2023-07-29",null,null,null,"Stable/Final","Completed","2023-07-29",null,null,null,"2024-07-08",null,null,null,"Stable/Final","Completed","2024-07-08",null,null,null,"Stable/Final","Completed","https://www.toldst.dk/","  ","  ",1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","EE-Eesti","None","2022-05-31","Stable/Final","Completed","2023-03-01",null,null,null,"2023-09-01",null,null,null,"Stable/Final","Completed","2023-09-30",null,null,null,"Stable/Final","Completed","2023-09-30",null,null,null,"2023-09-30",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed","https://www.emta.ee/ariklient/e-teenused-koolitused/e-teenuste-kasutamine/teenuste-tehniline-info","  ","  ",20,"2025-02-10","Customs Manegement Department","NCTS-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","ES-España","None","2022-06-30","Stable/Final","Completed","2022-12-19",null,null,null,"2024-03-11",null,null,null,"Stable/Final","Completed","2023-10-03",null,null,null,"Stable/Final","Completed","2023-10-03",null,null,null,"2024-03-11",null,null,null,"Stable/Final","Completed","2024-03-12",null,null,null,"Stable/Final","Completed","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html","  ","  ",3,"2025-02-06","NCTS P5 Information","NCTSP5.info@correo.aeat.es"]
["FI-Suomi/Finland:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","FI-Suomi/Finland","None","2022-03-31","Stable/Final","Completed",null,"2023-06-30","2024-06-30",null,null,"2023-12-31","2024-12-31",null,"Stable/Final","Completed",null,"2023-12-31","2024-10-05",null,"Stable/Final","In progress",null,"2023-12-31","2024-10-05",null,null,"2023-12-31","2024-10-05",null,"Stable/Final","Completed",null,"2023-12-31","2024-10-05",null,"Stable/Final","In progress","https://finnishcustoms-suomentulli.github.io/MIGs/Transit/en/index.html","The first step  contains all except integration to AES, prior decl and reduced dataset decl . Those will be implemented in step 2 which will be deployed in Q4/2024.Progress column indicates step 1.  ","  ",17,"2025-01-27"]
["FR-France:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","FR-France","None","2021-11-01","Stable/Final","Completed","2024-05-01",null,null,null,"2024-10-15",null,null,null,"Stable/Final","Completed","2024-11-23",null,null,null,"Stable/Final","Completed","2024-11-23",null,null,null,"2025-01-22",null,null,null,"Stable/Final","Completed","2025-01-22",null,null,null,"Stable/Final","Completed","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report  ","Updated planning  ",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-transit@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","GR-Ελλάδα","None","2024-08-31","Stable/Final","In progress","2024-07-29","N/A","N/A",null,"2024-11-29","N/A","N/A",null,"Stable/Final","Not started","2024-12-16",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-12-16","N/A","N/A",null,"Stable/Final","Not started","https://www.aade.gr/customs","  ","derogation request  ",7,"2024-06-28",null,"NCTS_NPM@AADE.GR"]
["HR-Hrvatska:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","HR-Hrvatska","None","2022-01-02","Stable/Final","Completed","2023-01-30",null,null,null,"2023-05-31",null,null,null,"Stable/Final","Completed","2023-06-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-06-01",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/","  ","  ",9,"2025-01-31","Sector for customs system","NCTS@carina.hr",38516102333]
["HU-Magyarország:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","HU-Magyarország","None","2024-03-28","Stable/Final","Completed","2024-07-01",null,null,null,"2024-11-15",null,null,null,"Stable/Final","In progress","2025-01-21",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2025-01-21",null,null,null,"Stable/Final","Completed",null,"  ","  ",1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","IE-Éire/Ireland","None","2022-08-19","Stable/Final","Completed",null,"2023-05-26","2024-04-08",null,null,"2025-01-21","2025-06-27",null,"Stable/Final","In progress"," ","2023-11-30","2025-06-30",null,"Stable/Final","In progress"," ","2024-07-01","2025-06-30",null," ","2024-12-31","2025-06-30",null,"Stable/Final","In progress"," ","2025-01-01","2025-06-30",null,"Stable/Final","In progress","https://www.revenue.ie/","  ","  ",17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","IT-Italia","None","2021-02-15","Stable/Final","Completed","2022-02-01",null,null,null,"2023-05-07",null,null,null,"Stable/Final","Completed","2023-11-29",null,null,null,"Stable/Final","Completed","2023-07-13",null,null,null,"2024-12-01",null,null,null,"Stable/Final","Completed","2024-12-01",null,null,null,"Stable/Final","Completed","https://www.adm.gov.it/portale/dogane/operatore/ecustoms-aida/progetti-aida","  ","  ",1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","LT-Lietuva","Requested","2024-02-01","Stable/Final","Completed","2024-08-01",null,null,null,"2024-11-28",null,null,null,"Stable/Final","Completed","2024-02-11",null,null,null,"Stable/Final","Completed","2024-09-01",null,null,null,"2024-11-28",null,null,null,"Stable/Final","Completed","2024-01-12",null,null,null,"Stable/Final","Completed","https://lrmuitine.lt/web/guest/599","There will be a big bang for all economic operators. Single deployment Single deployment","  ",14,"2025-01-31","Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_NCTS_C1-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","LU-Luxembourg","None","2022-02-22","Stable/Final","Completed","2022-09-01",null,null,null,"2024-10-01",null,null,null,"Stable/Final","Completed","2023-05-10",null,null,null,"Stable/Final","Completed","2023-05-23",null,null,null,"2024-12-02",null,null,null,"Stable/Final","Completed","2024-12-02",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/NCTS-phase-5.html","  ","  ",2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","LV-Latvija","None","2021-03-01","Stable/Final","Completed",null,"2023-02-01","2024-08-01",null,null,"2023-11-24","2024-11-30",null,"Stable/Final","Completed",null,"2023-11-27","2024-12-01",null,"Stable/Final","Completed",null,"N/A","N/A",null,null,"N/A","N/A",null,"Stable/Final","Not applicable",null,"2023-11-27","2024-12-01",null,"Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","  Interface with AES and functionality of \"D type\" declaration is implemented in national NCTS5 production environment in 2024 Q4, the development of the national legislation for the use of the functionalities will be completed in Q1 2025","  ",3,"2025-01-27","eCustoms Division of National Customs Board","nctshelpdesk@vid.gov.lv","+371 67120000"]
["MT-Malta:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","MT-Malta","None","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-02-04",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-02-04",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/","Due to the small amount of movements that Maltese EOs have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a GUI where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.  ","  ",3,"2025-02-10"]
["NL-Nederland:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","NL-Nederland","None","2023-12-11","Stable/Final","Completed","2024-03-01",null,null,null,"2024-05-30",null,null,null,"Stable/Final","Completed","2024-10-29",null,null,null,"Indicative","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2024-10-31",null,null,null,"Stable/Final","Completed","https://www.nhdouane.nl/","  The interface between NCTS P5 and AES has not been completed yet","  ",1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","PL-Polska","None","2021-05-31","Stable/Final","Completed","2023-01-16",null,null,null,"2023-12-21",null,null,null,"Stable/Final","Completed","2024-10-31",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-10-31",null,null,null,"Stable/Final","Completed","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje/","RfC.41 implemented  ","  ",0,"2025-02-05","Ministry of Finance Customs Department","ncts.hd@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","PT-Portugal","Requested","2023-01-10","Stable/Final","Completed","2023-03-15",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Completed","2025-01-20",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2025-01-21",null,null,null,"Stable/Final","Completed","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Stada_Transito_CAU/Paginas/default.aspx","  ","  ",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","RO-România ","None","2023-01-06","Stable/Final","Completed","2023-05-15",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-05-15",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-05-17",null,null,null,"Stable/Final","Completed","https://www.customs.ro/","NCTS5 is fully operational   ","  ",3,"2025-02-10","Tranzit office","tranzitcentraloffice@customs.ro",40213155858]
["SE-Sverige:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","SE-Sverige","None","2022-09-01","Stable/Final","Completed","2023-03-10",null,null,null,"2024-01-28",null,null,null,"Stable/Final","Completed","2024-01-28",null,null,null,"Stable/Final","Completed","2024-01-28",null,null,null,"2024-01-28",null,null,null,"Stable/Final","Completed","2024-01-28",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/updateofthenewcomputerisedtransitsystemncts.4.21f3dd0d183a9e9ca643a08.html","  ","  ",24,"2025-01-27","Control Department","projekt.transit@tullverket.se",46771520520]
["SI-Slovenija:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","SI-Slovenija","None","2020-02-15","Stable/Final","Completed","2021-09-01",null,null,null,"2023-01-20",null,null,null,"Stable/Final","Completed","2023-02-22",null,null,null,"Stable/Final","Completed","2023-02-22",null,null,null,"2023-02-22",null,null,null,"Stable/Final","Completed","2023-02-22",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/","A single deployment approach A single deployment approach A single deployment approach","  ",18,"2025-02-05","OUT","sd.fu@gov.si","01 478 3800"]
["SK-Slovensko:UCC NCTS upgrade (Phase 5)","UCC NCTS upgrade (Phase 5)","SK-Slovensko","Requested","2022-12-19","Stable/Final","Completed","2023-10-25",null,null,null,"2024-07-13",null,null,null,"Stable/Final","Completed","2024-07-28",null,null,null,"Stable/Final","Completed","2024-07-28",null,null,null,"2024-07-28",null,null,null,"Stable/Final","Completed","2024-07-28",null,null,null,"Stable/Final","Completed","https://www.financnasprava.sk/sk/elektronicke-sluzby/elektronicka-komunikacia/elektr-komunikacia-clo-emcs/projekty-cku/projekt-nctsp5","  ","Request for derogation sent on 2nd of October 2023   ",1,"2025-01-27","Customs division (IL)","cis@financnasprava.sk","00421-905-418188"]
["AT-Österreich:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","AT-Österreich","None","2024-10-01","Indicative","Completed",null,null,null,null,null,null,null,null,null,null,"2025-05-31",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-05-31",null,null,null,"Indicative","Not started","https://www.bmf.gv.at/themen/zoll/ACCS/ncts5.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/12","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51443"]
["BE-Belgique/België:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","BE-Belgique/België","None","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","N/A",null,null,null,"Indicative","Not applicable",null,null,null,null,null,null,null,null,null,null,"2025-01-09",null,null,null,"Indicative","Not started","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","BG-България","None","2024-10-25","Stable/Final","Completed","2025-01-20",null,null,null,"2025-06-06",null,null,null,"Stable/Final","Not started","2025-06-23",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-06-23",null,null,null,"Indicative","Not started","https://ep.customs.bg/eportal/",null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","CY-Κύπρος","None","N/A",null,"Not applicable","2025-07-01",null,null,null,"2025-08-15",null,null,null,"Stable/Final","Not started","2025-09-01",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-09-01",null,null,null,"Stable/Final","Not started",null,null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","CZ-Česká republika","None","2025-02-28","Stable/Final","In progress","2025-04-01",null,null,null,"2025-08-31",null,null,null,"Stable/Final","Not started","2025-09-01",null,null,null,"Stable/Final","Not started",null,null,null,null,null,null,null,null,null,null,"2025-09-01",null,null,null,"Indicative","Not started",null,null,null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Not applicable, i.e. no impact on EO due to the decision not to make use of the \"combined declaration\" following Art. 130 UCC (NCTS Phase 6).",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","DK-Danmark","None","2025-04-01","Indicative","Not started","2025-08-01",null,null,null,"2025-09-07",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"2025-12-31",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Indicative","Not started","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","EE-Eesti","None","2025-02-28","Stable/Final","In progress","2025-04-28",null,null,null,"2025-08-15",null,null,null,"Stable/Final","Not started","2025-08-16",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-08-16",null,null,null,"Stable/Final","Not started","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele","We have determined that NCTS phase 6 is closely linked to project.\nICS2 Release 3 and hence the project deadlines should be amended accordingly.",null,20,"2025-02-10","Customs Manegement Department","NCTS-NPM-EE@emta.ee","    00 372 8800 814"]
["ES-España:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","ES-España","None","2024-10-03","Indicative","Not started","2025-03-04",null,null,null,"2025-06-03",null,null,null,"Indicative","Not started","2025-06-03",null,null,null,"Indicative","Not started","2025-06-03",null,null,null,"2025-09-01",null,null,null,"Indicative","Not started","2025-09-02",null,null,null,"Indicative","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,3,"2025-02-06","NCTS P5 Information","NCTSP5.info@correo.aeat.es"]
["FI-Suomi/Finland:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","FI-Suomi/Finland","None","2024-12-31","Stable/Final","Completed","2025-06-30",null,null,null,"2025-06-30",null,null,null,"Stable/Final","In progress","2025-05-24",null,null,null,"Stable/Final","In progress","2025-05-24",null,null,null,"N/A",null,null,null,"Stable/Final","Not started","2025-05-24",null,null,null,"Stable/Final","Not started",null,"Deployment as opt-out. Decision for possible opt-in functionalities foreseen on Q2/2025. ",null,17,"2025-01-27"]
["FR-France:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","FR-France","None","2025-03-30","Indicative","Not started","2025-07-01",null,null,null,"2025-09-30",null,null,null,"Indicative","Not started","2025-10-31",null,null,null,"Indicative","Not started","2025-10-31",null,null,null,"2026-01-31",null,null,null,"Indicative","Not started","2026-01-31",null,null,null,"Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report","Updated planning",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-transit@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","GR-Ελλάδα","None","2025-03-31","Indicative","Not started","2025-06-30",null,null,null,"2025-09-30",null,null,null,"Indicative",null,"2025-09-30",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"2025-09-30",null,null,null,"Indicative","Not started","2025-09-30",null,null,null,"Indicative","Not started",null,null,null,7,"2024-06-28",null,"NCTS_NPM@AADE.GR"]
["HR-Hrvatska:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","HR-Hrvatska","None","2025-03-01","Indicative","Not started","2025-04-01",null,null,null,"2025-08-01",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2025-09-01",null,null,null,"Indicative","Not started","https://carina.gov.hr/",null,null,9,"2025-01-31","Sector for customs system","NCTS@carina.hr",38516102333]
["HU-Magyarország:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","HU-Magyarország","None","2025-02-20","Indicative","Not started","2025-07-01",null,null,null,"2025-08-31",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"2025-09-01",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D",null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","IE-Éire/Ireland","None","2025-02-28","Stable/Final","In progress","2025-06-15",null,null,null,"2025-08-31",null,null,null,"Stable/Final","Not started","2025-09-01",null,null,null,"Stable/Final","Not started","2025-09-01",null,null,null,"2025-09-01",null,null,null,"Stable/Final","Not started","2025-09-01",null,null,null,"Stable/Final","Not started","https://www.revenue.ie/",null,null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","IT-Italia","None","2025-04-15","Indicative","In progress",null,null,null,null,null,null,null,null,null,null,"2025-09-01",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/dichiarazioni-transito",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","LT-Lietuva","None","30/01/2025","Stable/Final","Completed","2025-08-02",null,null,null,"2025-08-29",null,null,null,"indicative","Not started","2025-09-01",null,null,null,"indicative","Not started","2025-09-01",null,null,null,"2025-09-01",null,null,null,"indicative","Not started","2025-09-01",null,null,null,"indicative","Not started",null,"There will be a big bang for all economic operators. ",null,14,"2025-01-31","Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_NCTS-C2-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","LU-Luxembourg","None","2025-06-16","Indicative","In progress","TBD",null,null,null,"TBD",null,null,null,null,"Not started","2025-12-01",null,null,null,"indicative","Not started","TBD",null,null,null,"TBD",null,null,null,null,"Not started","2025-12-01",null,null,null,"Indicative","Not started",null,null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","LV-Latvija","None","2025-03-01","Indicative","In progress","2025-06-01",null,null,null,"2025-08-30",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2025-09-01",null,null,null,"Indicative","Not started","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","Medium risk of delay",null,3,"2025-01-27","eCustoms Division of National Customs Board","nctshelpdesk@vid.gov.lv","+371 67120000"]
["MT-Malta:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","MT-Malta","None","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-09-01",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-09-01",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/","Due to the small amount of movements that Maltese EOs have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a GUI where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.",null,3,"2025-02-10"]
["NL-Nederland:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","NL-Nederland","None","N/A","Indicative","Not applicable","2025-01-01",null,null,null,"2025-03-02",null,null,null,"Indicative","Not started","2025-03-03",null,null,null,"Indicative","Not started","2025-03-03",null,null,null,"2025-08-31",null,null,null,"Indicative","Not started","2025-09-01",null,null,null,"Indicative","Not started","https://www.nhdouane.nl/",null,null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","PL-Polska","None","2026-02-02","Indicative","Not started","2026-04-01",null,null,null,"2026-05-29",null,null,null,"Indicative","Not started","2026-06-22",null,null,null,"Indicative","Not started","2026-06-15",null,null,null,"2026-06-19",null,null,null,"Indicative","Not started","2026-06-22",null,null,null,"Indicative","Not started","https://puesc.gov.pl/uslugi/uslugi-sieciowe-informacje-i-specyfikacje/","NCTS-P6 will be developed uder new contract (tendering in preparation phase)",null,0,"2025-02-05","Ministry of Finance Customs Department","ncts.hd@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","PT-Portugal","None","2025-02-01","Indicative","Not started","2025-04-01",null,null,null,"2025-08-30",null,null,null,"Indicative","Not started","2025-08-31",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-09-01",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Stada_Transito_CAU/Paginas/default.aspx",null,null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","RO-România ","None","2022-12-31","Indicative","Not started","2026-03-01",null,null,null,"2026-06-01",null,null,null,"Indicative","Not started","2026-06-01",null,null,null,"Indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2026-06-01",null,null,null,"Indicative","Not started","https://www.customs.ro/","Considering that the entry into production of NCTS phase 5 will take place on May 15, 2024, the implementation date of NCTS phase 6 will be postponed by at least 9 months",null,3,"2025-02-10","Tranzit office","tranzitcentraloffice@customs.ro",40213155858]
["SE-Sverige:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","SE-Sverige","None","2025-01-20","Stable/Final","Completed","2025-03-17",null,null,null,"2025-05-17",null,null,null,"Indicative","Not started","2025-05-17",null,null,null,"Indicative","Not started","2025-05-17",null,null,null,"2025-05-17",null,null,null,"Indicative","Not started","2025-05-17",null,null,null,"Indicative","Not started","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/goodstransportandstorage/updateofthenewcomputerisedtransitsystemncts.4.21f3dd0d183a9e9ca643a08.html","The deployment will be a \"big bang\". We are dependent of the delivarables from our contractor so the date 17th of May can still not be defenitaly confirmed. ",null,24,"2025-01-27","Control Department","projekt.transit@tullverket.se",46771520520]
["SI-Slovenija:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","SI-Slovenija","None","2025-03-01","Stable/Final","In progress","2025-05-01",null,null,null,"2025-07-30",null,null,null,"Stable/Final","Not started","2025-09-01",null,null,null,"Stable/Final","Not started","2025-09-01",null,null,null,"2025-09-01",null,null,null,"Stable/Final","Not started","2025-09-01",null,null,null,"Stable/Final","Not started","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/","Opt-out approch",null,18,"2025-02-05","OUT","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC NCTS upgrade (Phase 6)","UCC NCTS upgrade (Phase 6)","SK-Slovensko","None","2025-03-01","Indicative","In progress","2025-09-01",null,null,null,"2026-02-28",null,null,null,"Indicative","Not started","2026-03-01",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2026-03-01",null,null,null,"Indicative","Not started",null,null,"Project is still in planning phase. Once the NCTSP5 is finished, we will provide specific dates.",1,"2025-01-27","Customs division (IL)","cis@financnasprava.sk","00421-905-418188"]
["AT-Österreich:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","AT-Österreich","None","2020-12-31","Stable/Final","Completed","2024-06-10",null,null,null,"2024-12-16",null,null,null,"Stable/Final","Completed","2025-01-26",null,null,null,"Stable/Final","Completed","2025-01-26",null,null,null,"2025-05-31",null,null,null,"Stable/Final","Not started","2025-06-01",null,null,null,"Indicative","In progress","https://www.bmf.gv.at/themen/zoll/ACCS/aes.html","  ","  ",15,"2025-02-12","Federal ministry of finance, division I/13","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51444"]
["BE-Belgique/België:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","BE-Belgique/België","None","2021-09-01","Stable/Final","Completed","2023-06-23",null,null,null,"2024-04-12",null,null,null,"Stable/Final","Completed","2024-06-23",null,null,null,"Stable/Final","Completed","2024-06-23",null,null,null,"17/12/2024",null,null,null,"Stable/Final","Completed","2024-12-18",null,null,null,"Stable/Final","Completed","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0","  ","  ",3,"2025-01-30"]
["BG-България:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","BG-България","None","2022-08-31","Stable/Final","Completed","2023-07-24",null,null,null,"2023-08-11",null,null,null,"Stable/Final","Completed","2023-08-28",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-08-29",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/","  ","  ",10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","CY-Κύπρος","None","2023-08-01","Stable/Final","Completed","N/A","2023-09-18","N/A","2025-01-06","N/A","2023-11-30","N/A","N/A","Indicative","In progress","N/A","2023-12-18","2024-07-31","2025-01-20","Stable/Final","Completed","N/A","N/A","N/A","N/A","N/A","N/A","N/A","N/A",null,"Not applicable","N/A","2023-12-18","2024-07-31","2025-01-20","Stable/Final","Completed","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument","  ","  ",8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","CZ-Česká republika","None","2021-10-21","Stable/Final","Completed","2023-01-02",null,null,null,"2023-09-30",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","https://www.celnisprava.cz/cz/clo/e-customs/ecs/Stranky/dokumentace-pro-vyrobce-SW-UCC-AES.aspx","In CZ will be \"big bang\". All economic operators will start at the same date.   ","  ",1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","DE-Deutschland","None","2020-10-09","Stable/Final","Completed","2021-04-19",null,null,null,"2023-10-29",null,null,null,"Stable/Final","Completed","2021-03-06",null,null,null,"Stable/Final","Completed","2021-04-19",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-10-29",null,null,null,"Stable/Final","Completed","https://www.zoll.de/","This component is already implemented in the major release of the national Export System (AES Release 3.0)  The functionality \"Interface with EMCS\" was activated on 14.02.2024.The functionalities Centralised Clearance and  \"Interface with NCTS\" are already covered by by the national IT-systems ATLAS (Release 9.1) and AES Release 3.0. CCE was activated on 02.12.20224 and the the primary requirements for the \"Interface with NCTS\" were activated on 21.01.2025.","  ",7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","DK-Danmark","None","2022-08-01","Stable/Final","Completed",null,"2023-03-01","2023-12-06","2023-12-06",null,"2023-07-17","2023-12-12","2023-12-12","Stable/Final","Completed",null,"2023-07-29","2024-02-13","2025-01-21","Stable/Final","Completed",null,"2023-07-29","2024-02-13","2023-07-29",null,"2024-05-31","2024-05-31","2024-05-31","Stable/Final","Completed","2024-05-31",null,null,null,"Stable/Final","Completed","https://www.toldst.dk/","  ","  ",1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","EE-Eesti","None","2022-03-31","Stable/Final","Completed","2023-03-01",null,null,null,"2023-09-01",null,null,null,"Stable/Final","Completed","2023-09-30",null,null,null,"Stable/Final","Completed","2023-09-30",null,null,null,"2023-09-30",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed","https://www.emta.ee/ariklient/e-teenused-koolitused/e-teenuste-kasutamine/teenuste-tehniline-info","  ","  ",20,"2025-02-10","Customs Manegement Department","AES-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","ES-España","None","2021-04-15","Stable/Final","Completed","2021-11-10",null,null,null,"2023-05-08",null,null,null,"Stable/Final","Completed","2022-02-22",null,null,null,"Stable/Final","Completed","2022-10-18",null,null,null,"2023-05-08",null,null,null,"Stable/Final","Completed","2023-05-09",null,null,null,"Stable/Final","Completed",null,"  ","  ",3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","FI-Suomi/Finland","Requested","2023-06-30","Stable/Final","Completed","N/A","2023-06-30","N/A","2025-03-31","N/A","2024-12-31","N/A","2025-06-30","Stable/Final","In progress","N/A","2024-11-05","N/A","2025-05-24","Stable/Final","In progress","N/A","2024-10-04","N/A","2025-05-24","N/A","2024-11-05","N/A","2025-05-24","Stable/Final","Not started","N/A","2024-11-05","N/A","2025-05-24","Stable/Final","Not started","https://finnishcustoms-suomentulli.github.io/MIGs/Export/fi/index.html","The derogation paper has been sent for end date Q2/2024. Unfortunately we have to postpone the date until Q4/2024.  We have devided implementation into two phases. Phase 1  contains normal export, sp, simplifications, centralized clearance and EMCS integration.  Phase 2 contains exit functionalities and integration to EMSWe.  Phase 2 will be deployed Q2/2025. Phase 1 will be found in line for step 1 and phase 2 in line for step 3. Thus the line for step 2 will be empty.  ","  ",17,"2025-01-27"]
["FR-France:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","FR-France","None","2025-04-30","Indicative","In progress",null,"2025-03-31","2025-11-01","2027-04-01",null,"2025-09-30","2025-12-31","2027-09-30","Indicative","Not started",null,"2025-10-30","2026-02-01","2027-09-30","Indicative","Not started",null,"2025-10-30","N/A","2027-09-30",null,"2025-12-31","N/A","2028-03-30","Indicative","Not started",null,"2025-12-31","2025-12-31","2028-03-30","Indicative","Not started","https://www.douane.gouv.fr/services-aide/edi","Deployment of a partial perimeter \nProgress can be consulted via the following link: https://www.douane.gouv.fr/fiche/progress-report  ","Updated planning Updated planning Updated planningUpdated planning",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-delta@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","GR-Ελλάδα","None","2024-08-31","Stable/Final","In progress","2024-07-29",null,null,null,"2024-11-29",null,null,null,"Stable/Final","Not started","2024-12-16",null,null,null,"Stable/Final","Not started","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-12-16",null,null,null,"Stable/Final","Not started","https://www.aade.gr/customs","  ","derogation request  ",7,"2024-06-28",null,"AES_NPM@AADE.GR"]
["HR-Hrvatska:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","HR-Hrvatska","None","2021-12-31","Stable/Final","Completed","2022-10-01",null,null,null,"2023-03-10",null,null,null,"Stable/Final","Completed","2023-05-02",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-05-03",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/","  ","  ",9,"2025-01-31","Sector for customs system","AES@carina.hr",38516102333]
["HU-Magyarország:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","HU-Magyarország","None","2023-04-03","Stable/Final","Completed",null,"2024-05-02","2024-05-02","2025-06-01",null,"2025-02-11","2025-02-11","2025-09-29","Stable/Final","In progress",null,"2025-02-12","2025-02-12","2025-09-30","Indicative","Not started",null,null,null,null,null,null,null,null,null,null,null,"2025-02-12","2025-02-12","2025-09-30","Indicative","Not started","https://openkkk.nav.gov.hu/Megosztott dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FE%2DV%C3%81M%20specifik%C3%A1ci%C3%B3k%2FAES&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D","  ","  The CCE, Re-export notification and the EIDR functionalities won't be ready until 2nd December 2024.",1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","IE-Éire/Ireland","None","2022-01-28","Stable/Final","Completed",null,"2022-07-31","2022-07-31","2024-04-08",null,"2023-03-30","2024-12-01","2025-06-27","Stable/Final","In progress",null,"2023-03-21","2024-02-13","2025-06-30","Stable/Final","In progress",null,"2023-03-21","2024-02-13","2025-06-30",null,"2023-05-21","2024-02-13","2025-06-30","Stable/Final","In progress",null,"2023-05-21","2024-02-13","2025-06-30","Stable/Final","In progress","https://www.revenue.ie/"," Step 1 is complete Step 2 is completeCCE is available but EFBT to be completed","  ",17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","IT-Italia","None","2021-02-15","Stable/Final","Completed",null,"2022-02-01","N/A","2024-09-16",null,"2023-05-07","N/A","2024-11-29","Stable/Final","Completed",null,"2023-11-29","2024-02-13","2024-12-01","Indicative","Completed",null,"2023-03-01","N/A","2024-11-25",null,"2023-05-07","N/A","2024-12-01","Stable/Final","Completed",null,"2023-06-08","N/A","2024-12-01","Stable/Final","Completed","https://www.adm.gov.it/portale/dichiarazioni-export","  ","  ",1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","LT-Lietuva","None","2023-05-04","Stable/Final","Completed",null,"2023-06-04","2023-12-03","2024-03-18",null,"2023-12-01","2023-12-01","2024-08-31","Stable/Final","Completed",null,"2023-12-03","2023-12-03","2024-12-01","Stable/Final","Completed",null,"2023-12-03","2023-12-03","2024-12-01",null,"2023-12-03","2023-12-03","2024-12-01","Stable/Final","Completed",null,"2023-12-03","2023-12-03","2024-12-01","Stable/Final","Completed","https://www.lrmuitine.lt/web/guest/591","There will be a big bang for all economic operators.  ","  ",14,"2025-01-31","Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_AES_C1-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","LU-Luxembourg","None","2023-07-01","Stable/Final","Completed","2024-02-01",null,null,null,"2024-09-30",null,null,null,"Stable/Final","Completed","2024-07-08",null,null,null,"Stable/Final","Completed","2024-07-08",null,null,null,"2024-12-01",null,null,null,"Stable/Final","Completed","2024-12-02",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/aes.html","  ","  ",2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","LV-Latvija","None","N/A","Stable/Final","Not applicable",null,"2023-07-10","N/A","N/A",null,"2023-09-30","N/A","N/A","Stable/Final","Completed",null,"2023-10-10","2024-02-13","2024-12-01","Stable/Final","Completed",null,"N/A","N/A","N/A",null,"N/A","N/A","N/A","Stable/Final","Not applicable",null,"2023-10-10","2024-02-13","2024-12-01","Stable/Final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas"," Full funcionality according to the EU technical specifications including standart and simplified procedures, EXS, REN and Centralised clerance for export has been implemented (GUI) Adjustsments in the interface with EMCS according the the changes in EMCSInterface with NCTS is implemented in national AES production environment in 2024 Q4, the development of the national legislation for the use of the functionality will be completed in Q1 2025","  ",3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","MT-Malta","None","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-06-02",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/","Due to the small amount of movements that Maltese EOs have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a GUI where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.  ","  ",3,"2025-02-10"]
["NL-Nederland:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","NL-Nederland","None","2021-06-22","Stable/Final","Completed",null,"2022-09-20","2024-01-01","2024-08-01",null,"2022-09-21","2024-02-12","2024-12-01","Stable/Final","Completed",null,"2023-05-08","2024-02-13","2024-12-02","Stable/Final","Completed",null,"2023-05-08","N/A","N/A",null,"2023-11-30","N/A","N/A","Stable/Final","Completed",null,"2023-12-01","2024-02-13","2024-12-02","Stable/Final","Completed","https://www.nhdouane.nl/","  CCE and the interface between NCTS P5 and AES have not been completed yet","  ",1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","PL-Polska","None","2021-05-15","Stable/Final","Completed","2023-01-16",null,null,null,"2024-03-15",null,null,null,"Stable/Final","Completed","2024-10-31",null,null,null,"Indicative","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2024-10-31",null,null,null,"Stable/Final","Completed","https://puesc.gov.pl/en/uslugi/eksport","  ","  ",0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.projekt.ias.350000@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","PT-Portugal","Requested","2023-02-22","Stable/Final","Completed","2023-04-01",null,null,null,"2025-05-01",null,null,null,"Indicative","In progress","2025-05-03",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-05-06",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Sistema_exportacao_e_saida/Sistema_Automatico_Exportacao/Paginas/default.aspx","Test environment available to EOs. \nDeployment of core and non core funcionalities in the same date.\nDerrogation request to second semester 2024  ","  ",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","RO-România ","None","2023-01-06","Stable/Final","Completed","2023-05-15",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-05-15",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-03-16",null,null,null,"Stable/Final","Completed","https://www.customs.ro/e-customs/aes","AES system is fully operational   ","  ",3,"2025-02-10","Customs procedures department","ro_ecshd@customs.ro",40213155858]
["SE-Sverige:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","SE-Sverige","Requested","2022-12-15","Stable/Final","Completed","2024-01-24",null,null,null,"2024-12-02",null,null,null,"Stable/Final","Completed","2024-10-01",null,null,null,"Stable/Final","Completed","2024-10-01",null,null,null,"2024-12-02",null,null,null,"Stable/Final","Completed","2024-12-02",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/exportinggoods.4.422c8052175b1d82769598d.html","  ","  ",24,"2025-01-27","Control Department","projekt.export@tullverket.se",46771520520]
["SI-Slovenija:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","SI-Slovenija","None","2020-12-18","Stable/Final","Completed","2022-05-03",null,null,null,"2023-05-23",null,null,null,"Stable/Final","Completed","2023-05-24",null,null,null,"Stable/Final","Completed","2023-05-24",null,null,null,"2023-05-24",null,null,null,"Stable/Final","Completed","2023-05-24",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/","A single deployment approach A single deployment approach A single deployment approachA single deployment approach","  ",18,"2025-02-05","OPU","sd.fu@gov.si","01 478 3800"]
["SK-Slovensko:UCC AES (Component 1) \"Trans-European AES\"","UCC AES (Component 1) \"Trans-European AES\"","SK-Slovensko","Requested","2023-02-03","Stable/Final","Completed","2023-10-25",null,null,null,"2024-10-13",null,null,null,"Stable/Final","Completed","2024-11-01",null,null,null,"Stable/Final","Completed","2024-11-01",null,null,null,"2024-11-01",null,null,null,"Stable/Final","Completed","2024-11-01",null,null,null,"Stable/Final","Completed","https://www.financnasprava.sk/sk/elektronicke-sluzby/elektronicka-komunikacia/elektr-komunikacia-clo-emcs/projekty-cku/projekt-aes","  ","Request for derogation sent on 2nd of October 2023   ",1,"2025-01-27","Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]
["AT-Österreich:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","AT-Österreich","None","2020-12-31","Stable/Final","Completed","2024-06-10",null,null,null,"2024-12-16",null,null,null,"Stable/Final","Completed","2025-01-26",null,null,null,"Stable/Final","Completed","2025-01-26",null,null,null,"2025-05-31",null,null,null,"Stable/Final","Not started","2025-06-01",null,null,null,"Indicative","Completed","https://www.bmf.gv.at/themen/zoll/ACCS/aes.html",null,null,15,"2025-02-12","Federal ministry of finance, division I/14","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51445"]
["BE-Belgique/België:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","BE-Belgique/België","None","2021-09-01","Stable/Final","Completed","2023-06-23",null,null,null,"2024-12-17",null,null,null,"Stable/Final","Completed","2024-06-23",null,null,null,"Stable/Final","Completed","2024-06-23",null,null,null,"17/12/2024",null,null,null,"Stable/Final","Completed","2024-12-18",null,null,null,"Stable/Final","Completed","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,3,"2025-01-30"]
["BG-България:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","BG-България","None","2022-08-31","Stable/Final","Completed","2023-07-24",null,null,null,"2023-08-11",null,null,null,"Stable/Final","Completed","2023-08-28",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-08-29",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/",null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","CY-Κύπρος","None","2023-08-01","Stable/Final","Completed","2023-09-18",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-12-18",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-12-18",null,null,null,"Stable/Final","Completed","https://www.mof.gov.cy/mof/ce/theseas/theseas.nsf/techinfo_en/techinfo_en?OpenDocument",null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","CZ-Česká republika","None","2021-10-21","Stable/Final","Completed","2023-01-02",null,null,null,"2023-09-30",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-10-01",null,null,null,"Stable/Final","Completed","https://www.celnisprava.cz/cz/clo/e-customs/ecs/Stranky/dokumentace-pro-vyrobce-SW-UCC-AES.aspx","In CZ \"big bang\". All economic operators started at the same date. ",null,1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","DE-Deutschland","None","2020-10-09","Stable/Final","Completed","2021-04-19",null,null,null,"2023-10-29",null,null,null,"Stable/Final","Completed","2021-03-06",null,null,null,"Stable/Final","Completed","2021-04-19",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-10-29",null,null,null,"Stable/Final","Completed","https://www.zoll.de/","This component is implemented in line with the project \"UCC AES (Component 1) Transeuropean AES\"",null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","DK-Danmark","None","2022-08-01","Stable/Final","Completed","2023-03-01",null,null,null,"2023-12-12",null,null,null,"Stable/Final","Completed","2024-02-13",null,null,null,"Stable/Final","Completed","2023-07-29",null,null,null,"2024-05-31",null,null,null,"Stable/Final","Completed","2024-05-31",null,null,null,"Stable/Final","Completed","https://www.toldst.dk/",null,null,1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","EE-Eesti","None","2022-03-31","Stable/Final","Completed","2023-03-01",null,null,null,"2023-09-01",null,null,null,"Stable/Final","Completed","2023-09-30",null,null,null,"Stable/Final","Completed","2023-09-30",null,null,null,"2023-09-30",null,null,null,"Stable/Final","Completed","2023-10-01",null,null,null,"Stable/Final","Completed","https://www.emta.ee/ariklient/e-teenused-koolitused/e-teenuste-kasutamine/teenuste-tehniline-info",null,null,20,"2025-02-10","Customs Manegement Department","AES-NPM-EE@emta.ee","    00 372 8800 814"]
["ES-España:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","ES-España","None","2021-04-15","Stable/Final","Completed","2021-11-10",null,null,null,"2023-05-08",null,null,null,"Stable/Final","Completed","2022-10-18",null,null,null,"Stable/Final","Completed","2022-10-18",null,null,null,"2023-05-08",null,null,null,"Stable/Final","Completed","2023-05-09",null,null,null,"Stable/Final","Completed","https://sede.agenciatributaria.gob.es/Sede/aduanas/aduana-electronica/guias-tecnicas.html",null,null,3,"2025-02-06","Helpdesk Gestión Aduanera","helpdeskspain@correo.aeat.es"]
["FI-Suomi/Finland:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","FI-Suomi/Finland","Requested","2023-06-30","Stable/Final","Completed","2024-06-30",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Completed","2024-11-05",null,null,null,"Stable/Final","Completed","2024-10-04",null,null,null,"2024-11-05",null,null,null,"Stable/Final","Completed","2024-11-05",null,null,null,"Stable/Final","Completed","https://finnishcustoms-suomentulli.github.io/MIGs/Export/en/index.html","The derogation paper has been sent for end date Q2/2024. Unfortunately we have to postpone the date until Q4/2024.  We have divided implementation into two phases. Phase 1  contains normal export, sp, simplifications, centralized clearance and EMCS integration.  Phase 2 contains exit functionalities and integration to EMSWe.  Phase 2 will be deployed Q2/2025. Phase 1 will be found in line for step 1 and phase 2 in line for step 3. Thus the line for step 2 will be empty.",null,17,"2025-01-27"]
["FR-France:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","FR-France","None","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","N/A",null,null,null,"Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","N/A",null,null,null,"Indicative","Not applicable","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report","Updated planning",2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-delta@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","GR-Ελλάδα","None","2024-09-30","Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-12-31",null,null,null,"Indicative","Not started","2024-12-31",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Not started","2024-12-16",null,null,null,"Indicative","Not started","https://www.aade.gr/customs",null,null,7,"2024-06-28",null,"AES_NPM@AADE.GR"]
["HR-Hrvatska:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","HR-Hrvatska","None","2022-01-01","Stable/Final","Completed","2022-10-01",null,null,null,"2023-03-10",null,null,null,"Stable/Final","Completed","2023-05-02",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2023-05-02",null,null,null,"Stable/Final","Completed","https://carina.gov.hr/",null,null,9,"2025-01-31","Sector for customs system","AES@carina.hr",38516102333]
["HU-Magyarország:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","HU-Magyarország","None","2023-04-03","Stable/Final","Completed","2024-05-02",null,null,null,"2025-02-11",null,null,null,"Indicative","In progress","2025-02-12",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-02-12",null,null,null,"Indicative","Not started","https://openkkk.nav.gov.hu/Megosztott dokumentumok/Forms/AllItems.aspx?RootFolder=%2FMegosztott%20dokumentumok%2FSpecifik%C3%A1ci%C3%B3k%2FE%2DV%C3%81M%20specifik%C3%A1ci%C3%B3k%2FAES&FolderCTID=0x012000A74CCEA4C7223A438B470FB97E909D83&View=%7BC26B9F09%2DFC44%2D4213%2DA9A4%2D3F54E927FF75%7D",null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","IE-Éire/Ireland","None","2022-01-28","Stable/Final","Completed","2022-07-31",null,null,null,"2023-03-30",null,null,null,"Stable/Final","Completed","2023-03-21",null,null,null,"Stable/Final","Completed","2023-03-21",null,null,null,"2023-05-21",null,null,null,"Stable/Final","Completed","2023-05-21",null,null,null,"Stable/Final","Completed","https://www.revenue.ie/",null,null,17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","IT-Italia","None","2021-02-15","Stable/Final","Completed","2022-02-01",null,null,null,"2023-05-07",null,null,null,"Stable/Final","Completed","2023-11-29",null,null,null,"Stable/Final","Completed","2023-03-01",null,null,null,"2023-05-07",null,null,null,"Stable/Final","Completed","2023-06-08",null,null,null,"Stable/Final","Completed","https://www.adm.gov.it/portale/dichiarazioni-export",null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","LT-Lietuva","None","2023-05-04","Stable/Final","Completed","2023-06-04",null,null,null,"2023-12-01",null,null,null,"Stable/Final","Completed","2023-12-03",null,null,null,"Stable/Final","Completed","2023-12-03",null,null,null,"2023-12-03",null,null,null,"Stable/Final","Completed","2023-12-03",null,null,null,"Stable/Final","Completed","https://www.lrmuitine.lt/web/guest/591",null,null,14,"2025-01-31","Customs Procedure Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_AES_C2_N-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","LU-Luxembourg","None","2023-07-01","Stable/Final","Completed","2024-02-01",null,null,null,"2024-09-30",null,null,null,"Stable/Final","Completed","2024-07-08",null,null,null,"Stable/Final","Completed","2024-07-08",null,null,null,"2024-12-01",null,null,null,"stable/final","Completed","2024-12-02",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/aes.html",null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","LV-Latvija","None","N/A","stable/final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2023-10-10",null,null,null,"stable/final","Completed","N/A",null,null,null,"N/A",null,null,null,"stable/final","Not applicable","2023-10-10",null,null,null,"stable/final","Completed","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas",null,null,3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","MT-Malta","None","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2025-06-02",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-06-02",null,null,null,"Indicative","Not started","https://www.customs.gov.mt/","Due to the small amount of movements that Maltese EOs have, it is not feasible for the majority of EOs to develop a system-to-system mechanism and therefore a GUI where declarations can be filed suffices for the time being. Nonetheless, Malta will provide such facility at a later stage for those EOs interested in developing a system-to-system mechanism.",null,3,"2025-02-10"]
["NL-Nederland:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","NL-Nederland","None","2021-06-22","Stable/Final","Completed","2022-09-20",null,null,null,"2023-12-01",null,null,null,"Stable/Final","Completed","2023-05-08",null,null,null,"Stable/Final","Completed","2023-05-08",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-12-01",null,null,null,"Stable/Final","Completed","https://www.nhdouane.nl/","CCE and the interface between NCTS P5 and AES have not been completed yet",null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","PL-Polska","None","2021-05-15","Stable/Final","Completed","2023-01-16",null,null,null,"2024-03-15",null,null,null,"Stable/Final","Completed","2024-10-31",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable","2024-10-31",null,null,null,"Stable/Final","Completed","https://puesc.gov.pl/en/uslugi/eksport",null,null,0,"2025-02-05","Ministry of Finance Customs Department","aes.ais.projekt.ias.350000@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","PT-Portugal","Requested","2023-02-22","Stable/Final","Completed","2023-04-01",null,null,null,"2025-05-01",null,null,null,"Indicative","In progress","2025-05-03",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-05-06",null,null,null,"Indicative","Not started","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Sistema_exportacao_e_saida/Sistema_Automatico_Exportacao/Paginas/default.aspx","Test environment available to EOs. \nDeployment of core and non core funcionalities in the same date.",null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","RO-România ","None","2023-01-06","Stable/Final","Completed","2023-05-15",null,null,null,"2023-11-30",null,null,null,"Stable/Final","Completed","2023-05-15",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-03-16",null,null,null,"Stable/Final","Completed","https://www.customs.ro/e-customs/aes","AES system is fully operational ",null,3,"2025-02-10","Customs procedures department","ro_ecshd@customs.ro",40213155858]
["SE-Sverige:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","SE-Sverige","Requested","2022-12-15","Stable/Final","Completed","2024-01-24",null,null,null,"2024-12-02",null,null,null,"Stable/Final","Completed","2024-10-01",null,null,null,"Stable/Final","Completed","2024-10-01",null,null,null,"2024-12-02",null,null,null,"Stable/Final","Completed","2024-12-02",null,null,null,"Stable/Final","Completed","https://www.tullverket.se/en/startpage/business/infocus/futurecustomsprocedures/exportinggoods.4.422c8052175b1d82769598d.html"," According to our plan we will have a phased implementation and we will deploy EIDR the 1 October 2025 and the re export notification and exit summary declaration at the end of 2025. ",null,24,"2025-01-27","Control Department","projekt.export@tullverket.se",46771520520]
["SI-Slovenija:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","SI-Slovenija","None","2020-12-18","Stable/Final","Completed","2022-05-03",null,null,null,"2023-05-23",null,null,null,"Stable/Final","Completed","2023-05-24",null,null,null,"Stable/Final","Completed","2023-05-24",null,null,null,"2023-05-24",null,null,null,"Stable/Final","Completed","2023-05-24",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/",null,null,18,"2025-02-05","OPU","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC AES (Component 2) \"National Export Systems upgrade\"","UCC AES (Component 2) \"National Export Systems upgrade\"","SK-Slovensko","Requested","2023-02-03","stable/final","Completed","2023-10-25",null,null,null,"2024-10-13",null,null,null,"Stable/Final","Completed","2024-11-01",null,null,null,"Stable/Final","Completed","2024-11-01",null,null,null,"2024-11-01",null,null,null,"Stable/Final","Completed","2024-11-01",null,null,null,"Stable/Final","Completed","https://www.financnasprava.sk/sk/elektronicke-sluzby/elektronicka-komunikacia/elektr-komunikacia-clo-emcs/projekty-cku/projekt-aes",null,"Request for derogation sent on 2nd of October 2023 ",1,"2025-01-27","Customs division (MG)","cis@financnasprava.sk","00421-905-706222"]
["AT-Österreich:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","AT-Österreich","None","2022-04-01","Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-06-03",null,null,null,"Indicative","Completed","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress","https://www.bmf.gv.at/themen/zoll/ACCS/ics2-import-control-system.html","In Austria there is only air traffic. For other modes of transport Austria acts only as an involved member state (IMS)  ","None  ",15,"2025-02-12","Federal ministry of finance, division I/15","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51446"]
["BE-Belgique/België:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","BE-Belgique/België","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-06-03",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2025-09-01",null,null,null,"Stable/Final","In progress","2025-09-01",null,null,null,"Stable/Final","In progress","https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0","  ","  ",3,"2025-01-30"]
["BG-България:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","BG-България","None","2022-03-28","Stable/Final","Completed","2024-02-19",null,null,null,"2024-02-20",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-06-03",null,null,null,"Stable/Final","Completed","https://ep.customs.bg/eportal/","COMMISSION IMPLEMENTING DECISION (EU) o2023/2879 f 15.12.2023 establishing the Work Programme relating to the development and deployment for the electronic systems provided for in the Union Customs Code  ","  ",10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","CY-Κύπρος","None","2023-09-15","Stable/Final","Completed","N/A","2024-05-06","2024-05-06","N/A","N/A","2024-11-30","2025-03-26",null,"Stable/Final","In progress","N/A","2024-06-03","2024-06-03","N/A","Stable/Final","Completed","N/A","2024-06-03","2024-06-03","N/A","N/A","2024-12-04","2025-04-01",null,"Stable/Final","In progress","N/A","2024-12-04","2025-04-01","N/A","Stable/Final","In progress",null,"  ","  ",8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","CZ-Česká republika","None","N/A","Stable/Final","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Stable/Final","Not applicable","2024-06-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-06-01",null,null,null,"Stable/Final","Completed","https://celnisprava.gov.cz/cz/clo/e-customs/ics/Stranky/dokumentace-pro-vyrobce-sw.aspx","  ","  ",1,"2025-02-04","Subunit IT EU Systems","NPP.MASP@cs.mfcr.cz","420/261332621"]
["DE-Deutschland:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-06-03","2024-06-03","2024-12-04","2025-04-01","Stable/Final","In progress",null,null,null,null,null,null,null,null,null,null,null,"2024-12-04","2025-04-01","2025-09-01",null,null,null,"The national IT-System ATLAS is conform wiht ICS2-R3 will require no change compared to ICS2-Release 2. All Milestones relating to EO will be published by EU-COM. The Technical Specs for the external communication via STI-ICS2 will be provided by EU-COM. CT between EO and EU-COM will be scheduled individually in co-ordinaton with EU-MS concerned.  The date of Deployment and End of Transition Period are determined by the UCC-Work Programme and indicated for completeness. The date of Deployment and End of Transition Period are determined by the UCC-Work Programme and indicated for completeness.The date of Deployment and End of Transition Period are determined by the UCC-Work Programme and indicated for completeness.","  ",7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","DK-Danmark","None","2023-12-21","Stable/Final","Completed",null,"2023-12-22","2024-12-04","2024-04-01",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress","2024-05-25",null,null,null,"Stable/Final","Completed",null,"2024-06-03","2024-12-04","2025-04-01",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress","2025-09-01",null,null,null,"Indicative","In progress","https://www.toldst.dk/","  ","  ",1,"2025-02-14","Business Development Unit","forretning@toldst.dk"]
["EE-Eesti:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","EE-Eesti","None","2023-06-01","Stable/Final","Completed",null,"2023-11-01","2024-01-02","2024-12-04",null,"2025-04-01","2025-04-01","2025-09-01","Stable/Final","In progress",null,"2024-06-03","2024-06-03","2024-06-03","Stable/Final","Completed",null,"2024-06-03","2024-12-04","2025-04-01",null,"2025-04-01","2025-04-01","2025-09-01","Stable/Final","In progress",null,"2025-04-01","2025-04-01","2025-09-01","Stable/Final","In progress","https://www.emta.ee/ariklient/toll-kaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele","We have determined that NCTS phase 6 is closely linked to project ICS2 Release 3 and hence the project deadlines should be amended accordingly.  ","  ",20,"2025-02-10","Customs Manegement Department","ICS2-NPM-EE@emta.ee","00 372 8800 814"]
["ES-España:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","ES-España","None","2022-03-01","Stable/Final","Completed",null,"2023-12-01","2023-12-01","2023-12-01",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress",null,"2024-06-03","2024-12-04","2025-04-01","Stable/Final","In progress",null,"2024-06-03","2024-12-04","2025-04-01",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","Not started","https://sede.agenciatributaria.gob.es/Sede/aduanas/entrada-salida-mercancias/declaraciones-sumarias-ens.html","ICS2 R3 Deployment window has been increased  ","  ",3,"2025-02-06","Helpdesk ICS","ics.helpdesk@correo.aeat.es"]
["FI-Suomi/Finland:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","FI-Suomi/Finland","None","2022-03-31","Stable/Final","Completed",null,"2024-06-30","2024-06-30","2024-06-30",null,"2024-12-31","2025-03-31","2025-09-30","Stable/Final","In progress","2024-06-30","N/A","N/A","N/A","Stable/Final","Completed",null,"2024-06-03","2024-12-04","2025-04-01",null,"2025-04-01","2025-04-01","2025-09-01","Stable/Final","In progress",null,"2025-04-01","2025-04-01","2025-09-01","Stable/Final","In progress","https://finnishcustoms-suomentulli.github.io/MIGs/Entry2.5/en/index.html","  ","  ",17,"2025-01-27"]
["FR-France:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","FR-France","None","N/A","Stable/Final","Not applicable",null,"N/A",null,"N/A",null,"N/A",null,"N/A","Indicative","Not applicable",null,"2024-06-03",null,"2025-04-01","Stable/Final","In progress",null,"2024-06-03",null,"2025-04-01",null,"2025-04-01",null,"2025-09-30","Indicative","In progress",null,"2025-04-01",null,"2025-09-30","Indicative","In progress","https://www.douane.gouv.fr/services-aide/edi","Progress can be consulted via the following link  :https://www.douane.gouv.fr/fiche/progress-report  "," Updated planning Updated planning",2,"2025-02-04","Office JCF 2 DGDDI","Veille-ics-dg@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","GR-Ελλάδα","None","2023-10-01","Stable/Final","Completed","2023-09-30",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Completed","2024-06-14",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"2024-12-04",null,null,null,"Stable/Final","Completed","2024-06-14",null,null,null,"Stable/Final","Completed","https://www.aade.gr/customs","  ","  ",7,"2024-06-28",null,"ICS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","HR-Hrvatska","Requested","2023-05-01","Stable/Final","Completed","2024-06-03","2024-06-03","2024-06-03","2025-01-28","2025-09-01","2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress","2024-06-30","2024-06-03","2024-06-03","2025-04-01","Stable/Final","In progress","2024-06-30","2024-06-03","2024-06-03","2024-06-03","2025-09-01","2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress","2025-09-01","2024-12-04","2025-04-01","2025-09-01","Indicative","In progress","https://carina.gov.hr/","ICS2 R3 starts 03.06.2024. for maritime. The roll-out of Release 3 will occur in the following way: first maritime carriers will be phasing in (step 1  03. 06. 2024 for MS), then the house level filers (step 2), and then the road and rail carriers (step 3 from 01. 04. 2025 for MS). ICS2 R3 steps 1, 2 are nationally implemented and in full application. Step 3 will be implemented from 01.04.2025. Economic operators will use the transition period for step 2 until 01.04.2025. (maritime house level filers). Economic operators will use the transition period for step 3 until 01.09.2025. Completed (MS and EOs) In progress (MS completed, EO in progres -house level filers) Not started (MS start on 01.04.2025, Eos DW - 01.09.2025)","Derogation for ICS2 R3 (steps 1,2,3)Derogation for ICS2 R3 (steps 1,2,3 in line COMMISSION IMPLEMENTING DECISION (EU) 2023/2879)  ",9,"2025-01-31","Sector for customs system","ICS2@carina.hr",38516102333]
["HU-Magyarország:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","HU-Magyarország","None","2023-11-25","Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2023-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,null,"2024-12-04","2025-04-01","2025-09-01","Indicative","Not started",null,"No development task in connection with the R3 phase. The deployment date provided corresponds to the R2 phase. The system is already available. The carriers concerned with R3 (inland waterways, road and rail carriers) haven’t started to use the system yet.","  ",1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","IE-Éire/Ireland","None","2022-01-28","Stable/Final","Completed",null,"2023-12-01","2023-12-01","2023-12-01",null,"2024-11-30","2025-03-31","2025-07-31","Stable/Final","In progress",null,"2024-06-03","2024-12-04","2025-04-01","Stable/Final","In progress",null,"2024-06-03","2024-12-04","2025-04-01",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress","https://www.revenue.ie/","Link to EU Specs from Revenue Website  RoRo traffic both Accompanied and Un-accompanied will now be in a deployment window of Apr-Sept 2025RoRo traffic both Accompanied and Un-accompanied will now be in a deployment window of Apr-Sept 2025","  ",17,"2025-02-07","eCustoms Development Unit ","UCCITDev@revenue.ie","00353 67 63340"]
["IT-Italia:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","IT-Italia","None","2024-03-27","Stable/Final","Completed",null,"2024-05-03","2024-05-03","N/A",null,"2024-05-31","2024-05-31","N/A","Stable/Final","Completed",null,"2024-06-03","2024-06-03","N/A","Stable/Final","Completed",null,null,null,"N/A",null,null,null,"N/A",null,"Not applicable",null,null,null,"N/A",null,"Not applicable","https://www.adm.gov.it/portale/-/ics2","Technical Specs provided by EU  ","  ",1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","LT-Lietuva","None","2023-07-30","Stable/Final","Completed",null,"2023-10-15","2023-10-15","2023-10-15",null,"2024-11-04","2025-03-01","2025-08-01","Stable/Final","In progress",null,"2024-06-01","2024-06-01","2024-06-01","Stable/Final","Completed",null,"2024-03-01","2024-03-01","2024-03-01",null,"2024-11-04","2025-03-01","2025-08-01","Stable/Final","In progress",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress",null," Web Address for EO is Central ICS2 system  Web Address for EO is Central ICS2 system Web Address for EO is Central ICS2 system ","  ",14,"2025-01-31","Customs Control Organisation Division CUSTOMS DEPARTMENT UNDER THE MINISTRY OF FINANCE OF THE REPUBLIC OF LITHUANIA","UCC_ICS2_R1R2R3-LT@lrmuitine.lt","370 5 236 2302"]
["LU-Luxembourg:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","LU-Luxembourg","None","2024-02-01","Stable/Final","Completed","2024-03-01",null,null,null,"2024-12-31",null,null,null,"Stable/Final","Completed","2024-07-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-07-01",null,null,null,"Stable/Final","Completed","https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/ics2.html","The impact of ICS2R3 very limited for NA-LU with minor adaptions since NA-LU is involved MS. Not applicable since no land nor sea borders with 3rd country  Not applicable since no land nor sea borders with 3rd country Not applicable since no land nor sea borders with 3rd country ","  ",2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","LV-Latvija","None","2022-01-10","Stable/Final","Completed",null,"N/A","N/A","2025-03-03",null,"N/A","N/A","2025-03-28","Indicative","Not started","2023-03-01",null,null,null,"Stable/Final","Completed",null,"2024-07-03","2024-12-04","2025-04-01",null,"2024-12-04","2025-04-01","2025-09-01","Indicative","Not started",null,"2024-12-04","2025-04-01","2025-09-01","Indicative","Not started","https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas","  ","  ",3,"2025-01-27","eCustoms Division of National Customs Board","ecustoms@vid.gov.lv ","+371 67120000"]
["MT-Malta:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","MT-Malta","None","N/A","Indicative","Not applicable","N/A",null,null,null,"N/A",null,null,null,"Indicative","Not applicable",null,"2024-07-15","2024-07-15","2024-07-15","Indicative","In progress",null,null,null,null,null,null,null,null,null,null,null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress","https://customs.gov.mt/electronic-systems/import-control-system-2","  ","  ",3,"2025-02-10"]
["NL-Nederland:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","NL-Nederland","None","2023-09-01","Stable/Final","Completed","2024-03-01",null,null,null,"2024-05-24",null,null,null,"Stable/Final","Completed","2024-05-27",null,null,null,"Stable/Final","Completed",null,"2024-06-03","2024-12-04",null,null,"2024-12-04","2025-04-01",null,"Indicative","In progress",null,"2024-12-04","2025-04-01",null,"Indicative","In progress","https://www.nhdouane.nl/","Technical specs are NA PN TS maritime  ","  ",1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","PL-Polska","None","2022-09-19","Stable/Final","Completed","2023-12-11",null,null,null,"2025-08-31",null,null,null,"Stable/Final","In progress",null,"2024-06-03","2024-12-04","2025-04-01","Stable/Final","In progress","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","Not started","https://puesc.gov.pl/en/puesc","  ","  ",0,"2025-02-05","Ministry of Finance Customs Department","helpdesk.satos@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","PT-Portugal","None","2023-09-01","Stable/Final","Completed","2023-12-15",null,null,null,"2024-05-01",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-06-03",null,null,null,"Stable/Final","Completed","https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/ICS2/Paginas/default.aspx","There is no National Technical Specifications to the external interface.\nNot expetect any delay.  ","  ",7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","RO-România ","None","2022-11-07","Stable/Final","Completed","2024-12-16",null,null,null,"2025-09-01",null,null,null,"Indicative","In progress","2024-12-16",null,null,null,"Stable/Final","Completed",null,"2024-12-16","2024-12-16","2025-04-01",null,"2025-04-01","2025-04-01","2025-09-01","Indicative","In progress","2025-09-01",null,null,null,"Indicative","Not started","https://www.customs.ro/","  ","  ",3,"2025-02-10","Security and Safety Risk Analysis Service","ro.helpdesk.ics2@customs.ro",40216373051]
["SE-Sverige:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","SE-Sverige","None","N/A",null,"Not applicable",null,"N/A","N/A","N/A",null,"N/A","N/A","N/A",null,"Not applicable",null,"2024-06-03","2024-12-04","2025-04-01","Indicative","In progress",null,"2024-06-03","2024-12-04","2025-04-01",null,"2024-12-04","2025-04-01","2025-09-01","Indicative","In progress",null,"2024-12-04","2025-04-01","2025-09-01","Indicative","In progress","https://www.tullverket.se/en/startpage/business/declarationaccordingtotheucc/entrysummarydeclaration.4.422c8052175b1d8276959dc.html"," Dates for technical spec and CT are not applicable since the central ICS/STI will be used.  ","  ",24,"2025-01-27","Intelligence Department","underrattelseavd.npm.ics2@tullverket.se",46771520520]
["SI-Slovenija:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","SI-Slovenija","None","2023-10-01","Stable/Final","Completed","N/A","N/A","N/A","N/A",null,null,null,null,"Stable/Final","Not applicable","2024-06-02",null,null,null,"Stable/Final","Completed","2024-06-02",null,null,null,"2024-06-02",null,null,null,"Stable/Final","Completed","2024-06-03",null,null,null,"Stable/Final","Completed","https://www.fu.gov.si/carina/poslovanje_z_nami/e_carina/","A single deployment approach A single deployment approach A single deployment approachA single deployment approach","  ",18,"2025-02-05","OPU","sd.fu@gov.si","01 478 3800"]
["SK-Slovensko:UCC Import Control System 2 – Release 3","UCC Import Control System 2 – Release 3","SK-Slovensko","None","2023-01-01","Stable/Final","Completed",null,"N/A","N/A","2025-01-01",null,"N/A","N/A","2025-03-31","Indicative","Not started","2024-06-03",null,null,null,"Indicative","Completed",null,"2024-06-03","2024-12-04","2025-04-01",null,"2024-12-04","2025-04-01","2025-09-01","Stable/Final","In progress",null,"2024-12-04","2025-04-01","2025-09-01","Indicative","In progress","https://www.financnasprava.sk/sk/elektronicke-sluzby/elektronicka-komunikacia/elektr-komunikacia-clo-emcs/podavanie-cv-dovoz-vyvoz/elektronicke-colne-konanie","  ","  ",1,"2025-01-27","Customs division (IL)","cis@financnasprava.sk","00421-905-418188"]
["AT-Österreich:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","AT-Österreich","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,15,"2025-02-12","Federal ministry of finance, division I/16","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51447"]
["BE-Belgique/België:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","BE-Belgique/België","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,3,"2025-01-30"]
["BG-България:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","BG-България","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","CY-Κύπρος","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","CZ-Česká republika","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-02-04",null,"NPP.MASP@cs.mfcr.cz"]
["DE-Deutschland:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","DK-Danmark","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-02-14"]
["EE-Eesti:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","EE-Eesti","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,20,"2025-02-10","Customs Manegement Department","PoUS-NPM-EE@emta.ee","    00 372 8800 814"]
["ES-España:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","ES-España","None","2023-01-15","Stable/Final","Completed","2023-04-12",null,null,null,"2024-02-28",null,null,null,"Stable/Final","Completed","2024-01-15",null,null,null,"Stable/Final","Completed","2024-01-15",null,null,null,"2024-02-28",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","https://sede.agenciatributaria.gob.es/Sede/aduanas/estatuto-aduanero-mercancia.html?faqId=e91cc7756ab39710VgnVCM100000dc381e0aRCRD",null,null,3,"2025-02-06","POuS Information","POUS.info@correo.aeat.es"]
["FI-Suomi/Finland:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","FI-Suomi/Finland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,17,"2025-01-27"]
["FR-France:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","FR-France","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-transit@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","GR-Ελλάδα","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,7,"2024-06-28",null,"NCTS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","HR-Hrvatska","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-01-03",null,null,null,"Stable/Final","Completed",null,null,null,9,"2025-01-31","Sector for customs system","pous@carina.hr",38516102333]
["HU-Magyarország:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","HU-Magyarország","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","IE-Éire/Ireland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,17,"2025-02-07"]
["IT-Italia:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","IT-Italia","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","LT-Lietuva","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,14,"2025-01-31"]
["LU-Luxembourg:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","LU-Luxembourg","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","LV-Latvija","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,3,"2025-01-27"]
["MT-Malta:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","MT-Malta","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,3,"2025-02-10"]
["NL-Nederland:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","NL-Nederland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","PL-Polska","None","2023-09-15","Stable/Final","Completed","2023-09-16",null,null,null,"2024-02-29",null,null,null,"Stable/Final","Completed","2024-03-01",null,null,null,"Stable/Final","Completed","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2024-09-15",null,null,null,"Stable/Final","Completed","https://puesc.gov.pl/en/puesc",null,null,0,"2025-02-05","Ministry of Finance Customs Department","Aes.ais.projekt@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","PT-Portugal","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","RO-România ","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,3,"2025-02-10","Tranzit office","tranzitcentraloffice@customs.ro",40213155858]
["SE-Sverige:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","SE-Sverige","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,24,"2025-01-27",null,"ecustoms@tullverket.se"]
["SI-Slovenija:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","SI-Slovenija","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,18,"2025-02-05","OCP","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","SK-Slovensko","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01",null,null,null,"Stable/Final","Completed",null,null,null,1,"2025-01-27"]
["AT-Österreich:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","AT-Österreich","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,15,"2025-02-12","Federal ministry of finance, division I/17","pgm-steuerung-bmf.uzk@extern.bmf.gv.at","0043-1-51448"]
["BE-Belgique/België:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","BE-Belgique/België","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,3,"2025-01-30"]
["BG-България:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","BG-България","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,10,"2025-02-05","National Customs Agency of the Republic of Bulgaria","masp_bg@customs.bg","+359 2 9859 4528"]
["CY-Κύπρος:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","CY-Κύπρος","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,8,"2025-02-10","1) Department of Customs and Excise,\n2) Department of Information Technology Services","helpdesk.cyprus@customs.mof.gov.cy"]
["CZ-Česká republika:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","CZ-Česká republika","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,1,"2025-02-04",null,"NPP.MASP@cs.mfcr.cz"]
["DE-Deutschland:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","DE-Deutschland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,7,"2025-01-31","Central Customs Authority","DVIB23.gzd@zoll.bund.de"," +49 (0) 228 303-0"]
["DK-Danmark:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","DK-Danmark","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,1,"2025-02-14"]
["EE-Eesti:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","EE-Eesti","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,20,"2025-02-10","Customs Manegement Department","PoUS-NPM-EE@emta.ee","    00 372 8800 814"]
["ES-España:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","ES-España","None","2025-02-17","Indicative","In progress","2025-05-16",null,null,null,"2025-08-15",null,null,null,"Indicative","Not started","2025-07-14",null,null,null,"Indicative","Not started","2025-07-14",null,null,null,"2025-08-15",null,null,null,"Indicative","Not started","2025-08-15",null,null,null,"Indicative","Not started",null,null,null,3,"2025-02-06","POuS Information","POUS.info@correo.aeat.es"]
["FI-Suomi/Finland:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","FI-Suomi/Finland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,17,"2025-01-27"]
["FR-France:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","FR-France","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,2,"2025-02-04","Office COMINT 1 DGDDI","dg-comint1-transit@douane.finances.gouv.fr"]
["GR-Ελλάδα:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","GR-Ελλάδα","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,7,"2024-06-28",null,"NCTS_NPM@AADE.GR"]
["HR-Hrvatska:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","HR-Hrvatska","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,9,"2025-01-31","Sector for customs system","pous@carina.hr",38516102333]
["HU-Magyarország:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","HU-Magyarország","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,1,"2025-01-31","NTCA Customs Department","uvk_mp_masp@nav.gov.hu","(+36)-1-456-9556"]
["IE-Éire/Ireland:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","IE-Éire/Ireland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,17,"2025-02-07"]
["IT-Italia:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","IT-Italia","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,1,"2025-02-12","Direzione Organizzazione e trasformazione digitale","dir.odt@adm.gov.it","+39 06 5024 6577"]
["LT-Lietuva:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","LT-Lietuva","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,14,"2025-01-31"]
["LU-Luxembourg:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","LU-Luxembourg","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,2,"2025-01-30","Luxembourg Customs and Excise Agency","it.npm@do.etat.lu"]
["LV-Latvija:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","LV-Latvija","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,3,"2025-01-27"]
["MT-Malta:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","MT-Malta","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,3,"2025-02-10"]
["NL-Nederland:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","NL-Nederland","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,1,"2025-02-10","National Helpdesk Dutch Customs","NHD.apeldoorn@douane.nl","(+31)(0)88 156 6655"]
["PL-Polska:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","PL-Polska","None","N/A",null,"Not applicable","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2027-06-30",null,null,null,"indicative","Not started","N/A",null,null,null,"N/A",null,null,null,null,"Not applicable","2027-06-30",null,null,null,"indicative","Not started","https://puesc.gov.pl/en/puesc","Indicative dates of deployment and operation depend on the preparation of the modified NSW in tfe framowork of EMSWe and  are out of action of Customs Administration.",null,0,"2025-02-05","Ministry of Finance Customs Department","Aes.ais.projekt@mf.gov.pl","48 (22) 694 50 05"]
["PT-Portugal:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","PT-Portugal","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,7,"2025-02-03",null,"dsra@at.gov.pt",351218813890]
["RO-România :UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","RO-România ","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,3,"2025-02-10","Tranzit office","tranzitcentraloffice@customs.ro",40213155858]
["SE-Sverige:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","SE-Sverige","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,24,"2025-01-27",null,"ecustoms@tullverket.se"]
["SI-Slovenija:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","SI-Slovenija","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,18,"2025-02-05","OCP","sd.fu@gov.si"," 01 478 3800 "]
["SK-Slovensko:UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","SK-Slovensko","None",null,null,null,null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,"Indicative","Not started",null,null,null,1,"2025-01-27"]
["COM-UCC Proof of Union Status (PoUS) - Phase 1","UCC Proof of Union Status (PoUS) - Phase 1","COM",null,"2022-03-31",null,"Completed",null,null,null,null,null,null,null,null,null,null,"2024-03-01"]
["COM-UCC Proof of Union Status (PoUS) - Phase 2","UCC Proof of Union Status (PoUS) - Phase 2","COM",null,"2023-06-30",null,"Completed",null,null,null,null,null,null,null,null,null,null,"2025-08-15",null,null,null,null,"Not started"]

{"sheet":"Derogations","index":28,"n_rows":248,"n_cols":5,"rows_kept":248,"cut":false,"hidden":true,"merged":[[0,0,0,4]]}
["UCC Knowledge"]
["Last update date","2024-09-25"]
[]
["Project","MSs","Derogation Status","Source","Comment"]
["UCC National Import Systems upgrade","AT-Österreich","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Road and rail transport","AT-Österreich","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","AT-Österreich","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Aircraft","AT-Österreich","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","AT-Österreich","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","AT-Österreich","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","AT-Österreich","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","AT-Österreich","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","AT-Österreich","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Temporary Storage (TS) - Maritime","AT-Österreich","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","AT-Österreich","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC National Import Systems upgrade","BE-Belgique/België","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Road and rail transport","BE-Belgique/België","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Notification of Arrival (AN) - Aircraft","BE-Belgique/België","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","BE-Belgique/België","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Notification of Arrival (AN) - Maritime","BE-Belgique/België","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Maritime","BE-Belgique/België","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","BE-Belgique/België","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","BE-Belgique/België","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Aircraft","BE-Belgique/België","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","BE-Belgique/België","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","BG-България","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Notification of Arrival (AN) - Aircraft","BG-България","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","BG-България","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Notification of Arrival (AN) - Maritime","BG-България","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC National Import Systems upgrade","CY-Κύπρος","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Road and rail transport","CY-Κύπρος","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Notification of Arrival (AN) - Aircraft","CY-Κύπρος","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","CY-Κύπρος","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","CY-Κύπρος","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","CY-Κύπρος","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","CY-Κύπρος","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","CY-Κύπρος","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","CY-Κύπρος","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","CY-Κύπρος","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","CY-Κύπρος","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","CZ-Česká republika","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC National Import Systems upgrade","CZ-Česká republika","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","CZ-Česká republika","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","CZ-Česká republika","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","CZ-Česká republika","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","CZ-Česká republika","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","CZ-Česká republika","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","CZ-Česká republika","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","CZ-Česká republika","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","CZ-Česká republika","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","CZ-Česká republika","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","DK-Danmark","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC National Import Systems upgrade","DK-Danmark","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","DK-Danmark","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","DK-Danmark","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","DK-Danmark","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","DK-Danmark","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","DK-Danmark","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","DK-Danmark","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","DK-Danmark","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","DK-Danmark","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","DK-Danmark","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","EE-Eesti","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Notification of Arrival (AN) - Aircraft","EE-Eesti","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","EE-Eesti","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Temporary Storage (TS) - Aircraft","EE-Eesti","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","EE-Eesti","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","EE-Eesti","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","EE-Eesti","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","EE-Eesti","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","EE-Eesti","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","ES-España","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC National Import Systems upgrade","ES-España","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","ES-España","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","ES-España","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","ES-España","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","ES-España","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","ES-España","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","ES-España","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","ES-España","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","ES-España","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","ES-España","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC AES (Component 1) \"Trans-European AES\"","FI-Suomi/Finland","Requested","APR Survey","FI requested a derogation, planning a deployment of Export in Q4/2024 and Exit to be deployed in Q2/2025. "]
["UCC AES (Component 2) \"National Export Systems upgrade\"","FI-Suomi/Finland","Requested","APR Survey","FI requested a derogation, planning a deployment of Export in Q4/2024 and Exit to be deployed in Q2/2025. "]
["UCC Centralised Clearance for Import (Phase 1)","FI-Suomi/Finland","Requested","APR Survey","Derogation request to deploy by Q2/2025 as not confident they will be capable of deploying both phase 1 and 2 by June 2025"]
["UCC Centralised Clearance for Import (Phase 2)","FI-Suomi/Finland","Requested","Bilateral Meetings","Derogation request to deploy by Q2/2025 as not confident they will be capable of deploying both phase 1 and 2 by June 2025"]
["UCC Special Procedures (Component 1) \"National SP EXP\"","FI-Suomi/Finland","Requested","Bilateral Meetings","FI requested a derogation, planning a deployment of Export in Q4/2024 and Exit to be deployed in Q2/2025. "]
["UCC Notification of Arrival (AN) - Road and rail transport","FR-France","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC National Import Systems upgrade","FR-France","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","FR-France","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","FR-France","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","FR-France","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","FR-France","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","FR-France","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","FR-France","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","FR-France","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","FR-France","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","FR-France","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","GR-Ελλάδα","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC National Import Systems upgrade","GR-Ελλάδα","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","GR-Ελλάδα","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","GR-Ελλάδα","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","GR-Ελλάδα","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","GR-Ελλάδα","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","GR-Ελλάδα","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","GR-Ελλάδα","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","GR-Ελλάδα","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","GR-Ελλάδα","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","GR-Ελλάδα","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","HR-Hrvatska","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Import Control System 2 – Release 3","HR-Hrvatska","Requested","NPP Notes","Derogation sent for ICS2-R3. "]
["UCC Notification of Arrival (AN) - Aircraft","HR-Hrvatska","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","HR-Hrvatska","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Temporary Storage (TS) - Aircraft","HR-Hrvatska","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","HR-Hrvatska","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","HR-Hrvatska","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","HR-Hrvatska","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","HR-Hrvatska","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","HR-Hrvatska","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","HU-Magyarország","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC National Import Systems upgrade","HU-Magyarország","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","HU-Magyarország","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","HU-Magyarország","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","HU-Magyarország","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","HU-Magyarország","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Presentation Notification (PN) - Road and rail transport","HU-Magyarország","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","HU-Magyarország","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","HU-Magyarország","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","HU-Magyarország","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","HU-Magyarország","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Centralised Clearance for Import (Phase 1)","LT-Lietuva","Requested","NPP Notes","Derogation request as been sent. "]
["UCC National Import Systems upgrade","LT-Lietuva","Granted","APR Survey"]
["UCC NCTS upgrade (Phase 5)","LT-Lietuva","Requested","NPP Notes","Derogation request as been sent. "]
["UCC Special Procedures (Component 2) \"National SP IMP\"","LT-Lietuva","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","LT-Lietuva","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","LT-Lietuva","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","LT-Lietuva","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","LU-Luxembourg","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Road and rail transport","LU-Luxembourg","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC National Import Systems upgrade","LU-Luxembourg","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","LU-Luxembourg","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","LU-Luxembourg","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","LU-Luxembourg","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","LU-Luxembourg","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","LU-Luxembourg","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","LU-Luxembourg","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","LU-Luxembourg","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","LU-Luxembourg","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","MT-Malta","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Road and rail transport","MT-Malta","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC National Import Systems upgrade","MT-Malta","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","MT-Malta","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","MT-Malta","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","MT-Malta","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","MT-Malta","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","MT-Malta","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","MT-Malta","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","MT-Malta","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","MT-Malta","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","NL-Nederland","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Road and rail transport","NL-Nederland","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC National Import Systems upgrade","NL-Nederland","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","NL-Nederland","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","NL-Nederland","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","NL-Nederland","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","NL-Nederland","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","NL-Nederland","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","NL-Nederland","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","NL-Nederland","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","NL-Nederland","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","PL-Polska","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Road and rail transport","PL-Polska","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC National Import Systems upgrade","PL-Polska","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","PL-Polska","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","PL-Polska","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Temporary Storage (TS) - Aircraft","PL-Polska","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","PL-Polska","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","PL-Polska","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","PL-Polska","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","PL-Polska","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","PT-Portugal","Granted/Requested","APR Survey"]
["UCC Presentation Notification (PN) - Road and rail transport","PT-Portugal","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC AES (Component 1) \"Trans-European AES\"","PT-Portugal","Requested","APR Survey"]
["UCC AES (Component 2) \"National Export Systems upgrade\"","PT-Portugal","Requested","APR Survey"]
["UCC Centralised Clearance for Import (Phase 1)","PT-Portugal","Requested","APR Survey"]
["UCC National Import Systems upgrade","PT-Portugal","Granted/Requested","APR Survey"]
["UCC NCTS upgrade (Phase 5)","PT-Portugal","Requested","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","PT-Portugal","Granted/Requested","APR Survey"]
["UCC Presentation Notification (PN) - Aircraft","PT-Portugal","Granted/Requested","APR Survey"]
["UCC Special Procedures (Component 1) \"National SP EXP\"","PT-Portugal","Requested","APR Survey"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","PT-Portugal","Granted/Requested","APR Survey"]
["UCC Temporary Storage (TS) - Aircraft","PT-Portugal","Granted/Requested","APR Survey"]
["UCC Temporary Storage (TS) - Road and rail transport","PT-Portugal","Granted/Requested","APR Survey"]
["UCC Notification of Arrival (AN) - Maritime","PT-Portugal","Granted/Requested","APR Survey"]
["UCC Presentation Notification (PN) - Maritime","PT-Portugal","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","PT-Portugal","Granted/Requested","APR Survey"]
["UCC Notification of Arrival (AN) - Road and rail transport","RO-România ","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Road and rail transport","RO-România ","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC National Import Systems upgrade","RO-România ","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","RO-România ","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","RO-România ","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","RO-România ","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","RO-România ","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","RO-România ","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","RO-România ","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","RO-România ","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","RO-România ","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","SE-Sverige","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Road and rail transport","SE-Sverige","Granted/Requested","APR Survey","Derogation request sent for 15/08/2024 regarding maritime traffic only. "]
["UCC AES (Component 1) \"Trans-European AES\"","SE-Sverige","Requested","NPP Notes","Derogation request sent for 31/12/2024. An additional derogation regarding EIDR was request for 30/06/2025."]
["UCC AES (Component 2) \"National Export Systems upgrade\"","SE-Sverige","Requested","NPP Notes","Derogation request sent for 31/12/2024. An additional derogation regarding EIDR was request for 30/06/2025."]
["UCC Centralised Clearance for Import (Phase 1)","SE-Sverige","Requested","NPP Notes","Derogation request sent for 02/06/2025."]
["UCC National Import Systems upgrade","SE-Sverige","Granted","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","SE-Sverige","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","SE-Sverige","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Special Procedures (Component 1) \"National SP EXP\"","SE-Sverige","Requested","NPP Notes","Derogation request sent for 31/12/2024."]
["UCC Special Procedures (Component 2) \"National SP IMP\"","SE-Sverige","Granted","APR Survey","Derogation until 31 December 2023, deployment before 01/07/2024"]
["UCC Temporary Storage (TS) - Aircraft","SE-Sverige","Granted/Requested","APR Survey","Derogation request sent for 31/12/2024."]
["UCC Temporary Storage (TS) - Road and rail transport","SE-Sverige","Granted/Requested","APR Survey","Derogation request sent for 15/08/2024 regarding maritime traffic only. "]
["UCC Notification of Arrival (AN) - Maritime","SE-Sverige","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","SE-Sverige","Granted/Requested","APR Survey","Derogation request sent for 15/08/2024 regarding maritime traffic only. "]
["UCC Temporary Storage (TS) - Maritime","SE-Sverige","Granted/Requested","APR Survey","Derogation request sent for 15/08/2024 regarding maritime traffic only. "]
["UCC Notification of Arrival (AN) - Road and rail transport","SI-Slovenija","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Road and rail transport","SI-Slovenija","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Aircraft","SI-Slovenija","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","SI-Slovenija","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Temporary Storage (TS) - Aircraft","SI-Slovenija","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Road and rail transport","SI-Slovenija","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Maritime","SI-Slovenija","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Maritime","SI-Slovenija","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Temporary Storage (TS) - Maritime","SI-Slovenija","Granted","APR Survey","Derogation granted for AN, PN, and TS for other modes of transport until 29 February 2024"]
["UCC Notification of Arrival (AN) - Road and rail transport","SK-Slovensko","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Road and rail transport","SK-Slovensko","Granted/Requested","APR Survey"]
["UCC AES (Component 1) \"Trans-European AES\"","SK-Slovensko","Requested","NPP Notes","Second derogation request sent. "]
["UCC AES (Component 2) \"National Export Systems upgrade\"","SK-Slovensko","Requested","NPP Notes","Second derogation request sent. "]
["UCC Centralised Clearance for Import (Phase 1)","SK-Slovensko","Requested","APR Survey"]
["UCC Centralised Clearance for Import (Phase 2)","SK-Slovensko","Requested","APR Survey"]
["UCC National Import Systems upgrade","SK-Slovensko","Requested","APR Survey"]
["UCC NCTS upgrade (Phase 5)","SK-Slovensko","Requested","APR Survey"]
["UCC Notification of Arrival (AN) - Aircraft","SK-Slovensko","Granted","APR Survey","Derogation granted for AN, PN, and TS for air transport until 31 December 2023"]
["UCC Presentation Notification (PN) - Aircraft","SK-Slovensko","Granted/Requested","APR Survey"]
["UCC Special Procedures (Component 1) \"National SP EXP\"","SK-Slovensko","Requested","APR Survey"]
["UCC Special Procedures (Component 2) \"National SP IMP\"","SK-Slovensko","Requested","APR Survey"]
["UCC Temporary Storage (TS) - Aircraft","SK-Slovensko","Granted/Requested","APR Survey"]
["UCC Temporary Storage (TS) - Road and rail transport","SK-Slovensko","Granted/Requested","APR Survey"]
["UCC Notification of Arrival (AN) - Maritime","SK-Slovensko","Granted","APR Survey"]
["UCC Presentation Notification (PN) - Maritime","SK-Slovensko","Granted/Requested","APR Survey"]
["UCC Temporary Storage (TS) - Maritime","SK-Slovensko","Granted/Requested","APR Survey"]

{"sheet":"AUX_List","index":29,"n_rows":5,"n_cols":1,"rows_kept":5,"cut":false,"hidden":true,"merged":[]}
["Progress"]
["Completed"]
["In progress"]
["Not started"]
["Not applicable"]

{"sheet":"ICS2(1)","index":30,"n_rows":32,"n_cols":32,"rows_kept":32,"cut":false,"hidden":true,"merged":[[3,5,3,6],[3,8,3,10],[3,12,3,13],[3,15,3,17],[3,19,3,20]]}
[]
[]
[null,null,null,null,null,"Technical Specs",null,null,"CT",null,null,null,"Deployment",null,null,"Migration",null,null,null,"Operations",null,null,"Web",null,"Notes",null,"Version information and issue date",null,null,"Project Mgr Details"]
[null,null,null,null,null,{"$f":"formats!#REF!","v":{"$error":"#REF!"}},null,null,{"$f":"formats!#REF!","v":{"$error":"#REF!"}},null,null,null,{"$f":"formats!#REF!","v":{"$error":"#REF!"}},null,null,{"$f":"formats!#REF!","v":{"$error":"#REF!"}},null,null,null,{"$f":"formats!#REF!","v":{"$error":"#REF!"}},null,null,"Web address of specifications for EO's"]
[null,null,{"$f":"formats!A20","v":0},"Filter",null,"Date","Status",null,"Start Date","End Date","Status",null,"Date","Status",null,"Start Date","End Date","Status",null,"Date","Status",null,"Web address",null,"Note/Comment",null,"Version Number","Issue Date",null,"Project Mgr Name","e-Mail","Phone"]
[null,null,{"$f":"formats!D3&\"-\"&formats!E3","v":"AT-Österreich"},null,null,"N/A","stable/final",null,"2021-05-20","2021-05-31","stable/final",null,"2021-06-06","stable/final",null,null,null,null,null,"2021-07-01","stable/final",null,"ICS2 - Import Control System (bmf.gv.at)",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Manfred Winterleitner ","manfred.winterleitner@bmf.gv.at","0043-1-51433-504157"]
[null,null,{"$f":"formats!D4&\"-\"&formats!E4","v":"BE-Belgique/België"},null,null,null,null,null,null,null,null,null,"2021-03-15","stable/final",null,null,null,null,null,"2021-03-15","stable/final",null,"https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Alejandro Maria Aragon","alejandro.mariaaragon@minfin.fed.be"]
[null,null,{"$f":"formats!D5&\"-\"&formats!E5","v":"BG-България"},null,null,null,null,null,"2021-01-25","2021-04-10","stable/final",null,"2021-03-01","stable/final",null,null,null,null,null,"2021-04-17","stable/final",null,"https://ep.customs.bg/eportal/",null,"Deployed on production environment on 17.04.2021",null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Milena Ivanova","masp_bg@customs.bg","0035952689531"]
[null,null,{"$f":"formats!D6&\"-\"&formats!E6","v":"CY-Κύπρος"},null,null,"2020-01-31","stable/final",null,"2021-03-31","2021-05-14","stable/final",null,"2021-05-14","stable/final",null,null,null,null,null,"2021-10-01","stable/final",null,null,null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Zinonas Zinonos","zzinonos@customs.mof.gov.cy",35722601673]
[null,null,{"$f":"formats!D7&\"-\"&formats!E7","v":"CZ-Česká republika"},null,null,"2020-11-26","stable/final",null,"2021-01-01","2021-03-14","stable/final",null,"2021-03-15","stable/final",null,null,null,null,null,"2021-03-15","stable/final",null,null,null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Miloslav Šlegr","NPP.MASP@cs.mfcr.cz","420/261332631"]
[null,null,{"$f":"formats!D8&\"-\"&formats!E8","v":"DE-Deutschland"},null,null,null,null,null,null,null,null,null,"2021-03-06","stable/final",null,null,null,null,null,null,null,null,"Not applicable",null,"This Phase is already implemented as part of the national IT-System ATLAS (Release 9.1)",null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Michael Schröter","DIIB12.gzd@zoll.bund.de","0049(0)228/303-21096"]
[null,null,{"$f":"formats!D9&\"-\"&formats!E9","v":"DK-Danmark"},null,null,"2021-03-15","stable/final",null,"2021-08-30","2022-03-23","stable/final",null,"2021-10-01","stable/final",null,"2021-10-01","2021-10-01","stable/final",null,"2021-10-01","stable/final",null,null,null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Mette Ehlers Mikkelsen","Mette.Mikkelsen@ufst.dk","+45 7238 2223"]
[null,null,{"$f":"formats!D10&\"-\"&formats!E10","v":"EE-Eesti"},null,null,"2020-09-30","stable/final",null,null,null,"stable/final",null,"2021-03-15","stable/final",null,"2021-03-15","2021-03-15","stable/final",null,"2021-03-15","stable/final",null,"https://www.emta.ee/ariklient/toll-\nkaubavahetus/tolliinfosusteemid/tolliinfosusteemide-kasutajatele",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Leili Kristovald","ICS2-NPM-EE@emta.ee","00 372 676 1041"]
[null,null,{"$f":"formats!D11&\"-\"&formats!E11","v":"GR-Ελλάδα"},null,null,"2021-06-30","stable/final",null,"2021-09-30","2022-09-30","stable/final",null,"2021-09-30","stable/final",null,null,null,null,null,"2021-09-30","stable/final",null,"https://www.aade.gr/customs",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}}]
[null,null,{"$f":"formats!D12&\"-\"&formats!E12","v":"ES-España"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}}]
[null,null,{"$f":"formats!D13&\"-\"&formats!E13","v":"FI-Suomi/Finland"},null,null,"2020-03-31","stable/final",null,"2020-06-30","2021-03-31","stable/final",null,"2021-03-31","stable/final",null,"2021-03-31","2021-09-30","stable/final",null,"2021-03-31","stable/final",null,null,null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Leila Lappalainen","leila.lappalainen@tulli.fi"]
[null,null,{"$f":"formats!D14&\"-\"&formats!E14","v":"FR-France"},null,null,"NA",null,null,"NA","NA",null,null,"2021-03-31","stable/final",null,"2021-03-31","2021-03-31","stable/final",null,"2021-03-31","stable/final",null,"www.douane.gouv.fr  > Services et Aide > Tout sur les services et aides > EDI",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Office JCF 2 DGDDI","Veille-ics-dg@douane.finances.gouv.fr"]
[null,null,{"$f":"formats!D15&\"-\"&formats!E15","v":"HR-Hrvatska"},null,null,null,"stable/final",null,null,null,"stable/final",null,"2021-03-01","stable/final",null,null,"2021-10-01","stable/final",null,"2021-10-01","stable/final",null,"https://carina.gov.hr ",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Albert Đurđević","albert.durdevic@carina.hr ",38516211536]
[null,null,{"$f":"formats!D16&\"-\"&formats!E16","v":"HU-Magyarország"},null,null,"2020-01-01","stable/final",null,"2021-02-22","2021-03-08","stable/final",null,"2021-03-15","stable/final",null,null,null,null,null,"2021-03-15","stable/final",null,"https://openkkk.nav.gov.hu/default.aspx?RootFolder=%2FDokumentumok%2FSpecifik%C3%A1ci%C3%B3k&FolderCTID=&View=%7B33F087E2-CEC9-4020-A148-2852161E114C%7D",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Scodnik Balázs","uvk_mp_masp@nav.gov.hu",3614704296]
[null,null,{"$f":"formats!D17&\"-\"&formats!E17","v":"IE-Éire/Ireland"},null,null,"N/A","stable/final",null,"N/A","N/A","stable/final",null,"2021-03-15","stable/final",null,null,null,null,null,"2021-03-15","stable/final",null,"www.revenue.ie",null,"Link to EU Specs from Revenue Website",null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Paul Paxman","UCCITDev@revenue.ie"]
[null,null,{"$f":"formats!D18&\"-\"&formats!E18","v":"IT-Italia"},null,null,"Already in operation",null,null,"Already in operation",null,null,null,"2021-03-15","stable/final",null,null,null,null,null,null,null,null,"https://www.adm.gov.it/portale/web/guest/home",null,"Already in production environment",null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Sarah Melini","Sarah.Melini@adm.gov.it","+39 06 5024 6425"]
[null,null,{"$f":"formats!D19&\"-\"&formats!E19","v":"LT-Lietuva"},null,null,"2020-02-02","stable/final",null,"2020-11-01","2021-02-20","stable/final",null,"2021-03-14","stable/final",null,"2021-03-15","2021-09-30","stable/final",null,"2021-09-30","stable/final",null,"www.lrmuitine.lt",null,"Web Adres for EO is Central ICS2 system ",null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Vitalis Vareikis","UCC_ICS2_R1R2R3-LT@lrmuitine.lt",37052666144]
[null,null,{"$f":"formats!D20&\"-\"&formats!E20","v":"LU-Luxembourg"},null,null,"2021-01-25","stable/final",null,null,null,null,null,"2021-03-15","stable/final",null,null,null,null,null,"2021-03-15","stable/final",null,"https://douanes.public.lu/fr/services-ligne/edouanes/LUCCS/ics2.html",null,"No migration.",null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Robert Scheueren","it.npm@do.etat.lu","+352 621 306 782"]
[null,null,{"$f":"formats!D21&\"-\"&formats!E21","v":"LV-Latvija"},null,null,"2020-10-20","stable/final",null,"2021-02-15","2021-09-30","stable/final",null,"2021-08-10","stable/final",null,"N/A","N/A","stable/final",null,"2021-08-10","stable/final",null,"https://www.vid.gov.lv/lv/k%C4%81-lietot-emdas  ",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}}]
[null,null,{"$f":"formats!D22&\"-\"&formats!E22","v":"MT-Malta"},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"www.customs.gov.mt",null,"Launched on the 1st of october 2021",null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Marco Catania","marco.l.catania@gov.mt",35625685209]
[null,null,{"$f":"formats!D23&\"-\"&formats!E23","v":"NL-Nederland"},null,null,null,"stable/final",null,null,null,"stable/final",null,"2021-03-15","stable/final",null,"2021-03-15","2021-10-01","stable/final",null,"2021-03-15","stable/final",null,null,null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"National Helpdesk Dutch Customs"]
[null,null,{"$f":"formats!D24&\"-\"&formats!E24","v":"PL-Polska"},null,null,"2021-06-15","stable/final",null,"2021-07-12","2021-07-30","stable/final",null,"2021-10-01","stable/final",null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Beata Utylska","satos.ics2@mf.gov.pl","(+48) 12 62 90 201"]
[null,null,{"$f":"formats!D25&\"-\"&formats!E25","v":"PT-Portugal"},null,null,"2020-12-01","stable/final",null,"2021-02-01","2021-02-01","stable/final",null,"2021-03-14","stable/final",null,null,null,null,null,"2021-03-15","stable/final",null,"https://info-aduaneiro.portaldasfinancas.gov.pt/pt/informacao_aduaneira/Pages/default.aspx",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Ana Freitas Couto","Ana.Freitas.Couto@at.gov.pt","00351 218 813 872"]
[null,null,{"$f":"formats!D26&\"-\"&formats!E26","v":"RO-România "},null,null,null,null,null,"2021-09-01","2021-10-11","stable/final",null,"2021-10-01","stable/final",null,null,null,null,null,"2021-11-16","stable/final",null,"https://www.customs.ro/e-customs/ICS2/reglementari",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Loredana Iovu","loredana.iovu@customs.ro",40723220158]
[null,null,{"$f":"formats!D27&\"-\"&formats!E27","v":"SE-Sverige"},null,null,"NA",null,null,"NA",null,null,null,"2021-03-15","stable/final",null,null,null,null,null,"2021-03-15","stable/final",null,"https://www.tullverket.se/nyheter/nyheter/nyuppgiftslamningforpostochexpressforsandelserfraktademedflyg.5.422c8052175b1d827691fc0.html",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Johan Froby","underrattelseavd.npm.ics2@tullverket.se"]
[null,null,{"$f":"formats!D28&\"-\"&formats!E28","v":"SI-Slovenija"},null,null,"2019-10-01","stable/final",null,"2021-03-01","2021-03-13","stable/final",null,"2021-03-15","stable/final",null,"2021-03-15","2021-10-15","stable/final",null,"2021-10-15","stable/final",null,"e-Carina | FINANČNA UPRAVA REPUBLIKE SLOVENIJE (gov.si)",null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"M.Sc Milan Kušer","sd.fu@gov.si","00386 1/478 38 84"]
[null,null,{"$f":"formats!D29&\"-\"&formats!E29","v":"SK-Slovensko"},null,null,null,null,null,null,null,null,null,"2021-03-01","stable/final",null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},{"$f":"IF(#REF!=\"\",\"\",#REF!)","v":{"$error":"#REF!"}},null,"Igor Lalík","igor.lalik@financnasprava.sk"]